## WP-JAN (hidden)
LAMU COUNTY GOVERNMENT
F.Y 2019/2020
DEVELOPMENT BUDGET REQUISITION
MAIN CODE 321000000
HEAD CODE | TITLE | REQUISITION
MARCH
3212000000 | COUNTY EXECUTIVE SERVICES
| Construction of County Annex-Conditional Grant | 0
| Construction of Enforcement and Training (Command) Centers | 0
| Construction of Governors Residence phase one | 0
| construction of county headquartes phase one | 0
| Fire station | 0
| Construction of information centre at lamu town | 0
| Construction of information centre at witu | 0
| Purchase of Exchanges and other Communications Equipment | 0
| NET EXPENDITURE | 0
3213000000 | FINANCE
| Supply & Installation of weigh bridge for revenue centres | 0
0
3214000000 | AGRICULTURE & IRRIGATION
| Renovation of Training and Accommodation facility (old hostel and training Institution)at the ATC | 0
| Provision of certified maize seeds, NERICA seeds, cow peas and green grams | 2460000
| ASSDP | 0
| KENYA CLIMATE SMART | 0
| Purchase of Agricultural Machinery and Equipment | 0
| Procurement of Grafted cashewnut seedlings | 0
| Procurement of coconut seedlings | 0
2460000
3223000000 | WATER MANAGEMENT
| Extension of piped water - Barigoni to Mswakini | 0
| Overheads tank for witu | 0
| Extension of Water Project Bangure - Ndambwe | 0
| Desalinition Plant mkokoni | 0
| Desalination Plant | 0
| Constuction of boreholes | 0
| Constuction of boreholes | 0
| Construction of water pans at kiangwe | 0
| Water Supply and connection | 27793987
| Drilling of 10 Boreholes | 0
| Sefu to Sinambio water connection | 0
| Raskitau farm & livestock connection | 0
| Improvement of Lamu water supply sources | 0
| Sefu water project | 0
| Siyu Desalination plant and maintenance | 0
| feasibility study | 0
| NET EXPENDITURE | 27793987
3215000000 | LANDS
| Survey and Planning of Hidabu & Swafaa | 0
| Planning and tiitling of Baraka Town | 0
| Planning and survey | 0
| Survey and demarcation | 0
| Survey and Planning | 0
| Regulartion and titling at KIZIWA CHA PAKA | 0
| Planning & surveying of Majembeni town | 0
| Planning & surveying of Moa | 0
| Planning, Surveying, Regularization and issuance of titles at Kihongwe settlement scheme | 0
| Planning, survey & regularization of squatters in Amu Ranch & Adjacent public land | 0
| Survey & regularization of Hindi Township | 0
| Survey & regularization of Hongwe Centre | 0
| Survey & regularization of Muhamarani Centre | 0
| Planning, survey & regularization of Mararani village | 0
| Planning, survey & regularization of Kiwayu villages & farms | 0
| Survey & regularization of Katsaikakairu Centre | 0
| Planning, survey & regularization of Tewe Centre | 0
| Planning, survey & regularization of Kiangwe village & farms | 0
| Survey & regularization of Kiunga New Town | 0
| NET EXPENDITURE | 0
3216000000 | EDUCATION AND VOCATIONAL TRAINING
| 2 ECD Classrooms | 0
| ECD Classrooms | 703850.35
| Construction of ECD and Toilet | 2891068
| Construction of VIP Toilet | 0
| ECD Classes | 0
| ECD Classroom | 0
| ECD CLASSES - Lumshi,Jipendeni | 0
| Two ECD Classrooms | 0
| Construction of an ECD centre at Pate | 0
| Youth Polytechnics Grants | 0
| ECD EQUIPMENT, Learning and Teaching Material | 0
| Equipments for polytechnics | 0
| Education Promotion | 0
| Construction of ECD Centers and toilets-Mkunumbi, Matondoni, Upendo, Basuba, Ishakani, Hindi, Shella, Kizuke, Bomani Siyu and Katsakakairu | 0
| Toilets at ECD | 0
| Construction of ECD Centers | 0
| Youth Polytechnics Grants b | 0
| NET EXPENDITURE | 3594918.35
3224000000 | YOUTH, GENDER, CULTURE, SPORTS AND SOCIAL SERVICES
| Social Hall | 0
| construction of Social Hall | 0
| Social Hall Mkokoni | 0
| Social Hall | 0
| Social Hall-Ndau | 0
| Renovation and expansion of shella Social Hall | 0
| Social Hall | 0
| Youth Empowerment | 0
| Two 7 Aside Field | 0
| Development of ongoing PWD PROJECTS | 0
| Construction of a 7 Aside Field | 0
| Basket Ball pitch | 0
| Provision of Goalposts & Nets in Ten pitches | 0
| Levelling of Kiangwe Sports Grounds Plus Provision of Goalposts | 0
| Levelling of Siyu Sports Grounds | 0
| Purchase of Sports Equipment | 0
| ONGOING PROJECTS FOR PWD | 0
| Empowerment of People with Disabilities | 0
| Construction and Rehabilitation of Sports Facilities | 0
| Construction and Rehabilitation of Sports Facilities | 0
| Construction and Rehabilitation of Sports Facilities | 0
| Driving licence/coxwain | 0
| Women Empowerment | 0
| NET EXPENDITURE | 0
3217000000 | MEDICAL SERVICES
| Fencing Muhamarani Disspensary | 0
| Completion of siyu Health centre | 0
| Fencing of Uziwa Dispensary | 0
| Procurement of an advanced life Support ambulance 4x4 vehicle for Kiunga | 0
| Procurement of motorbike for Manda dispensary | 0
| Procurement of motorbike for Ishakani dispensary | 0
| NHIF Indigent cover for 16,500 households | 0
| Renovation of Pandanguo dispensary | 0
| Procurement of immunoanalyzer | 0
| Construction of Women and Children hospital | 0
| Construction of VIP latrines at Kiunga H/C | 0
| Procurement of an advanced life Support ambulance 4x4 vehicle for Faza Hospital | 0
| Construction of a dispensary at Wiyoni | 0
| Construction of a dispensary at Kashmir-Phase 1 | 0
| Construction of a dispensary at Mavuno | 0
| Construction and equipping of Uziwa dispensary laboratory | 0
| Shella incinerator | 0
| Construction of sanitary block at Hindi and water tower | 0
| Renovation of Witu outpatient block/variation | 0
| Renovation of King Fahd Hospital | 0
| Construction of perimeter wall at Kizingitini | 0
| Construction of new dispensary Hongwe & Mavuno | 0
| Purchase of Medical equipment; Ophthalmology, Dental and Physio | 0
| Furnishing of New building at King Fahd | 0
| Upgrading of Mokowe Health centre | 0
| Completion of Witu Accident & Emergency unit | 0
| Construction of perimeter wall at Faza SCH | 0
| Construction of Laundry & Kitchen at Faza SCH | 0
| Construction of Moa Dispensary | 0
| Construction of a dispensary at Chalaluma | 0
| Construction of Laundry at Mpeketoni | 0
| Construction of incinerators at Kiunga | 0
| Provision of VIP latrines at Sinambio | 0
| Construction of a dispensary at Kiangwe village | 0
| Completion of perimeter fence at Mpeketoni | 0
| Construction of OPD at Faza SCH and Extension of Maternity wing at Faza SCH | 0
| Construction of public toilets at Ras kitau and Manda | 0
| Construction of a dispensary at Siyu village | 0
| Construction of Kiunga Incinerator | 0
| Renovation for Dispensary | 0
| Construction of Delivery maternity at Muhamarani | 0
| Repair of Theatre Oxygen | 0
| Construction of Maternity | 0
| Construction of Maternity | 4055500
| Construction of Maternity at Witu | 0
| NET EXPENDITURE | 4055500
3225000000 | SANITATION & ENVIRONMENT
| Construction of perimeter wall at Shella Damping site | 0
| Establishment of cleansing unit- Provision of yard and equipments | 0
| Acquisition and fencing of waste disposal sites | 0
| Acquisition and fencing of waste disposal sites | 0
| Construction of modern toilets | 2510187.8
| NET EXPENDITURE | 2510187.8
3218000000 | TRADE
| Boda Boda shades in Hindi | 0
| Boda Boda shades in Hongwe | 0
| Women group shade(Ngoi trading centre) | 0
| Beautification of the Mkomani sea front | 0
| Construction of Majembeni Open Air Market phase II | 0
| Construction of Kizingitini Local Boat Building Shed | 0
| Construction of Boda Boda Shede at Mpeketoni | 0
| Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | 4867447
| Construction of Boda Boda Shed at Mtangawanda | 0
| Construction of Boda Boda Shed at Witu | 0
| NET EXPENDITURE | 4867447
3220000000 | LIVESTOSK, VETINANRY & COOP DEVELOMENT
| Renovation/construction of Slaughter House | 0
| Community Pasture and feed development project | 0
| Construct Mpeketoni Modern slaughter house | 0
| Livestock health improvement programme | 0
| Construction of Mpeketoni Slaughter house Phase I | 0
| Construction of Mpeketoni Slaughter house Phase II | 0
| SLAUGHTER HOUSE RAILS AT AMU | 0
| Construction of Kitumbini Cattle Dip | 0
| Construction of Nagele Auction yard | 0
| Construction of Pangani Cattle Dip | 0
| Construction of Perimeter fence for Mokowe Co-operative Office | 0
| Purchase of Veterinary Laboratories Equipment | 0
| Rehabilitation of Amu Slaughter House | 0
| NET EXPENDITURE | 0
3226000000 | FISHERIES
| Purchase of Fishing Gears | 0
| Purchase of collers | 0
| Construction of fisherman landing site (campsite) | 0
| Construction of step ladders at kiwayu Jetty | 0
| Construction of fisherman landing site (campsite) | 0
| Purchase of Fishing Gears | 0
| Completion of Kizingitini Ice Plant | 0
| ISHAKANI FISH LANDING SITE | 0
| NET EXPENDITURE | 0
3228000000 | INFRASTUCTURE
| Kizingitini /Mbwajumali -Mabiyu access road | 0
| Opening New roads at Ngoi | 0
| Cabros at Mpketoni Market | 0
| Opening Road from Nadhani to Kizuke | 0
| Opening of Kitamba - Kisauni road | 0
| Road and bridge repair Mugumoine and Mkondoni | 0
| Opening New roads at Manda Island | 0
| Nyongoro-chalaruma road | 0
| Maishamasha road | 0
| A7 JUCTION -SINAMBIO | 0
| Majembeni-Sinanbio road-1 | 0
| Majembeni-Sinanbio road-2 | 0
| Mpeketoni -ndambwe | 0
| Ndambwe-Bangure road | 0
| A7 JUCTION -Mokowe | 0
| Cabro works | 0
| Mpeketoni-bahari road | 0
| Purchase & installation of electric street lights | 0
| Siyu seawall | 0
| cabro/drainage/pavement | 0
| Maintainance of rooads from Fuel Levy 2018-19 | 0
| NET EXPENDITURE | 0
3228000000 | MUNICIPALITY
| Construction of Modern Market | 0
| Construction of Modern Market | 0
| NET EXPENDITURE | 0
| TOTAL EXPENDITURE | 45282040.15
COMPILED BY :
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….
APPROVED BY:
NAME:
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….

## LEDGER (hidden)
LAMU COUNTY GOVERNMENT
F.Y 2019/2020
DEVELOPMENT BUDGET CONTROL LEDGER
HEAD CODE | TITLE | DEVT ESTIMATES | REQUISITION |  |  |  |  | BALANCE
|  |  | JANUARY | FEBRUARY | MARCH
3212000000 | COUNTY EXECUTIVE SERVICES
| Construction of County Annex-Conditional Grant | #REF! | 0 | 0 | 22132070 |  |  | #REF!
| Construction of Enforcement and Training (Command) Centers | #REF! |  |  | 19899999.52 |  |  | #REF!
| Construction of Governors Residence phase one | #REF! | [5 empty] | #REF!
| construction of county headquartes phase one | #REF! | [5 empty] | #REF!
| Fire station | #REF! | [5 empty] | #REF!
| Construction of information centre at lamu town | #REF! | [5 empty] | #REF!
| Construction of information centre at witu | #REF! | [5 empty] | #REF!
| Purchase of Exchanges and other Communications Equipment | #REF! |  |  | 470960 |  |  | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 42503029.52 | 0 | 0 | #REF!
3213000000 | FINANCE
| Supply & Installation of weigh bridge for revenue centres | #REF! | [5 empty] | #REF!
|  | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
3214000000 | AGRICULTURE & IRRIGATION
| Renovation of Training and Accommodation facility (old hostel and training Institution)at the ATC | #REF! | [5 empty] | #REF!
| Provision of certified maize seeds, NERICA seeds, cow peas and green grams | #REF! |  |  |  |  | 2460000 | #REF!
| ASSDP | #REF! | [5 empty] | #REF!
| KENYA CLIMATE SMART | #REF! | [5 empty] | #REF!
| Purchase of Agricultural Machinery and Equipment | #REF! | [5 empty] | #REF!
| Procurement of Grafted cashewnut seedlings | #REF! | [5 empty] | #REF!
| Procurement of coconut seedlings | #REF! | [5 empty] | #REF!
0
|  | #REF! | 0 | 0 | 0 | 0 | 2460000 | #REF!
3223000000 | WATER MANAGEMENT
| Extension of piped water - Barigoni to Mswakini | #REF! | [5 empty] | #REF!
| Overheads tank for witu | #REF! | [5 empty] | #REF!
| Extension of Water Project Bangure - Ndambwe | #REF! | [5 empty] | #REF!
| Desalinition Plant mkokoni | #REF! | [5 empty] | #REF!
| Desalination Plant | #REF! |  | 7941139 |  |  |  | #REF!
| Constuction of boreholes | #REF! | [5 empty] | #REF!
| Constuction of boreholes | #REF! | [5 empty] | #REF!
| Construction of water pans at kiangwe | #REF! | [5 empty] | #REF!
| Water Supply and connection | #REF! |  |  |  |  | 27793987 | #REF!
| Drilling of 10 Boreholes | #REF! | [5 empty] | #REF!
| Sefu to Sinambio water connection | #REF! | [5 empty] | #REF!
| Raskitau farm & livestock connection | #REF! | [5 empty] | #REF!
| Improvement of Lamu water supply sources | #REF! | [5 empty] | #REF!
| Sefu water project | #REF! | [5 empty] | #REF!
| Siyu Desalination plant and maintenance | #REF! | [5 empty] | #REF!
| feasibility study | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 7941139 | 0 | 0 | 27793987 | #REF!
3215000000 | LANDS
| Survey and Planning of Hidabu & Swafaa | #REF! | [5 empty] | #REF!
| Planning and tiitling of Baraka Town | #REF! | [5 empty] | #REF!
| Planning and survey | #REF! | [5 empty] | #REF!
| Survey and demarcation | #REF! | [5 empty] | #REF!
| Survey and Planning | #REF! | [5 empty] | #REF!
| Regulartion and titling at KIZIWA CHA PAKA | #REF! | [5 empty] | #REF!
| Planning & surveying of Majembeni town | #REF! | [5 empty] | #REF!
| Planning & surveying of Moa | #REF! | [5 empty] | #REF!
| Planning, Surveying, Regularization and issuance of titles at Kihongwe settlement scheme | #REF! | [5 empty] | #REF!
| Planning, survey & regularization of squatters in Amu Ranch & Adjacent public land | #REF! | [5 empty] | #REF!
| Survey & regularization of Hindi Township | #REF! | [5 empty] | #REF!
| Survey & regularization of Hongwe Centre | #REF! | [5 empty] | #REF!
| Survey & regularization of Muhamarani Centre | #REF! | [5 empty] | #REF!
| Planning, survey & regularization of Mararani village | #REF! | [5 empty] | #REF!
| Planning, survey & regularization of Kiwayu villages & farms | #REF! | [5 empty] | #REF!
| Survey & regularization of Katsaikakairu Centre | #REF! | [5 empty] | #REF!
| Planning, survey & regularization of Tewe Centre | #REF! | [5 empty] | #REF!
| Planning, survey & regularization of Kiangwe village & farms | #REF! | [5 empty] | #REF!
| Survey & regularization of Kiunga New Town | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
3216000000 | EDUCATION AND VOCATIONAL TRAINING
| 2 ECD Classrooms | #REF! | [5 empty] | #REF!
| ECD Classrooms | #REF! |  | 826848 |  |  | 703850.35 | #REF!
| Construction of ECD and Toilet | #REF! |  |  |  |  | 2891068 | #REF!
| Construction of VIP Toilet | #REF! | [5 empty] | #REF!
| ECD Classes | #REF! | [5 empty] | #REF!
| ECD Classroom | #REF! | [5 empty] | #REF!
| ECD CLASSES - Lumshi,Jipendeni | #REF! | [5 empty] | #REF!
| Two ECD Classrooms | #REF! | [5 empty] | #REF!
| Construction of an ECD centre at Pate | #REF! | [5 empty] | #REF!
| Youth Polytechnics Grants | #REF! | [5 empty] | #REF!
| ECD EQUIPMENT, Learning and Teaching Material | #REF! | 1984894 |  |  |  |  | #REF!
| Equipments for polytechnics | #REF! | [5 empty] | #REF!
| Education Promotion | #REF! | [5 empty] | #REF!
| Construction of ECD Centers and toilets-Mkunumbi, Matondoni, Upendo, Basuba, Ishakani, Hindi, Shella, Kizuke, Bomani Siyu and Katsakakairu | #REF! | [5 empty] | #REF!
| Toilets at ECD | #REF! | [5 empty] | #REF!
| Construction of ECD Centers | #REF! | [5 empty] | #REF!
| Youth Polytechnics Grants b | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 1984894 | 826848 | 0 | 0 | 3594918.35 | #REF!
3224000000 | YOUTH, GENDER, CULTURE, SPORTS AND SOCIAL SERVICES
| Social Hall | #REF! | [5 empty] | #REF!
| construction of Social Hall | #REF! | [5 empty] | #REF!
| Social Hall Mkokoni | #REF! | [5 empty] | #REF!
| Social Hall | #REF! | [5 empty] | #REF!
| Social Hall-Ndau | #REF! | [5 empty] | #REF!
| Renovation and expansion of shella Social Hall | #REF! | [5 empty] | #REF!
| Social Hall | #REF! | [5 empty] | #REF!
| Youth Empowerment | #REF! | [5 empty] | #REF!
| Two 7 Aside Field | #REF! | [5 empty] | #REF!
| Development of ongoing PWD PROJECTS | #REF! | [5 empty] | #REF!
| Construction of a 7 Aside Field | #REF! | [5 empty] | #REF!
| Basket Ball pitch | #REF! | [5 empty] | #REF!
| Provision of Goalposts & Nets in Ten pitches | #REF! | [5 empty] | #REF!
| Levelling of Kiangwe Sports Grounds Plus Provision of Goalposts | #REF! | [5 empty] | #REF!
| Levelling of Siyu Sports Grounds | #REF! | [5 empty] | #REF!
| Purchase of Sports Equipment | #REF! | [5 empty] | #REF!
| ONGOING PROJECTS FOR PWD | #REF! | [5 empty] | #REF!
| Empowerment of People with Disabilities | #REF! | [5 empty] | #REF!
| Construction and Rehabilitation of Sports Facilities | #REF! | [5 empty] | #REF!
| Construction and Rehabilitation of Sports Facilities | #REF! | [5 empty] | #REF!
| Construction and Rehabilitation of Sports Facilities | #REF! | [5 empty] | #REF!
| Driving licence/coxwain | #REF! |  | 14040000 |  |  |  | #REF!
| Women Empowerment | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 14040000 | 0 | 0 | 0 | #REF!
3217000000 | MEDICAL SERVICES
| Fencing Muhamarani Disspensary | #REF! | [5 empty] | #REF!
| Completion of siyu Health centre | #REF! | [5 empty] | #REF!
| Fencing of Uziwa Dispensary | #REF! | [5 empty] | #REF!
| Procurement of an advanced life Support ambulance 4x4 vehicle for Kiunga | #REF! | [5 empty] | #REF!
| Procurement of motorbike for Manda dispensary | #REF! | [5 empty] | #REF!
| Procurement of motorbike for Ishakani dispensary | #REF! | [5 empty] | #REF!
| NHIF Indigent cover for 16,500 households | #REF! | [5 empty] | #REF!
| Renovation of Pandanguo dispensary | #REF! | [5 empty] | #REF!
| Procurement of immunoanalyzer | #REF! | [5 empty] | #REF!
| Construction of Women and Children hospital | #REF! | [5 empty] | #REF!
| Construction of VIP latrines at Kiunga H/C | #REF! | [5 empty] | #REF!
| Procurement of an advanced life Support ambulance 4x4 vehicle for Faza Hospital | #REF! |  |  |  | 9010000 |  | #REF!
| Construction of a dispensary at Wiyoni | #REF! | [5 empty] | #REF!
| Construction of a dispensary at Kashmir-Phase 1 | #REF! | [5 empty] | #REF!
| Construction of a dispensary at Mavuno | #REF! | [5 empty] | #REF!
| Construction and equipping of Uziwa dispensary laboratory | #REF! | [5 empty] | #REF!
| Shella incinerator | #REF! | [5 empty] | #REF!
| Construction of sanitary block at Hindi and water tower | #REF! | [5 empty] | #REF!
| Renovation of Witu outpatient block/variation | #REF! | [5 empty] | #REF!
| Renovation of King Fahd Hospital | #REF! | [5 empty] | #REF!
| Construction of perimeter wall at Kizingitini | #REF! | [5 empty] | #REF!
| Construction of new dispensary Hongwe & Mavuno | #REF! | [5 empty] | #REF!
| Purchase of Medical equipment; Ophthalmology, Dental and Physio | #REF! | [5 empty] | #REF!
| Furnishing of New building at King Fahd | #REF! | [5 empty] | #REF!
| Upgrading of Mokowe Health centre | #REF! | [5 empty] | #REF!
| Completion of Witu Accident & Emergency unit | #REF! | [5 empty] | #REF!
| Construction of perimeter wall at Faza SCH | #REF! | [5 empty] | #REF!
| Construction of Laundry & Kitchen at Faza SCH | #REF! | [5 empty] | #REF!
| Construction of Moa Dispensary | #REF! | [5 empty] | #REF!
| Construction of a dispensary at Chalaluma | #REF! | [5 empty] | #REF!
| Construction of Laundry at Mpeketoni | #REF! | [5 empty] | #REF!
| Construction of incinerators at Kiunga | #REF! | [5 empty] | #REF!
| Provision of VIP latrines at Sinambio | #REF! | [5 empty] | #REF!
| Construction of a dispensary at Kiangwe village | #REF! | [5 empty] | #REF!
| Completion of perimeter fence at Mpeketoni | #REF! | [5 empty] | #REF!
| Construction of OPD at Faza SCH and Extension of Maternity wing at Faza SCH | #REF! | [5 empty] | #REF!
| Construction of public toilets at Ras kitau and Manda | #REF! | [5 empty] | #REF!
| Construction of a dispensary at Siyu village | #REF! | [5 empty] | #REF!
| Construction of Kiunga Incinerator | #REF! | [5 empty] | #REF!
| Renovation for Dispensary | #REF! | [5 empty] | #REF!
| Construction of Delivery maternity at Muhamarani | #REF! | [5 empty] | #REF!
| Repair of Theatre Oxygen | #REF! | [5 empty] | #REF!
| Construction of Maternity | #REF! | [5 empty] | #REF!
| Construction of Maternity | #REF! |  |  |  |  | 4055500 | #REF!
| Construction of Maternity at Witu | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 9010000 | 4055500 | #REF!
3225000000 | SANITATION & ENVIRONMENT
| Construction of perimeter wall at Shella Damping site | #REF! | [5 empty] | #REF!
| Establishment of cleansing unit- Provision of yard and equipments | #REF! | [5 empty] | #REF!
| Acquisition and fencing of waste disposal sites | #REF! | [5 empty] | #REF!
| Acquisition and fencing of waste disposal sites | #REF! | [5 empty] | #REF!
| Construction of modern toilets | #REF! |  |  |  | 1437193 | 2510187.8 | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 1437193 | 2510187.8 | #REF!
3218000000 | TRADE
| Boda Boda shades in Hindi | #REF! | [5 empty] | #REF!
| Boda Boda shades in Hongwe | #REF! | [5 empty] | #REF!
| Women group shade(Ngoi trading centre) | #REF! | [5 empty] | #REF!
| Beautification of the Mkomani sea front | #REF! | [5 empty] | #REF!
| Construction of Majembeni Open Air Market phase II | #REF! | [5 empty] | #REF!
| Construction of Kizingitini Local Boat Building Shed | #REF! | [5 empty] | #REF!
| Construction of Boda Boda Shede at Mpeketoni | #REF! |  |  |  | 1963671.4 |  | #REF!
| Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | #REF! |  |  |  |  | 4867447 | #REF!
| Construction of Boda Boda Shed at Mtangawanda | #REF! |  |  |  | 1986500 |  | #REF!
| Construction of Boda Boda Shed at Witu | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 3950171.4 | 4867447 | #REF!
3220000000 | LIVESTOSK, VETINANRY & COOP DEVELOMENT
| Renovation/construction of Slaughter House | #REF! | [5 empty] | #REF!
| Community Pasture and feed development project | #REF! | [5 empty] | #REF!
| Construct Mpeketoni Modern slaughter house | #REF! | [5 empty] | #REF!
| Livestock health improvement programme | #REF! | [5 empty] | #REF!
| Construction of Mpeketoni Slaughter house Phase I | #REF! | [5 empty] | #REF!
| Construction of Mpeketoni Slaughter house Phase II | #REF! | [5 empty] | #REF!
| SLAUGHTER HOUSE RAILS AT AMU | #REF! | [5 empty] | #REF!
| Construction of Kitumbini Cattle Dip | #REF! | [5 empty] | #REF!
| Construction of Nagele Auction yard | #REF! | [5 empty] | #REF!
| Construction of Pangani Cattle Dip | #REF! | [5 empty] | #REF!
| Construction of Perimeter fence for Mokowe Co-operative Office | #REF! |  |  |  | 934472.8 |  | #REF!
| Purchase of Veterinary Laboratories Equipment | #REF! | [5 empty] | #REF!
| Rehabilitation of Amu Slaughter House | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 934472.8 | 0 | #REF!
3226000000 | FISHERIES
| Purchase of Fishing Gears | #REF! | [5 empty] | #REF!
| Purchase of collers | #REF! | [5 empty] | #REF!
| Construction of fisherman landing site (campsite) | #REF! | [5 empty] | #REF!
| Construction of step ladders at kiwayu Jetty | #REF! | [5 empty] | #REF!
| Construction of fisherman landing site (campsite) | #REF! | [5 empty] | #REF!
| Purchase of Fishing Gears | #REF! | [5 empty] | #REF!
| Completion of Kizingitini Ice Plant | #REF! | [5 empty] | #REF!
| ISHAKANI FISH LANDING SITE | #REF! | [5 empty] | #REF!
| NET EXPENDITURE | #REF! | 0 | 0 | 0 | 0 |  | #REF!
3228000000 | INFRASTUCTURE
| Kizingitini /Mbwajumali -Mabiyu access road | #REF! | [5 empty] | #REF!
| Opening New roads at Ngoi | #REF! | [5 empty] | #REF!
| Cabros at Mpketoni Market | #REF! | [5 empty] | #REF!
| Opening Road from Nadhani to Kizuke | #REF! | [5 empty] | #REF!
| Opening of Kitamba - Kisauni road | #REF! | [5 empty] | #REF!
| Road and bridge repair Mugumoine and Mkondoni | #REF! | [5 empty] | #REF!
| Opening New roads at Manda Island | #REF! | [5 empty] | #REF!
| Nyongoro-chalaruma road | #REF! | [5 empty] | #REF!
| Maishamasha road | #REF! | [5 empty] | #REF!
| A7 JUCTION -SINAMBIO | #REF! | [5 empty] | #REF!
| Majembeni-Sinanbio road-1 | #REF! | [5 empty] | #REF!
| Majembeni-Sinanbio road-2 | #REF! | [5 empty] | #REF!
| Mpeketoni -ndambwe | #REF! | [5 empty] | #REF!
| Ndambwe-Bangure road | #REF! | [5 empty] | #REF!
| A7 JUCTION -Mokowe | #REF! | [5 empty] | #REF!
| Cabro works | #REF! | [5 empty] | #REF!
| Mpeketoni-bahari road | #REF! | [5 empty] | #REF!
| Purchase & installation of electric street lights | #REF! | [5 empty] | #REF!
| Siyu seawall | #REF! | [5 empty] | #REF!
| cabro/drainage/pavement | #REF! | [5 empty] | #REF!
| Maintainance of rooads from Fuel Levy 2018-19 | #REF! | [5 empty] | #REF!
|  | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
3228000000 | MUNICIPALITY
| Construction of Modern Market | #REF! | [5 empty] | #REF!
| Construction of Modern Market | #REF! | [5 empty] | #REF!
0
|  | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
| TOTAL EXPENDITURE | #REF! | 1984894 | 22807987 | 42503029.52 | 15331837.2 | 45282040.15 | #REF!
COMPILED BY : | [6 empty] | 127909787.87
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….
APPROVED BY:
NAME:
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….

## PROJECT STATUS
PROJECT STATUS AS AT 30TH JUNE 2020
PROJECT NAME | HEAD CODE | ESTIMATES | AMOUNT PAID | LEVEL OF COMPLETION | REASON FOR DELAY
COUNTY EXECUTIVE
Construction of County Annex-Conditional Grant | County Headquarters -Mokowe | 121000000 | 0 | 0%
Construction of Enforcement and Training (Command) Centers | County Headquarters - Port Road Junction | 20000000 | 19899999.52 | 99.5%
Construction of Governors Residence phase one | County headquarters | 45000000 | 0 | 0%
construction of county headquartes phase one | County headqurters | 56000000 | 31987330 | 57.12%
Fire station | County headquarters | 2000008 | 0 | 0%
Construction of information centre at lamu town | Mkomani | 989376 | 989376 | 100%
Construction of information centre at witu | Witu | 696000 | 0 | 0%
Purchase of Exchanges and other Communications Equipment | County headquarters | 1000000 | 470960 | 47.1%
GROSS EXPENDITURE… KSH |  | 246685384 | 53347665.52 | 21.63%
FINANCE
Instalation of witu weigh bridge | Witu | 4100000 |  | 0%
GROSS EXPENDITURE… KSH
Net District / Location 32100001 .. .. .. … KSH
Total Net Expenditure Vote R3213 |  | 4100000 | 0 | 0%
AGRICULTURE AND IRRIGATION
Renovation of Training and Accommodation facility (old hostel and training Institution)at the ATC | ATC, Mpeketoni | 5000000 |  | 0%
Provision of certified maize seeds, NERICA seeds, cow peas and green grams | County wide | 13000000 | 13503138.45 | 103.9%
ASSDP | Witu, Mkunumbi, Bahari, Hindi, Faza and Kiunga Ward | 27441632 | 8919797 | 32.5%
KENYA CLIMATE SMART | Mkomani,, Shella, Witu, Mkunumbi, Bahari, Hongwe, Hindi, Faza, Basuba and Kiunga Ward | 122000000 | 71690680.35 | 58.76%
Purchase of Agricultural Machinery and Equipment | witu,mpeketoni,hindi,faza,kiunga | 0 | 0 | #DIV/0!
Procurement of Grafted cashewnut seedlings | County Wide | 860000 | 860000 | 100%
Procurement of coconut seedlings | county wide | 1600000 | 1600000 | 100%
GROSS EXPENDITURE… KSH |  | 169901632 | 96573615.8 | 56.84%
LANDS AND PHYSICAL PLANNING
Survey and Planning of Hidabu & Swafaa | Hidabu | 7000000 | 2746880 | 39.24%
Planning and tiitling of Baraka Town | Baraka | 3000000 | 0 | 0%
Planning and survey | Bomani town and Mini Valley | 4000000 | 3960000 | 99%
Survey and demarcation | Kihongwe Town | 3000000 | 0 | 0%
Survey and Planning | Kiangwe and Basuba | 5000000 | 3489280 | 69.79%
Regulartion and titling at KIZIWA CHA PAKA | WITU | 5000000 | 2686560 | 53.73%
Planning & surveying of Majembeni town |  | 2000000 | 0 | 0%
Planning & surveying of Moa |  | 2000000 | 0 | 0%
Planning, Surveying, Regularization and issuance of titles at Kihongwe settlement scheme | Bahari | 20000000 | 17490480 | 87.45%
Planning, survey & regularization of squatters in Amu Ranch & Adjacent public land | Mkunumbi | 11960000 | 0 | 0%
Survey & regularization of Hindi Township | Hindi | 6794955 | 2717982.08 | 40%
Survey & regularization of Hongwe Centre | Hongwe | 3140955 | 1256382.08 | 40%
Survey & regularization of Muhamarani Centre | Mkunumbi | 5170955 | 2068382.08 | 40%
Planning, survey & regularization of Mararani village | Shella | 7928032 | 0 | 0%
Planning, survey & regularization of Kiwayu villages & farms | Kiunga | 11615747 | 3484724.1 | 30%
Survey & regularization of Katsaikakairu Centre | Witu | 8885600 | 8885600 | 100%
Planning, survey & regularization of Tewe Centre | Bahari | 12748400 | 12748400 | 100%
Planning, survey & regularization of Kiangwe village & farms | Basuba | 11356400 | 0 | 0%
Survey & regularization of Kiunga New Town | Kiunga | 10045600 | 10045600 | 100%
GROSS EXPENDITURE… KSH |  | 140646644 | 71580270.34 | 50.89%
EDUCATION AND VOCATIONAL TRAINING
2 ECD Classrooms | Hongwe | 6600000 | 0 | 0%
ECD Classrooms | Sikomani ECD | 3300000 | 826848 | 25.06%
Construction of ECD and Toilet | Juhudi and Mangu Primary | 9000000 | 7180381.2 | 79.78%
Construction of VIP Toilet | Mikinduni ECD | 1500000 | 1237743.8 | 82.52%
ECD Classes | Lake Kenyatta | 3300000 | 0 | 0%
ECD Classroom | Mangai and Kiangwe | 4000000 | 0 | 0%
ECD CLASSES - Lumshi,Jipendeni | WITU | 6600000 | 0 | 0%
Two ECD Classrooms | Tangeni and Thaku Thaku | 6600000 | 0 | 0%
Construction of an ECD centre at Pate |  | 3000000 | 0 | 0%
Youth Polytechnics Grants |  | 41288298 | 0 | 0%
ECD EQUIPMENT, Learning and Teaching Material | All Wards | 12541623 | 7661794 | 61.09%
Equipments for polytechnics | county wide | 9100000 | 0 | 0%
Education Promotion | All Wards | 2000000 | 0 | 0%
Construction of ECD Centers and toilets-Mkunumbi, Matondoni, Upendo, Basuba, Ishakani, Hindi, Shella, Kizuke, Bomani Siyu and Katsakakairu | Basuba, Kiunga, Hindi, Shella and Hongwe | 33000000 | 2797805 | 8.478%
Toilets at ECD | Hongwe | 4984000 |  | 0%
Construction of ECD Centers | Moa ECD classroom | 262146 | 262145 | 100%
| Ndeu ECD classroom | 307724 | 307724.8 | 100%
| Construction of madina ecd classroom cum office | 826848 | 0 | 0%
| Construction of ecd classroom /office at madina | 191980 | 191980 | 100%
Youth Polytechnics Grants b | Countywide | 31210000 | 31210000 | 100%
GROSS EXPENDITURE… KSH |  | 179612619 | 51676421.8 | 28.77%
MEDICAL SERVICES
Fencing Muhamarani Disspensary | Muhamarani | 1500000 | 0 | 0%
Completion of siyu Health centre | FAZA | 10000000 | 0 | 0%
Fencing of Uziwa Dispensary | Uziwa | 1000000 | 0 | 0%
Procurement of an advanced life Support ambulance 4x4 vehicle for Kiunga | Kiunga | 8000000 | 0 | 0%
Procurement of motorbike for Manda dispensary | Shella | 150000 | 0 | 0%
Procurement of motorbike for Ishakani dispensary | Kiunga | 150000 | 0 | 0%
NHIF Indigent cover for 16,500 households | Countywide | 120000000 | 120000000 | 100%
Renovation of Pandanguo dispensary | Witu | 2500000 | 0 | 0%
Procurement of immunoanalyzer | Hindi | 6000000 | 0 | 0%
Construction of Women and Children hospital | Bahari | 80000000 | 28296343.7 | 35.37%
Construction of VIP latrines at Kiunga H/C | Kiunga | 1000000 | 0 | 0%
Procurement of an advanced life Support ambulance 4x4 vehicle for Faza Hospital | Faza | 10000000 | 9010000 | 90.1%
Construction of a dispensary at Wiyoni | Mkomani | 7000000 | 0 | 0%
Construction of a dispensary at Kashmir-Phase 1 | Mkomani | 8000000 | 0 | 0%
Construction of a dispensary at Mavuno | Mkunumbi | 6000000 | 0 | 0%
Construction and equipping of Uziwa dispensary laboratory | Mkunumbi | 4000000 | 0 | 0%
Shella incinerator | Shella | 1000000 | 0 | 0%
Construction of sanitary block at Hindi and water tower | Hindi | 3000000 | 629575.5 | 20.99%
Renovation of Witu outpatient block/variation | Witu | 4230969 | 0 | 0%
Renovation of King Fahd Hospital | Mkomani | 5000000 | 0 | 0%
Construction of perimeter wall at Kizingitini | Faza | 3000000 | 0 | 0%
Construction of new dispensary Hongwe & Mavuno | Hongwe & Mkunumbi | 6000000 | 3988865.7 | 66.48%
Purchase of Medical equipment; Ophthalmology, Dental and Physio | Mkomani | 5000000 | 850000 | 17%
Furnishing of New building at King Fahd | Mkomani | 4319512 | 0 | 0%
Upgrading of Mokowe Health centre | Hindi | 1533935 | 0 | 0%
Completion of Witu Accident & Emergency unit | Witu | 1206159 | 778574 | 64.55%
Construction of perimeter wall at Faza SCH | Faza | 2598723 | 0 | 0%
Construction of Laundry & Kitchen at Faza SCH | Faza | 1405923 | 0 | 0%
Construction of Moa Dispensary | Witu | 665359 | 0 | 0%
Construction of a dispensary at Chalaluma | Witu | 6000000 | 0 | 0%
Construction of Laundry at Mpeketoni | Bahari | 5000000 | 0 | 0%
Construction of incinerators at Kiunga | Kiunga | 970688 | 0 | 0%
Provision of VIP latrines at Sinambio | Witu | 126475 | 0 | 0%
Construction of a dispensary at Kiangwe village | Bahari | 1195588 | 0 | 0%
Completion of perimeter fence at Mpeketoni | Bahari | 2177842 | 0 | 0%
Construction of OPD at Faza SCH and Extension of Maternity wing at Faza SCH | Faza | 4547086 | 4547086 | 100%
Construction of public toilets at Ras kitau and Manda | Shella | 741185 | 0 | 0%
Construction of a dispensary at Siyu village | Faza | 4965207 | 4636106 | 93.37%
Construction of Kiunga Incinerator | Kiunga | 681268 | 0 | 0%
Renovation for Dispensary |  | 134930 | 0 | 0%
Construction of Delivery maternity at Muhamarani | Mkunumbi | 128180 | 0 | 0%
Repair of Theatre Oxygen |  | 350000 | 0 | 0%
Construction of Maternity |  | 128180 | 0 | 0%
Construction of Maternity |  | 4055500 | 4055500 | 100%
Construction of Maternity at Witu | Witu | 778575 | 0
GROSS EXPENDITURE… KSH |  | 336241284 | 176792050.9 | 52.58%
TRADE
Boda Boda shades in Hindi | Hindi | 2000000 | 1714924.8 | 85.75%
Boda Boda shades in Hongwe | Hongwe | 2000000 | 1751268 | 87.56%
Women group shade(Ngoi trading centre) | Bahari | 2000000 | 1932093.66 | 96.6%
Beautification of the Mkomani sea front | Mkomani | 400000 | 0 | 0%
Construction of Majembeni Open Air Market phase II | Mkunumbi | 6500000 | 3517940.54 | 54.12%
Construction of Kizingitini Local Boat Building Shed | Faza | 3000000 | 2447646 | 81.59%
Construction of Boda Boda Shede at Mpeketoni | BAHARI | 2000000 | 1963671.4 | 98.18%
Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | BAHARI | 6000000 | 5849047 | 97.48%
Construction of Boda Boda Shed at Mtangawanda | FAZA | 2000000 | 1986500 | 99.33%
Construction of Boda Boda Shed at Witu | WITU | 2000000 | 1713237.6 | 85.66%
GROSS EXPENDITURE… KSH |  | 27900000 | 22876329 | 81.99%
LIVESTOCK
Renovation/construction of Slaughter House | Mokowe Town | 6000000 | 0 | 0%
Community Pasture and feed development project | Witu, Faza | 3000000 | 0 | 0%
Construct Mpeketoni Modern slaughter house | Bahari | 3000000 | 677904 | 22.6%
Livestock health improvement programme | Countywide | 6000000 | 3657000 | 60.95%
Construction of Mpeketoni Slaughter house Phase I | Bahari | 698658 | 0 | 0%
Construction of Mpeketoni Slaughter house Phase II | Bahari | 3000000 | 0 | 0%
SLAUGHTER HOUSE RAILS AT AMU | Amu | 2200000 | 1161021.6 | 52.77%
Construction of Kitumbini Cattle Dip | Witu | 4000000 | 0 | 0%
Construction of Nagele Auction yard | Witu | 9478595 | 0 | 0%
Construction of Pangani Cattle Dip | Witu | 1040000 | 924885.4 | 88.93%
Construction of Perimeter fence for Mokowe Co-operative Office | Mokowe - Hindi | 1200000 | 1144432.8 | 95.37%
Purchase of Veterinary Laboratories Equipment | County wide | 1400000 | 1397000 | 99.79%
Rehabilitation of Amu Slaughter House | Amu | 2000000 | 0 | 0%
GROSS EXPENDITURE… KSH |  | 43017253 | 8962243.8 | 20.83%
WATER
Extension of piped water - Barigoni to Mswakini | Bargoni to Mswakini | 3000000 | 0 | 0%
Overheads tank for witu | Witu | 1500000 | 0 | 0%
Extension of Water Project Bangure - Ndambwe | Mkunumbi | 6000000 | 0 | 0%
Desalinition Plant mkokoni | Kiunga | 10000000 | 1359054.5 | 13.59%
Desalination Plant | Mtangawanda | 10000000 | 7941139 | 79.41%
Constuction of boreholes | Basuba | 7000000 | 0 | 0%
Constuction of boreholes | Hongwe | 10000000 | 0 | 0%
Construction of water pans at kiangwe | Basuba | 7000000 | 0 | 0%
Water Supply and connection | Faza and kiunga | 90000000 | 53414563.24 | 59.35%
Drilling of 10 Boreholes | Hongwe | 7200000 | 0 | 0%
Sefu to Sinambio water connection | Hongwe | 7500000 | 0 | 0%
Raskitau farm & livestock connection | Shella | 5000000 | 0 | 0%
Improvement of Lamu water supply sources | Mkomani | 6000000 | 0 | 0%
Sefu water project | Hongwe | 2009961 | 0 | 0%
Siyu Desalination plant and maintenance | Faza | 2462112 | 0 | 0%
feasibility study | lamu west | 8000000 | 0 | 0%
GROSS EXPENDITURE… KSH |  | 182672073 | 62714756.74 | 34.33%
GENDER AND YOUTH
Social Hall | Lake amu | 5000000 | 4059291.25 | 81.19%
construction of Social Hall | Hindi Town | 5000000 | 3073959.4 | 61.48%
Social Hall Mkokoni | Kiunga | 5000000 | 0 | 0%
Social Hall | Shanga Rubu | 5000000 | 3372409.8 | 67.45%
Social Hall-Ndau | Kiunga | 3000000 | 0 | 0%
Renovation and expansion of shella Social Hall | Shella | 5000000 | 0 | 0%
Social Hall | Mokowe Town | 5000000 | 1364097.36 | 27.28%
Youth Empowerment | All wards | 5000000 | 5000000 | 100%
Two 7 Aside Field | Mkomani | 29000000 | 0 | 0%
Development of ongoing PWD PROJECTS | Bahari | 3500000 | 0 | 0%
Construction of a 7 Aside Field | Shella | 14000000 | 0 | 0%
Basket Ball pitch | Mkomani | 1500000 | 0 | 0%
Provision of Goalposts & Nets in Ten pitches | All the Wards | 750000 | 712000 | 94.93%
Levelling of Kiangwe Sports Grounds Plus Provision of Goalposts | Basuba Ward | 250000 | 0 | 0%
Levelling of Siyu Sports Grounds | Faza Ward | 1500000 | 0 | 0%
Purchase of Sports Equipment | All Wards | 500000 | 500000 | 100%
ONGOING PROJECTS FOR PWD | BAHARI | 2000000 | 0 | 0%
Empowerment of People with Disabilities | Countywide | 5000000 | 5000000 | 100%
Construction and Rehabilitation of Sports Facilities | FAZA | 3000000 | 2994120 | 99.8%
Construction and Rehabilitation of Sports Facilities | MKOMANI | 3000000 | 936909 | 31.23%
Construction and Rehabilitation of Sports Facilities | Bahari | 4000000 | 0 | 0%
Driving licence/coxwain | Countywide | 14040000 | 14040000 | 100%
Women Empowerment | Countywide | 4756840 | 4756840.45 | 100%
GROSS EXPENDITURE… KSH |  | 124796840 | 45809627.26 | 36.71%
PUBLIC HEALTH
Construction of perimeter wall at Shella Damping site | Shella | 581390.08 | 0
Establishment of cleansing unit- Provision of yard and equipments | Headquarters | 3000000 | 0
Acquisition and fencing of waste disposal sites | Bahari | 1000000 | 0
Acquisition and fencing of waste disposal sites | Hindi | 1000000 | 0
Construction of modern toilets | All Wards | 26000000 | 12065565.2 | 46.41%
GROSS EXPENDITURE… KSH |  | 31581390.08 | 12065565.2 | 46.41%
FISHERIES
Purchase of Fishing Gears | COUNTY WIDE | 10000000 | 8889400 | 88.89%
Purchase of collers | Countywide | 2000000 | 0 | 0%
Construction of fisherman landing site (campsite) | Rubu , Mambore and Mvundeni | 2000000 | 0 | 0%
Construction of step ladders at kiwayu Jetty | Kiunga | 1500000 | 0 | 0%
Construction of fisherman landing site (campsite) | Mtangawanda, Kiwayuu and Kipungani | 5000000 | 0 | 0%
Purchase of Fishing Gears | County wide | 5000000 | 3870000 | 77.4%
Completion of Kizingitini Ice Plant | Kizingitini - Faza | 11521643 | 0 | 0%
ISHAKANI FISH LANDING SITE | KIUNGA | 76560 | 76560 | 100%
GROSS EXPENDITURE… KSH |  | 37098203 | 12835960 | 34.6%
INFRASTRUCTURE
Kizingitini /Mbwajumali -Mabiyu access road | Faza | 4550000 | 4295634 | 94.41%
Opening New roads at Ngoi | Bahari | 6000000 | 5973735 | 99.56%
Cabros at Mpketoni Market | Bahari | 17000000 | 6170805.6 | 36.3%
Opening Road from Nadhani to Kizuke | Mkunumbi | 5000000 | 4708029 | 94.16%
Opening of Kitamba - Kisauni road | Kitamba - Kisauni | 5000000 | 0 | 0%
Road and bridge repair Mugumoine and Mkondoni | Hongwe | 10000000 | 4880664 | 48.81%
Opening New roads at Manda Island | Shella | 31900000 | 31900000 | 100%
Nyongoro-chalaruma road | WITU | 5864936.8 | 5415045 | 92.33%
Maishamasha road | WITU | 8086661.6 | 7498623 | 92.73%
A7 JUCTION -SINAMBIO | Hongwe | 8755580.24 |  | 0%
Majembeni-Sinanbio road-1 | Hongwe | 9844838.8 | 9783788 | 99.38%
Majembeni-Sinanbio road-2 | Hongwe | 7930920 | 7323223 | 92.34%
Mpeketoni -ndambwe | Mkunumbi | 8426416.32 | 8399355 | 99.68%
Ndambwe-Bangure road | Mkunumbi | 3637365.6 |  | 0%
A7 JUCTION -Mokowe | Hindi | 8479659.76 | 8461216 | 99.78%
Cabro works | Mkomani | 6716718.72 |  | 0%
Mpeketoni-bahari road | Bahari | 5926220.76 | 6151896 | 103.8%
Purchase & installation of electric street lights | County wide | 37928165 |  | 0%
Siyu seawall | Faza | 10000000 |  | 0%
cabro/drainage/pavement | County wide | 38000000 | 4985961 | 13.12%
Maintainance of rooads from Fuel Levy 2018-19 | Kiangwe -basuba roads | 7246044 | 7246044 | 100% | FUEL LEVY
| A7 JUNCTION -Sinambio road | 11950236 | 14604164 | 122.2% | FUEL LEVY
| Countywide | 4632525
GROSS EXPENDITURE… KSH |  | 262876288.6 | 137798182.6 | 52.42%
MUNICIPALITY
Construction of Modern Market | Mokowe | 50000000 |  | 0%
Construction of Modern Market | Mkomani | 48247400 | 14374862.6 | 29.79%
GROSS EXPENDITURE… KSH |  | 98247400 | 14374862.6 | 0.29794
Gross Development Total |  | 1885377010.68 | 767407551.56 | 40.7%

## Sheet2 (hidden)
DEVELOPMENT PAYMENT VOURCHERS FOR REQUISITION
NO. | PAYEE | DEPARTMENT | DESCRIPTION | AMOUNT
1 | M/S KEREY KAYU GENERAL CONTRACTORS | EDUCATION | CONSTRUCTION OF ECD CLASSROM CUM OFFICE AT MOA | 262145.55
2 | MS SKYLINE GEN SUPPLIERS LTD | PUBLIC HEALTH | CONSTRUCTION OF MODERN TOILET AT SIYU | 1250642.4
3 | MS BIMSPORT MAINTENANCE AGENCY LTD | PUBLIC HEALTH | PROPOSED MATERNITY WING AND RENOVATION OF THE EXISTING BUILDING AT MPEKETON SUB COUNTY AGENCY LTD | 4055500
4 | MS ROPISA KENYA LTD | EDUCATION | CONSTRUCTION OF ECD CLASSROM AT MADINA | 191980
5 | M/S SKYLINE GEN SUPPLIERS LTD | EDUCATION | CONSTRUCTION OF MODERN TOILET AT FAZA | 1259545.4
6 | M/S SKYLINE GEN SUPPLIERS LTD | EDUCATION | CONSTRUCTION OF ECD CLASSROM AT NDEU | 249724.8
7 | M/S MTWANGU GENERAL SUPPLIERS | TRADE | CONTRACTION OF JUA KALI SHED KIANGWE | 4867447
8 | DAVIS AND SHARTLIFF | WATER | DESALINATION PLANT FOR KIUNGA KIZINGITINI AND NDAU | 27793987
9 | M/S ABUZAHI GEN SUPPLY | EDUCATION | CONSTRUCTION OF ECD CLASSROM AND 2 DOOR VIP TOILET AT ISHAKANI | 2891068
10 | DHULKIFLI ABDALLAH | AGRICULTURE | SUPPLY OF 20,000 COCONUT SEEDLING FOR FARMERS | 1600000
11 | MPEKETONI MODERN TECHNOLOGY | AGRICULTURE | SUPPLY OF CASHEWNUT SEEDS | 860000
TOTAL |  |  |  | 45282040.15

## Sheet1 (hidden)
LAMU COUNTY GOVERNMENT
F.Y 2019/2020
DEVELOPMENT BUDGET CONTROL LEDGER
HEAD CODE | TITLE | DEVT ESTIMATES | REQUISITION | [11 empty] | BALANCE
|  |  | JANUARY | FEBRUARY | MARCH |  |  | APRIL | MAY | JUNE
3212000000 | COUNTY EXECUTIVE SERVICES
| Construction of County Annex-Conditional Grant | 121000000 | 0 | 0 | [10 empty] | 121000000
| Construction of Enforcement and Training (Command) Centers | 20000000 |  |  | 19899999.52 | [8 empty] | 19899999.52 | 100000.48
| Construction of Governors Residence phase one | 45000000 | [11 empty] | 0 | 45000000
| construction of county headquartes phase one | 56000000 |  |  | 22132070 | [6 empty] | 9855260 |  | 31987330 | 24012670
| Fire station | 2000008 | [11 empty] | 0 | 2000008
| Construction of information centre at lamu town | 989376 | [9 empty] | 989376 |  | 989376 | 0
| Construction of information centre at witu | 696000 | [11 empty] | 0 | 696000
| Purchase of Exchanges and other Communications Equipment | 1000000 |  |  | 470960 | [8 empty] | 470960 | 529040
| NET EXPENDITURE | 246685384 | 0 | 0 | 42503029.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10844636 | 0 | 53347665.52 | 193337718.48
0
3213000000 | FINANCE | [12 empty] | 0
| Supply & Installation of weigh bridge for revenue centres | 4100000 | [11 empty] | 0 | 4100000
|  | 4100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000
3214000000 | AGRICULTURE & IRRIGATION
| Renovation of Training and Accommodation facility (old hostel and training Institution)at the ATC | 5000000 | [11 empty] | 0 | 5000000
| Provision of certified maize seeds, NERICA seeds, cow peas and green grams | 13000000 | [7 empty] | 2075000.45 | 11428138 |  |  | 13503138.45 | -503138.45
| ASSDP | 27441632 | [11 empty] | 0 | 27441632
| KENYA CLIMATE SMART | 122000000 | [11 empty] | 0 | 122000000
| Purchase of Agricultural Machinery and Equipment | 0 | [11 empty] | 0 | 0
| Procurement of Grafted cashewnut seedlings | 860000 |  |  |  |  | 860000 | [6 empty] | 860000 | 0
| Procurement of coconut seedlings | 1600000 |  |  |  |  | 1600000 | [6 empty] | 1600000 | 0
[14 empty] | 0 | 0
|  | 169901632 | 0 | 0 | 0 | 0 | 2460000 | 0 | 0 | 2075000.45 | 11428138 | 0 | 0 | 15963138.45 | 153938493.55
3223000000 | WATER MANAGEMENT
| Extension of piped water - Barigoni to Mswakini | 3000000 | [11 empty] | 0 | 3000000
| Overheads tank for witu | 1500000 | [11 empty] | 0 | 1500000
| Extension of Water Project Bangure - Ndambwe | 6000000 | [11 empty] | 0 | 6000000
| Desalinition Plant mkokoni | 10000000 | [9 empty] | 1359054.5 |  | 1359054.5 | 8640945.5
| Desalination Plant | 10000000 |  | 7941139 | [9 empty] | 7941139 | 2058861
| Constuction of boreholes | 7000000 | [11 empty] | 0 | 7000000
| Constuction of boreholes | 10000000 | [11 empty] | 0 | 10000000
| Construction of water pans at kiangwe | 7000000 | [11 empty] | 0 | 7000000
| Water Supply and connection | 90000000 |  |  |  |  | 27793987 | 12476132.5 |  |  | 1172441 | 11972002.74 |  | 53414563.24 | 36585436.76
| Drilling of 10 Boreholes | 7200000 | [11 empty] | 0 | 7200000
| Sefu to Sinambio water connection | 7500000 | [11 empty] | 0 | 7500000
| Raskitau farm & livestock connection | 5000000 | [11 empty] | 0 | 5000000
| Improvement of Lamu water supply sources | 6000000 | [11 empty] | 0 | 6000000
| Sefu water project | 2009961 | [11 empty] | 0 | 2009961
| Siyu Desalination plant and maintenance | 2462112 | [11 empty] | 0 | 2462112
| feasibility study | 8000000 | [11 empty] | 0 | 8000000
| NET EXPENDITURE | 182672073 | 0 | 7941139 | 0 | 0 | 27793987 | 12476132.5 | 0 | 0 | 1172441 | 13331057.24 | 0 | 62714756.74 | 119957316.26
3215000000 | LANDS
| Survey and Planning of Hidabu & Swafaa | 7000000 | [8 empty] | 2746880 |  |  | 2746880 | 4253120
| Planning and tiitling of Baraka Town | 3000000 | [11 empty] | 0 | 3000000
| Planning and survey | 4000000 | [8 empty] | 3960000 |  |  | 3960000 | 40000
| Survey and demarcation | 3000000 | [11 empty] | 0 | 3000000
| Survey and Planning | 5000000 | [8 empty] | 3489280 |  |  | 3489280 | 1510720
| Regulartion and titling at KIZIWA CHA PAKA | 5000000 | [8 empty] | 2686560 |  |  | 2686560 | 2313440
| Planning & surveying of Majembeni town | 2000000 | [11 empty] | 0 | 2000000
| Planning & surveying of Moa | 2000000 | [11 empty] | 0 | 2000000
| Planning, Surveying, Regularization and issuance of titles at Kiangwe settlement scheme | 20000000 | [8 empty] | 17490480 |  |  | 17490480 | 2509520
| Planning, survey & regularization of squatters in Amu Ranch & Adjacent public land | 11960000 | [11 empty] | 0 | 11960000
| Survey & regularization of Hindi Township | 6794955 | [5 empty] | 2717982.08 | [5 empty] | 2717982.08 | 4076972.92
| Survey & regularization of Hongwe Centre | 3140955 | [5 empty] | 1256382.08 | [5 empty] | 1256382.08 | 1884572.92
| Survey & regularization of Muhamarani Centre | 5170955 | [5 empty] | 2068382.08 | [5 empty] | 2068382.08 | 3102572.92
| Planning, survey & regularization of Mararani village | 7928032 | [11 empty] | 0 | 7928032
| Planning, survey & regularization of Kiwayu villages & farms | 11615747 | [5 empty] | 3484724.1 | [5 empty] | 3484724.1 | 8131022.9
| Survey & regularization of Katsaikakairu Centre | 8885600 | [5 empty] | 3554240 |  |  | 5331360 |  |  | 8885600 | 0
| Planning, survey & regularization of Tewe Centre | 12748400 | [5 empty] | 5099360 |  |  | 7649040 |  |  | 12748400 | 0
| Planning, survey & regularization of Kiangwe village & farms | 11356400 | [11 empty] | 0 | 11356400
| Survey & regularization of Kiunga New Town | 10045600 | [5 empty] | 4018240 |  |  | 6027360 |  |  | 10045600 | 0
0
0
| NET EXPENDITURE | 140646644 | 0 | 0 | 0 | 0 | 0 | 22199310.34 | 0 | 0 | 49380960 | 0 | 0 | 71580270.34 | 69066373.66
3216000000 | EDUCATION AND VOCATIONAL TRAINING
| 2 ECD Classrooms | 6600000 | [11 empty] | 0 | 6600000
| ECD Classrooms | 3300000 |  | 826848 | [9 empty] | 826848 | 2473152
| Construction of ECD and Toilet | 9000000 |  |  |  |  | 2891068 |  |  |  | 4289313.2 |  |  | 7180381.2 | 1819618.8
| Construction of VIP Toilet | 1500000 | [8 empty] | 1237743.8 |  |  | 1237743.8 | 262256.2
| ECD Classes | 3300000 | [11 empty] | 0 | 3300000
| ECD Classroom | 4000000 | [11 empty] | 0 | 4000000
| ECD CLASSES - Lumshi,Jipendeni | 6600000 | [11 empty] | 0 | 6600000
| Two ECD Classrooms | 6600000 | [11 empty] | 0 | 6600000
| Construction of an ECD centre at Pate | 3000000 | [11 empty] | 0 | 3000000
| Youth Polytechnics Grants | 41288298 | [11 empty] | 0 | 41288298
| ECD EQUIPMENT, Learning and Teaching Material | 12541623 | 1984894 |  |  |  |  | 3996900 |  | 1680000 |  |  |  | 7661794 | 4879829
| Equipments for polytechnics | 9100000 | [11 empty] | 0 | 9100000
| Education Promotion | 2000000 | [11 empty] | 0 | 2000000
| Construction of ECD Centers and toilets-Mkunumbi, Matondoni, Upendo, Basuba, Ishakani, Hindi, Shella, Kizuke, Bomani Siyu and Katsakakairu | 33000000 | [8 empty] | 2797805 |  |  | 2797805 | 30202195
| Toilets at ECD | 4984000 | [11 empty] | 0 | 4984000
| Construction of ECD Centers | 1588698 |  |  |  |  | 703850.35 | 58000 | [5 empty] | 761850.35 | 826847.65
| Youth Polytechnics Grants b | 31210000 | [11 empty] | 0 | 31210000
| NET EXPENDITURE | 179612619 | 1984894 | 826848 | 0 | 0 | 3594918.35 | 4054900 | 0 | 1680000 | 8324862 | 0 | 0 | 20466422.35 | 159146196.65 | 9416740.95
3224000000 | YOUTH, GENDER, CULTURE, SPORTS AND SOCIAL SERVICES | [14 empty] | 11049681.4
| Social Hall | 5000000 | [8 empty] | 4059291.25 |  |  | 4059291.25 | 940708.75
| construction of Social Hall | 5000000 | [8 empty] | 3073959.4 |  |  | 3073959.4 | 1926040.6
| Social Hall Mkokoni | 5000000 | [11 empty] | 0 | 5000000
| Social Hall | 5000000 | [8 empty] | 3372409.8 |  |  | 3372409.8 | 1627590.2
| Social Hall-Ndau | 3000000 | [11 empty] | 0 | 3000000
| Renovation and expansion of shella Social Hall | 5000000 | [11 empty] | 0 | 5000000
| Social Hall | 5000000 | [9 empty] | 1364097.36 |  | 1364097.36 | 3635902.64
| Youth Empowerment | 5000000 | [8 empty] | 5000000 |  |  | 5000000 | 0
| Two 7 Aside Field | 29000000 | [11 empty] | 0 | 29000000
| Development of ongoing PWD PROJECTS | 3500000 | [11 empty] | 0 | 3500000
| Construction of a 7 Aside Field | 14000000 | [11 empty] | 0 | 14000000
| Basket Ball pitch | 1500000 | [11 empty] | 0 | 1500000
| Provision of Goalposts & Nets in Ten pitches | 750000 | [8 empty] | 712000 |  |  | 712000 | 38000
| Levelling of Kiangwe Sports Grounds Plus Provision of Goalposts | 250000 | [11 empty] | 0 | 250000
| Levelling of Siyu Sports Grounds | 1500000 | [11 empty] | 0 | 1500000
| Purchase of Sports Equipment | 500000 | [6 empty] | 251500 |  | 248500 |  |  | 500000 | 0
| ONGOING PROJECTS FOR PWD | 2000000 | [11 empty] | 0 | 2000000
| Empowerment of People with Disabilities | 5000000 | [8 empty] | 5000000 |  |  | 5000000 | 0
| Construction and Rehabilitation of Sports Facilities | 3000000 |  |  |  |  | 2994120 | [6 empty] | 2994120 | 5880
| Construction and Rehabilitation of Sports Facilities | 3000000 | [8 empty] | 936909 |  |  | 936909 | 2063091
| Construction and Rehabilitation of Sports Facilities | 4000000 | [11 empty] | 0 | 4000000
| Driving licence/coxwain | 14040000 |  | 14040000 | [9 empty] | 14040000 | 0
| Women Empowerment | 4756840 | [8 empty] | 4756840.45 |  |  | 4756840.45 | -0.45
| NET EXPENDITURE | 124796840 | 0 | 14040000 | 0 | 0 | 2994120 | 0 | 251500 | 0 | 27159909.9 | 1364097.36 | 0 | 45809627.26 | 78987212.74
3217000000 | MEDICAL SERVICES
| Fencing Muhamarani Disspensary | 1500000 | [11 empty] | 0 | 1500000
| Completion of siyu Health centre | 10000000 | [11 empty] | 0 | 10000000
| Fencing of Uziwa Dispensary | 1000000 | [11 empty] | 0 | 1000000
| Procurement of an advanced life Support ambulance 4x4 vehicle for Kiunga | 8000000 | [11 empty] | 0 | 8000000
| Procurement of motorbike for Manda dispensary | 150000 | [11 empty] | 0 | 150000
| Procurement of motorbike for Ishakani dispensary | 150000 | [11 empty] | 0 | 150000
| NHIF Indigent cover for 16,500 households | 120000000 | [5 empty] | 120000000 | [5 empty] | 120000000 | 0
| Renovation of Pandanguo dispensary | 2500000 | [11 empty] | 0 | 2500000
| Procurement of immunoanalyzer | 6000000 | [11 empty] | 0 | 6000000
| Construction of Women and Children hospital | 80000000 | [7 empty] | 18821326.85 | 9284755 |  | 190261.85 | 28296343.7 | 51703656.3
| Construction of VIP latrines at Kiunga H/C | 1000000 | [11 empty] | 0 | 1000000
| Procurement of an advanced life Support ambulance 4x4 vehicle for Faza Hospital | 10000000 |  |  |  | 9010000 | [7 empty] | 9010000 | 990000
| Construction of a dispensary at Wiyoni | 7000000 | [11 empty] | 0 | 7000000
| Construction of a dispensary at Kashmir-Phase 1 | 8000000 | [11 empty] | 0 | 8000000
| Construction of a dispensary at Mavuno | 6000000 | [11 empty] | 0 | 6000000
| Construction and equipping of Uziwa dispensary laboratory | 4000000 | [11 empty] | 0 | 4000000
| Shella incinerator | 1000000 | [11 empty] | 0 | 1000000
| Construction of sanitary block at Hindi and water tower | 3000000 | [6 empty] | 629575.5 |  |  |  |  | 629575.5 | 2370424.5
| Renovation of Witu outpatient block/variation | 4230969 | [11 empty] | 0 | 4230969
| Renovation of King Fahd Hospital | 5000000 | [11 empty] | 0 | 5000000
| Construction of perimeter wall at Kizingitini | 3000000 | [11 empty] | 0 | 3000000
| Construction of new dispensary Hongwe & Mavuno | 6000000 | [6 empty] | 3988865.7 |  |  |  |  | 3988865.7 | 2011134.3
| Purchase of Medical equipment; Ophthalmology, Dental and Physio | 5000000 | [5 empty] | 850000 | [5 empty] | 850000 | 4150000
| Furnishing of New building at King Fahd | 4319512 | [11 empty] | 0 | 4319512
| Upgrading of Mokowe Health centre | 1533935 | [11 empty] | 0 | 1533935
| Completion of Witu Accident & Emergency unit | 1206159 | [5 empty] | 778574 | [5 empty] | 778574 | 427585
| Construction of perimeter wall at Faza SCH | 2598723 | [11 empty] | 0 | 2598723
| Construction of Laundry & Kitchen at Faza SCH | 1405923 | [11 empty] | 0 | 1405923
| Construction of Moa Dispensary | 665359 | [11 empty] | 0 | 665359
| Construction of a dispensary at Chalaluma | 6000000 | [11 empty] | 0 | 6000000
| Construction of Laundry at Mpeketoni | 5000000 | [11 empty] | 0 | 5000000
| Construction of incinerators at Kiunga | 970688 | [11 empty] | 0 | 970688
| Provision of VIP latrines at Sinambio | 126475 | [11 empty] | 0 | 126475
| Construction of a dispensary at Kiangwe village | 1195588 | [11 empty] | 0 | 1195588
| Completion of perimeter fence at Mpeketoni | 2177842 | [11 empty] | 0 | 2177842
| Construction of OPD at Faza SCH and Extension of Maternity wing at Faza SCH | 4547086 | [8 empty] | 3215406 |  | 1331680 | 4547086 | 0
| Construction of public toilets at Ras kitau and Manda | 741185 | [11 empty] | 0 | 741185
| Construction of a dispensary at Siyu village | 4965207 | [8 empty] | 4636106 |  |  | 4636106 | 329101
| Construction of Kiunga Incinerator | 681268 | [11 empty] | 0 | 681268
| Renovation for Dispensary | 134930 | [11 empty] | 0 | 134930
| Construction of Delivery maternity at Muhamarani | 128180 | [11 empty] | 0 | 128180
| Repair of Theatre Oxygen | 350000 | [11 empty] | 0 | 350000
| Construction of Maternity | 128180 | [11 empty] | 0 | 128180
| Construction of Maternity | 4055500 |  |  |  |  | 4055500 | [6 empty] | 4055500 | 0
| Construction of Maternity at Witu | 778575 | [11 empty] | 0 | 778575
| NET EXPENDITURE | 336241284 | 0 | 0 | 0 | 9010000 | 4055500 | 121628574 | 4618441.2 | 18821326.85 | 17136267 | 0 | 1521941.85 | 176792050.9 | 159449233.1
3225000000 | SANITATION & ENVIRONMENT
| Construction of perimeter wall at Shella Damping site | 581390.08 | [11 empty] | 0 | 581390.08
| Establishment of cleansing unit- Provision of yard and equipments | 3000000 | [11 empty] | 0 | 3000000
| Acquisition and fencing of waste disposal sites | 1000000 | [11 empty] | 0 | 1000000
| Acquisition and fencing of waste disposal sites | 1000000 | [11 empty] | 0 | 1000000
| Construction of modern toilets | 26000000 |  |  |  | 1437193 | 2510187.8 |  |  | 6945672.4 |  | 1172512 |  | 12065565.2 | 13934434.8
| NET EXPENDITURE | 31581390.08 | 0 | 0 | 0 | 1437193 | 2510187.8 | 0 | 0 | 6945672.4 | 0 | 1172512 | 0 | 12065565.2 | 19515824.88
3218000000 | TRADE
| Boda Boda shades in Hindi | 2000000 | [8 empty] | 1714924.8 |  |  | 1714924.8 | 285075.2
| Boda Boda shades in Hongwe | 2000000 | [8 empty] | 1751268 |  |  | 1751268 | 248732
| Women group shade(Ngoi trading centre) | 2000000 | [8 empty] | 1932093.66 |  |  | 1932093.66 | 67906.34
| Beautification of the Mkomani sea front | 400000 | [11 empty] | 0 | 400000
| Construction of Majembeni Open Air Market phase II | 6500000 | [6 empty] | 3212113.08 |  | 305827.46 |  |  | 3517940.54 | 2982059.46
| Construction of Kizingitini Local Boat Building Shed | 3000000 | [6 empty] | 2447646 |  |  |  |  | 2447646 | 552354
| Construction of Boda Boda Shede at Mpeketoni | 2000000 |  |  |  | 1963671.4 | [7 empty] | 1963671.4 | 36328.6
| Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | 6000000 |  |  |  |  | 4867447 |  | 981600 |  |  |  |  | 5849047 | 150953
| Construction of Boda Boda Shed at Mtangawanda | 2000000 |  |  |  | 1986500 | [7 empty] | 1986500 | 13500
| Construction of Boda Boda Shed at Witu | 2000000 | [8 empty] | 1713237.6 |  |  | 1713237.6 | 286762.4
| NET EXPENDITURE | 27900000 | 0 | 0 | 0 | 3950171.4 | 4867447 | 0 | 6641359.08 | 0 | 7417351.52 | 0 | 0 | 22876329 | 5023671
3220000000 | LIVESTOSK, VETINANRY & COOP DEVELOMENT
| Renovation/construction of Slaughter House | 6000000 | [11 empty] | 0 | 6000000
| Community Pasture and feed development project | 3000000 | [11 empty] | 0 | 3000000
| Construct Mpeketoni Modern slaughter house | 3000000 | [7 empty] | 677904 |  |  |  | 677904 | 2322096
| Livestock health improvement programme | 6000000 | [6 empty] | 3257000 |  | 400000 |  |  | 3657000 | 2343000
| Construction of Mpeketoni Slaughter house Phase I | 698658 | [11 empty] | 0 | 698658
| Construction of Mpeketoni Slaughter house Phase II | 3000000 | [11 empty] | 0 | 3000000
| SLAUGHTER HOUSE RAILS AT AMU | 2200000 | [7 empty] | 1161021.6 |  |  |  | 1161021.6 | 1038978.4
| Construction of Kitumbini Cattle Dip | 4000000 | [11 empty] | 0 | 4000000
| Construction of Nagele Auction yard | 9478595 | [11 empty] | 0 | 9478595
| Construction of Pangani Cattle Dip | 1040000 | [7 empty] | 924885.4 |  |  |  | 924885.4 | 115114.6
| Construction of Perimeter fence for Mokowe Co-operative Office | 1200000 |  |  |  | 934472.8 | [5 empty] | 209960 |  | 1144432.8 | 55567.2
| Purchase of Veterinary Laboratories Equipment | 1400000 | [8 empty] | 1397000 |  |  | 1397000 | 3000
| Rehabilitation of Amu Slaughter House | 2000000 | [11 empty] | 0 | 2000000
| NET EXPENDITURE | 43017253 | 0 | 0 | 0 | 934472.8 | 0 | 0 | 3257000 | 2763811 | 1797000 | 209960 | 0 | 8962243.8 | 31996442
3226000000 | FISHERIES
| Purchase of Fishing Gears | 10000000 | [8 empty] | 8889400 |  |  | 8889400 | 1110600
| Purchase of collers | 2000000 | [8 empty] | 0 |  |  | 0 | 2000000
| Construction of fisherman landing site (campsite) | 2000000 | [11 empty] | 0 | 2000000
| Construction of step ladders at kiwayu Jetty | 1500000 | [11 empty] | 0 | 1500000
| Construction of fisherman landing site (campsite) | 5000000 | [11 empty] | 0 | 5000000
| Purchase of Fishing Gears | 5000000 | [5 empty] | 3870000 | [5 empty] | 3870000 | 1130000
| Completion of Kizingitini Ice Plant | 11521643 | [11 empty] | 0 | 11521643
| ISHAKANI FISH LANDING SITE | 76560 |  |  |  |  | 76560 | [6 empty] | 76560 | 0
| NET EXPENDITURE | 37098203 | 0 | 0 | 0 | 0 | 76560 | 3870000 | 0 | 0 | 8889400 | 0 | 0 | 12835960 | 5110600
3228000000 | INFRASTUCTURE
| Kizingitini /Mbwajumali -Mabiyu access road | 4550000 | [8 empty] | 4295634 |  |  | 4295634 | 254366
| Opening New roads at Ngoi | 6000000 | [8 empty] | 5973735 |  |  | 5973735 | 26265
| Cabros at Mpketoni Market | 17000000 | [8 empty] | 6170805.6 |  |  | 6170805.6 | 10829194.4
| Opening Road from Nadhani to Kizuke | 5000000 | [8 empty] | 4708029 |  |  | 4708029 | 291971
| Opening of Kitamba - Kisauni road | 5000000 | [11 empty] | 0 | 5000000
| Road and bridge repair Mugumoine and Mkondoni | 10000000 | [8 empty] | 4880664 |  |  | 4880664 | 5119336
| Opening New roads at Manda Island | 31900000 | [8 empty] | 31900000 |  |  | 31900000 | 0
| Nyongoro-chalaruma road | 5864936.8 | [11 empty] | 0 | 5864936.8
| Maishamasha road | 8086661.6 | [11 empty] | 0 | 8086661.6
| A7 JUCTION -SINAMBIO | 8755580.24 | [11 empty] | 0 | 8755580.24
| Majembeni-Sinanbio road-1 | 9844838.8 | [11 empty] | 0 | 9844838.8
| Majembeni-Sinanbio road-2 | 7930920 | [11 empty] | 0 | 7930920
| Mpeketoni -ndambwe | 8426416.32 | [11 empty] | 0 | 8426416.32
| Ndambwe-Bangure road | 3637365.6 | [11 empty] | 0 | 3637365.6
| A7 JUCTION -Mokowe | 8479659.76 | [11 empty] | 0 | 8479659.76
| Cabro works | 6716718.72 | [11 empty] | 0 | 6716718.72
| Mpeketoni-bahari road | 5926220.76 | [11 empty] | 0 | 5926220.76
| Purchase & installation of electric street lights | 37928165 | [11 empty] | 0 | 37928165
| Siyu seawall | 10000000 | [11 empty] | 0 | 10000000
| cabro/drainage/pavement | 38000000 | [10 empty] | 4985961 | 4985961 | 33014039
| Maintainance of roads from Fuel Levy 2018-19 | 23828805 | [11 empty] | 0 | 23828805
|  | 262876288.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57928867.6 | 0 | 4985961 | 62914828.6 | 199961460
3228000000 | MUNICIPALITY
| Construction of Modern Market | 50000000 | [12 empty] | 50000000
| Construction of Modern Market | 48247400 | [12 empty] | 48247400
0
|  | 98247400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98247400
| TOTAL EXPENDITURE | 1885377010.68 | 1984894 | 22807987 | 42503029.52 | 15331837.2 | 48352720.15 | 164228916.84 | 14768300.28 | 32285810.7 | 190635197.02 | 26922262.6 | 6507902.85 | 566328858.16 | 1297837942.32
COMPILED BY :
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….
APPROVED BY:
NAME:
SIGN: ……………………………………………………………..
DATE: …………………………………………………………….