## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Mararani ECD | Construction of ECDE classrooms at Mararani | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.16'59''S 40.54'08''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2020/2021 | 2021-01-13 | 2021-01-13 | 10992902 | 10992902 |  | CGL | n/a | 10992902 | 0 | 10992902 | 100% | 10992902 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ECD is incompelete (no floor, doors, construction blocks on site) Built 2015(1810412) 2017(5588787.2) 2021(3593703.2)
2 | Shela primary ECD | Construction of ECDE classrooms at Shela | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.17'35''S 40.54'27''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2017-01-19 | 2017-01-19 | 4992286.2 | 4992286.2 |  | CGL | n/a | 4992286.2 | 0 | 4992286.2 | 100% | 4992286.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
3 | Manda Maweni primary ECD | Construction of ECDE classrooms at Manda Maweni | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.16'54''S 50.56'17''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2016-11-06 | 2016-11-06 | 1993889.2 | 1993889.2 |  | CGL | n/a | 1993889.2 | 0 | 1993889.2 | 100% | 1993889.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Lack of Perimeter wall and indequate water
4 | Shela Mararani ECD | Construction of ECDE classrooms at Shela Mararani | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.16'59''S 40.54'08''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2015-12-17 | 2015-12-17 | 1810412 | 1810412 |  | CGL | n/a | 1810412 | 0 | 1810412 | 100% | 1810412 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ECD is incompelete (no floor, doors, construction blocks on site)
5 | Manda Airport ECD | Construction of ECDE classrooms at Manda | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'48''S 40.55'19''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 1800412.8 | 1800412.8 |  | CGL | n/a | 1800412.8 | 0 | 1800412.8 | 100% | 1800412.8 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Security concern; the school has no perimeter wall
6 | Shella seven aside football pitch | Construction of a 7 Aside Field | To provide a standard football pitch for sports development | 7 aside football pitch constructed | 3110299 | Infrastructure | Lamu Central | Shella | 2.17'35''S 40.54'27''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 14836328 | 14836328 |  | CGL | n/a | 14836328 | 0 | 14836328 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
7 | Fencing and renovation of Shella nursery school and toilets | Fencing and renovation of Shella nursery school and toilets | To improve security, learning environment, and sanitation | Shella Nursery school fenced and renovated | 3110299 | Infrastructure | Lamu Central | Shella | 2.17'35''S 40.54'27''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 5000000 | 5000000 |  | CGL | n/a | 5000000 | 0 | 5000000 | 100% | 4992286.2 | 0 | 0 |  | 99.85% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
8 | Renovation of Shella Social Hall | Renovation of Shella Social Hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall renovated | 3110299 | Infrastructure | Lamu Central | Shella | 2.17'35''S 40.54'27''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 5000000 | 5000000 |  | CGL | n/a | 5000000 | 0 | 5000000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
9 | Renovation, Equipping and Beautifiction of Shella ECDE & Play ground | Renovation, Equipping and Beautifiction of Shella ECDE & Play ground | To improve the learning environment through renovation, equipping, and beautification of Shella ECDE and playground. | Palyground renovated | 3110299 | Infrastructure | Lamu Central | Shella | 2.17'35''S 40.54'27''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 5000000 | 5000000 |  | CGL | n/a | 5000000 | 0 | 5000000 | 100% | 4995712 | 0 | 0 |  | 99.91% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
10 | Shella Dispensary | construction of shella incinarator | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.17'34''S, 50.54'47''E | Medical Service | Medical | Medical Service | - | - | 2021/2022 | 2021/2022 | 3000000 | 3000000 |  | CGL | n/a | 3000000 | 0 | 3000000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
11 | Manda Dispensary | Renovation and Extension of Manda Dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'55''S 40.55'16''E | Medical Service | Medical | Medical Service | - | 2017/2018 | 2017-07-31 | 2017-07-31 | 1850490 | 1850490 |  | CGL | n/a | 1850490 | 0 | 1850490 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The facility has no water and electricity, facility roof is leaking and in some rooms collapsing.
12 | Manda Dispensary | construction of 4 door VIP Toilet at Raskitau & Manda Dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'55''S 40.55'16''E | Medical Service | Medical | Medical Service | - | 2017/2018 | 2018-05-30 | 2018-05-30 | 1994275 | 1994275 |  | CGL | n/a | 1994275 | 0 | 1994275 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
13 | Manda Dispensary | Completion of Manda Maweni Dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'55''S 40.55'16''E | Medical Service | Medical | Medical Service | - | - | 2022/2023 | 2022/2023 | 2500000 | 2500000 |  | CGL | n/a | 2500000 | 0 | 2500000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
15 | Manda Maweni Public Toilets | 4 no 2 Door Toilets Manda at Maweni | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.16'52''S 40.56'40''E | Public HealtH,Sanitation and Environment | Environment | Public HealtH,Sanitation and Environment | - | - | 2018/2019 | 2018/2019 | 1803196.8 | 1803196.8 |  | CGL | n/a | 1803196.8 | 0 | 1803196.8 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Several toilets at different site, not branded
16 | Manda water Project | Construction of solar water tower and resaviour | To provide reliable and sustainable water supply through a solar-powered water tower and reservoir. | Water tower constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.15'42''S 40.54'58''E | Water | Water | Water | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
17 | Manda Airpot WaterKiosk | Establishing of a waterKiosk at Manda airport | To provide reliable access to clean and safe water. | Water kiosk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'54''S 40.55'17''E | Water | Water | Water | - | - | 2014/2015 | 2014/2015 | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
19 | Manda Maweni toilet | Construction of Modern Toilet Manda Maweni | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.16'52''S 40.56'40''E | Trade and Tourism | Trade | Trade and Tourism | - | 2019/2020 | 2020-06-11 | 2020-06-11 | 1193083.2 | 1193083.2 |  | CGL | n/a | 1193083.2 | 0 | 1193083.2 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
20 | Manda ICT Center | Construction of Manda ICT Center | To build youth and professional capacity in emerging technologies and digital innovation. | Ict center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Shella | 2.14'55''S 40.55'16''E | ICT AND E-Governance | ICT AND E-Governance | ICT AND E-Governance | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ICT center has only be operational for 2 months, no electricity depends on solar
24 | Matondoni Primary ECD | Construction of ECDE classrooms at Matondoni Primary | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'14''S 40.50'14''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2016-05-17 | 2016-05-17 | 4202855.92 | 4202855.92 |  | CGL | n/a | 4202855.92 | 0 | 4202855.92 | 100% | 4202855.92 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
25 | Matondoni Social Hall | Construction of Matondoni Social Hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'10''S 40.50'22''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2017/2018 | 2017-09-28 | 2017-09-28 | 6565518.8 | 6565518.8 |  | CGL | n/a | 6565518.8 | 0 | 6565518.8 | 100% | 6565518.8 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
26 | Matondoni dispensary | Construction of dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'12''S 40.50'22''E | National Government | Medical | National Government | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
28 | Matondi Seawall | Construction of Matondi Seawall | Improve infrastructure | Construction of Matondi Seawall | 2220207 | Construction of Matondi Seawall | Lamu Central | Mkomani | 2.16'02''E 40.50'17''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2016/2017 | 2017-02-20 | 2017-02-20 | 4094394 | 4094394 |  | CGL | n/a | 4094394 | 0 | 4094394 | 100% | 4094394 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
29 | Kwa Guyo ECD | Construction of ECDE classrooms at Kwa Guyo | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110299 | Construction of building | Lamu Central | Mkomani | 2.16'23''S 40.50'22''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2017/2018 | 2017-09-28 | 2017-09-28 | 1985346.96 | 1985346.96 |  | CGL | n/a | 1985346.96 | 0 | 1985346.96 | 100% | 1985346.96 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
30 | Social Hall Kipungani | Construction of social hall at Kipungani | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.18'28''S 40.4'03''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 4990343.2 | 4990343.2 |  | CGL | n/a | 4990343.2 | 0 | 4990343.2 | 100% | 4990343.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
31 | Kipungani dispensary | Construction of dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.18'27''S 40.48'57''E | National Government | Medical | National Government | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The building is dilapidated, with damaged floors and windows. There is insufficient space, forcing patients to be accommodated along the corridor. There is no network coverage in the area, making it very challenging to register patients for SHA. The facility also lacks a perimeter wall, reliable electricity, and a water supply
32 | Construction Kipungani Seawall | Construction Kipungani Seawall | Improve infrastructure | Construction Kipungani Seawall | 2220207 | Construction Kipungani Seawall | Lamu Central | Mkomani | 2.1827S 40.48'55''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2016/2017 | 2017-04-18 | 2017-04-18 | 7995288.4 | 7995288.4 |  | CGL | n/a | 7995288.4 | 0 | 7995288.4 | 100% | 7995288.4 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
33 | Kashmir ECD | Construction of ECDE classrooms at Kashmir | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.75503, 40.8978155 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2016-06-14 | 2016-06-14 | 1993183.92 | 1993183.92 |  | CGL | n/a | 1993183.92 | 0 | 1993183.92 | 100% | 1993183.92 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | ECDE School not in use, building occupied by tenants
34 | Jisaidie ECD | Construction of ECDE classrooms at Kibaki Grounds | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'26''S 40.54'11E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2016-03-08 | 2016-03-08 | 1982904 | 1982904 |  | CGL | n/a | 1982904 | 0 | 1982904 | 100% | 1982904 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
35 | Bin Fadhil Primary ECD | Construction of ECDE classrooms at Bin Fadhil Primary | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE with Modern twin Toilet classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'27''S 40.54'08''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2016-11-25 | 2016-11-25 | 2000965.2 | 2000965.2 |  | CGL | n/a | 2000965.2 | 0 | 2000965.2 | 100% | 2000965.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
36 | Lamu Primary ECDE classroom and toilet | Construction of 2 ECDE classrooms and 2 doors VIP toilet at Lamu Primary School | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'29''S 40.54'06''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 2950000 | 2950000 |  | CGL | n/a | 2950000 | 0 | 2950000 | 100% | 2950000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
37 | Wiyoni Primary ECDE | Construction of ECDE classrooms at Kwa Guyo | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.2527539, 40.8954849 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2022/2023 | 2022-07-14 | 2022-07-14 | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is done inside a public primary school which has no perimeter wall
38 | Langoni Dumpsite Perimeter Wall | construction of perimeter wall at langoni waste collection site | To secure the dumpsite and improve waste management. | Perimeter wall installed | 3110299 | Construction of building | Lamu Central | Mkomani | 2.16'27''S 40.54'10''E | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | 2021/2022 | 2021/2022 | 2000000 | 2000000 |  | CGL | n/a | 2000000 | 0 | 2000000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
39 | Langoni Cementry perimeter wall | Construction of Cemetery perimeter wall | To protect the cemetery | Perimeter wall installed | 3110299 | Construction of building | Lamu Central | Mkomani | 2.16'28''S 40.54'10''E | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | - | - | 9259890 | 9259890 |  | CGL | n/a | 9259890 | 0 | 9259890 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
41 | Wiyoni road murram | Murram paving of Lamu island ring road phase II | To improve road accessibility. | Murram road | 3110299 | Construction of building | Lamu Central | Mkomani | 2.2579090, 40.8958800 | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | - | - | 14463750 | 14463750 |  | CGL | n/a | 14463750 | 0 | 14463750 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
42 | Wiyoni road murram | Murram paving of Lamu island ring road phase I | To improve road accessibility. | Murram road | 3110299 | Construction of building | Lamu Central | Mkomani | 2.2579090, 40.8958800 | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | - | - | 12593000 | 12593000 |  | CGL | n/a | 12593000 | 0 | 12593000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
43 | Amu market extension | Renovation and Extension of Lamu Market | To expand market space and improve trading conditions. | market constructed | 3110299 | Construction of building | Lamu Central | Mkomani | 2.16'10''S 40.54'08''E | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | - | - | 44950454 | 44950454 |  | CGL | n/a | 44950454 | 0 | 44950454 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
44 | Civil works at Amu market | Proposed Improvement of Drainage System andWalkways along the Road adjacent to Amu Market and Construction of Chicken Cage | To improve market infrastructure and service delivery. | market constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'11''S 40.54'08''E | Lamu Municipality | Lamu Municipality | Lamu Municipality | - | - | - | - | 1232616 | 1232616 |  | CGL | n/a | 1232616 | 0 | 1232616 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
45 | Lamu Cattle dip | Construction of lamu cattle dip | To improve livestock health and disease control. | Cattle dip constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'44''S 40.50'22''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Cost and year of completion yet to be determine
46 | Construction of a seven Aside st lamu Boys | Construction of a seven Aside st lamu Boys | To provide a standard football pitch for community use. | 7 aside football pitch constructed | 3110202 | Infrastructure | Lamu Central | Mkomani | 2.16'24''S 40.54'03''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 13059328 | 13059328 |  | CGL | n/a | 13059328 | 0 | 13059328 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
47 | Construction of Seven A-side pitch at Twaifu Grounds | Construction of Seven A-side pitch at Twaifu Grounds | To provide a standard football pitch for community use. | 7 aside football pitch constructed | 3110202 | Infrastructure | Lamu Central | Mkomani | 2.16'04''S 40.53'44''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 13000000 | 13000000 |  | CGL | n/a | 13000000 | 0 | 13000000 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
48 | Construction of 2 door toilets at Jisaidie ECDE | Construction of 2 door toilets at Kibaki ECDE | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'26''S 40.54'11E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 1000000 | 1000000 |  | CGL | n/a | 1000000 | 0 | 1000000 | 100% | 999000 | 0 | 0 |  | 99.9% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
49 | Construction of Wiyoni ECDE | Construction of Wiyoni ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.2579090, 40.8958800 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 3000000 | 3000000 |  | CGL | n/a | 3000000 | 0 | 3000000 | 100% | 2999644 | 0 | 0 |  | 99.99% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
50 | Mkomani ICT center | Construction of Mkomani ICT center | To build youth and professional capacity in emerging technologies and digital innovation. | Ict center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'40''S 40.54'22''E | ICT & E-governance |  | ICT & E-governance | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
51 | Mkomani Firestation | Construction of Mkomani firestation | Improve Safety | Fires station constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'39''S 40.54'22''E | Devolution |  |  | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
58 | Perimeter Fence for King Fahd Hospital | construction fence king hospital center at king | To provide comprehensive specialized and super-specialized healthcare services to referred patients | perimeter wall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.27'894''S 40.90'62E | Medical Service | Medical Service | Medical Service | - | - | 2015/2017 | 2015/2017 | 7886415 | 7886415 |  | CGL | n/a | 7886415 | 0 | 7886415 | 100% | 7886415 | 0 | 0 | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
59 | General Renovations for King Fahd Hospital | renovating king fahad hospital | To provide comprehensive specialized and super-specialized healthcare services to referred patients | king fahad renovated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.27'894''S 40.90'62E | Medical Service | Medical Service | Medical Service | - | - | 2015/2018 | 2015/2018 | 7758361.87 | 7758361.87 |  | CGL | n/a | 7758361.87 | 0 | 7758361.87 | 100% | 7758361.87 | 0 | 0 | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
60 | Improvement of Lamu Vocational Training Center | Construction of Fashion Design/Admin Block | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2017/2018 | 2017-11-02 | 2017-11-02 | 2206259 | 2206259 |  | CGL | n/a | 2206259 | 0 | 2206259 | 100% | 2206259 | 0 | 0 |  | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
61 | Improvement of Lamu Vocational Training Center | Construction of Hair Dressing /ICT block | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2019/2020 | 2019-10-01 | 2019-10-01 | 3292232.7 | 3292232.7 |  | CGL | n/a | 3292232.7 | 0 | 3292232.7 | 100% | 3292232.7 | 0 | 0 |  | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
62 | Improvement of Lamu Vocational Training Center | Construction of Hospitaility/Conference block | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
63 | Improvement of Lamu Vocational Training Center | Construction of Welding and Plumbing | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
64 | Improvement of Lamu Vocational Training Center | Construction of Masonry section | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
65 | Improvement of Lamu Vocational Training Center | Construction of Housing Block 1 | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2024/2025 | 2025-01-31 | 2025-01-31 | 1519939.88 | 1519939.88 |  | CGL | n/a | 1519939.88 | 0 | 1519939.88 | 100% | 1519939.88 | 0 | 0 |  | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
66 | Improvement of Lamu Vocational Training Center | Construction of Housing Block 2 | To improve access to technical education for youth empowerment | Classroom /workshop Constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2024/2025 | 2025-01-31 | 2025-01-31 | 1519939.88 | 1519939.88 |  | CGL | n/a | 1519939.88 | 0 | 1519939.88 | 100% | 1519939.88 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
67 | Improvement of Lamu Vocational Training Center | Cabro paving and graduation podium/DIAS | To improve access to technical education for youth empowerment | Cabro paved compound | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
68 | Improvement of Lamu Vocational Training Center | Construction of Perimeter Wall | To improve access to technical education for youth empowerment | Perimeter Wall | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'36''S 40.54'09''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational Training | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
69 | Construction of Lamu Livestock Office and NDMA | Construction of livestock office at Lamu | To enhance livestock sector administration | Livestock office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.28'13''S 40.90'71''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | 2015/2016 | 2016-03-08 | 2016-03-08 | 2025441.2 | 2025441.2 |  | CGL | n/a | 2025441.2 | 0 | 2025441.2 | 100% | 2025441.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
70 | Amu Slaughter house | Construction of slaughter house at Amu | To promote safe meat processing | Slaughter house constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.15'46''S 40.53'55''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | 2023/2024 | 2024-06-21 | 2024-06-21 | - | - |  | CGL | n/a | - | 0 | - | - | 0 | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
71 | Kashmir Dispensary | Construction of dispensary with 2 door modern toilet | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.75503, 40.8978155 | Medical Service | Medical | Medical Service | - | 2022/2023 | 2022-07-16 | 2022-07-16 | 4928179.96 | 4928179.96 | 4928179.96 | CGL | n/a | 4928179.96 | 0 | 4928179.96 | 100% | 4928179.96 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | Legal - No ownership of land built on | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | There is an adjacent unfinished building within the same compound intended for use as a dispensary. There is no security during the day, and the dispensary is located near a liquor den, where intoxicated individuals often disturb patients.
72 | Wiyoni Dispensary | Construction of dispensary with 2 door modern toilet | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Health dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.2579090, 40.8958800 | Medical Service | Medical | Medical Service | - | 2022/2023 | 2022-07-16 | 2022-07-16 | 4945579.96 | 4945579.96 | 4945579.96 | CGL | n/a | 4945579.96 | 0 | 4945579.96 | 100% | 4945579.96 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | Legal - No ownership of land built on | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | No booth for security at night and day shift
73 | Public Health and Public Works Toilet | Construction of Modern Toilet PH & PW Offices | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Modern toilets constructed. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu Central | Mkomani | 2.16'41''S 40.54.23''E | Public HealtH,Sanitation and Environment | Environment | Public HealtH,Sanitation and Environment | - | 2020/2021 | 2021-06-15 | 2021-06-15 | 1724027 | 1724027 |  | CGL | n/a | 1724027 | 0 | 1724027 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
77 | Twaifu Ground Toilet | Construction of Modern Toilet at Twaifu Ground | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110299 | Construction of building | Lamu Central | Mkomani | 2.16'04''S 40.53'44''E | Public HealtH,Sanitation and Environment | Environment | Public HealtH,Sanitation and Environment | - | 2020/2021 | 2020-12-28 | 2020-12-28 | 1187990 | 1187990 |  | CGL | n/a | 1187990 | 0 | 1187990 | 100% | - | 0 | 0 |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
80 | Bahamisi ECD | Construction of ECDE classrooms at Bahamisi | To improve access to ECDE services | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.06'33''S 40.58'34''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2017-02-10 | 2017-02-10 | 1999695.5 | 1999695.5 |  | CGL | n/a | 1999695.5 | 0 | 1999695.5 | 100% | 1999695.5 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
81 | Bahamisi Dispensary | Constrcution of dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.06'31''S 40.58'32''E | Medical Service | Medical | Medical service | - | - | - | - |  | - |  | Alkheir | Alkheir | - |  | - | - | - |  |  |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
82 | Bahamisi dumpsite | Construction of dumpsite | To provide a designated and controlled facility for safe disposal of solid waste within the county. | Dumpsite constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.06'31''S 40.58'33''E | Medical Service | Medical | Medical service | - | - | - | - |  | - |  | Alkheir | Alkheir | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
83 | Modern Toilet Mbwajumwali stage | construction of Modern Toilet at Mbwajumwali stage | improve hygiene | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'44''S 41.07'56''E | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2020/2021 | 2020-12-28 | 2020-12-28 | 1261372 | 1261372 |  | CGL | n/a | 1261372 | 0 | 1261372 | 100% | 1261372 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
84 | Mbwajumwali dispensary | Construction of Mbwajumwali dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'44''S 41.07'56''E | Medical Service | Medical | Medical service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
85 | Mbwajumwali sea wall | Construction of Mbwajumwali sea wall | To protect coastal communities, infrastructure, and property from erosion, storm surges, and wave action. | Sea wall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'36''S 41.08'13''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
86 | Mbwajumwali boda boda shed | Construction of Mbwajumwali boda boda shed | To provide a secure shed for boda boda operators | Boda boda shed constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'43''S 41.07'57''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
87 | Renovations of Mbwajumali ECDE | Renovations of Mbwajumali ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'45''S 41.07'51''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2016-01-22 | 2016-01-22 | 3089110 | 3089110 |  | CGL | n/a | 3089110 | 0 | 3089110 | 100% | - | 0 | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
88 | Kizingitini Dumpsite | Construction of Kizingitini dumpsite | To provide a designated and controlled facility for safe disposal of solid waste within the county. | Dumpsite constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'32''S 41.08'34''E | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
89 | Kizingitini market | Construction of Kizingitini market | To improve trading facilities and provide a conducive environment | market constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'22''S 41.08'49''E | Trade |  |  | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
90 | Kizingitini Vocational Training Center | Construction of kzingitini workshop and staff houses | To provide competency-based technical and vocational skills aligned with industry standards. | VTC and staff houses constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'23''S 41.08'56''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Vocational | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
91 | Kizingitini fisheries office | Construction of kizingitini office | To provide an administrative and operational base for delivery of fisheries services at the county or sub-county level | Fisheries office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'19''S 41.08'44''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
92 | Desalination plant Kizingitini | Contruction of Desalination plant | To enhance public health outcomes by reducing waterborne diseases through provision of treated and safe drinking water. | Desalination plant | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | 2.04'19''S 41.08'44''E | Water and Energy | Water and Energy | Water and Energy | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
93 | Expansion of Kizingitini Hospital | exapansion of kizingitini hospital | To improve access to comprehensive primary healthcare services for residents within the catchment area | hospital expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'23''S 41.08'39''E | Medical Service | Medical Service | Medical Service | - | 2020/2021 | 2021-06-07 | 2021-06-07 | 7988242.2 | 7988242.2 |  | CGL | n/a | 7988242.2 | 0 | 7988242.2 | 100% | 7988242.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
94 | Construction of Kizingitini Local Boat Building Shed | Construction of Kizingitini Local Boat Building Shed | To enhance occupational safety for fishermen and marine operators through organized and well-designed boat handling areas | shades constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'24''S 41.08'34''E | Trade ,tourism,investment and culture | Trade | Trade ,tourism,investment and culture | - | - | 2019/2020 | 2019/2020 | 2447646 | 2447646 |  | CGL | n/a | 2447646 | 0 | 2447646 | 100% | 2447646 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
95 | Construction of boatyard at kizingitini | Construction of boatyard at kizingitini | To enhance occupational safety for fishermen and marine operators through organized and well-designed boat handling areas | ICE PLANT constructed and machine installed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'20''S 41.08'39''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2023/2024 | - | 2023/2024 | 2023/2024 | 2100000 | 2100000 |  | CGL | n/a | 2100000 | 0 | 2100000 | 100% | 2100000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
96 | Completion of Kizingitini Ice Plant | Completion of Kizingitini Ice Plant | To support the blue economy and agricultural value chains by strengthening cold-chain infrastructure at landing sites, markets, and aggregation centres. | ICE PLANT constructed and machine installed | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | 2.04'19''S 41.08'44''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2019/2020 | - | 2019/2020 | 2019/2020 | 11521643 | 11521643 |  | CGL | n/a | 11521643 | 0 | 11521643 | 100% | 11521643 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
97 | CONSTRUCTION OF ICE PLANT- Kizingitini | Constcrution of ICE plant and cold store- Kizingitini | To support the blue economy and agricultural value chains by strengthening cold-chain infrastructure at landing sites, markets, and aggregation centres. | ICE PLANT constructed and machine installed | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | 2.04'19''S 41.08'44''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2018/2019 | - | 2018/2019 | 2018/2019 | 2601775.6 | 2601775.6 |  | CGL | n/a | 2601775.6 | 0 | 2601775.6 | 100% | 2601775.6 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
98 | Completion of Kizingitini iceplant phase II | Completion of Kizingitini iceplant phase II | To support the blue economy and agricultural value chains by strengthening cold-chain infrastructure at landing sites, markets, and aggregation centres. | Iceplant | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | 2.04'19''S 41.08'44''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2016/2017 | - | 2016/2017 | 2016/2017 | 17000000 | 17000000 |  | CGL | n/a | 17000000 | 0 | 17000000 | 100% | 17000000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
99 | Concrete Paving Blocks at Kizingitini | Concrete Paving and sitting barazas Blocks at Kizingitini | To improve accessibility and mobility within urban centres, markets, bus parks, and public facilities through durable paved surfaces | Concrete Paving Blocks at Kizingitini | 3110402 | Access Roads | Lamu East | Faza | 2.04'11''S 41.08'31''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - | 6116680 | 6116680 |  | CGL | n/a | 6116680 | 0 | 6116680 | 100% | 0 | 0 | 0 | Completed | 0% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
100 | Improvement of Faza Kizingtini Road | Improvement of Faza Kizingtini Road | To improve connectivity and accessibility between communities, markets, public institutions, and service centres within the county | Improvement of Faza Kizingtini Road | 3110402 | Access Roads | Lamu East | Faza | 2.04'23''S 41.08'56''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2017/2018 | 2018-03-13 | 2018-03-13 | 3709749.6 | 3709749.6 |  | CGL | n/a | 3709749.6 | 0 | 3709749.6 | 100% | 3709749.6 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
101 | Cabro work at Kizingitini Seafront | Cabro work at Kizingitini Seafront | To improve accessibility and mobility within urban centres, markets, bus parks, and public facilities through durable paved surfaces | Cabro work at Kizingitini Seafront | 3110402 | Access Roads | Lamu East | Faza | 2.04'20''S 41.08'40''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | 2024/2025 | 2024/2025 | 2024-10-16 | 2024-10-16 | 9800260 | 9800260 |  | CGL | n/a | 9800260 | 0 | 9800260 | 100% | 9800260 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
102 | Rehabilitation of Kizingitini Social Hall | Rehabilitation of Kizingitini Social Hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | 2.04'21''S 41.08'32''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 4997899 | 4997899 |  | CGL | n/a | 4997899 | 0 | 4997899 | 100% | 4997565.9 | 0 | 0 | Completed | 99.99% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
103 | Kizingitini social hall | Construction of Kizingitini social hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'21''S 41.08'32''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
104 | Renovation of Kizingitini ECDE | Renovation of Kizingitini ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | 2.04'23''S 41.08'30''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 2500000 | 2500000 |  | CGL | n/a | 2500000 | 0 | 2500000 | 100% | 2498802.4 | 0 | 0 | Completed | 99.95% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
105 | Renovations of Kizingitini ECDE | Renovations of Kizingitini ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | 2.04'23''S 41.08'30''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | 2023/2024 | 2023/2024 | 3089110 | 3089110 |  | CGL | n/a | 3089110 | 0 | 3089110 | 100% | 3089110 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
106 | Kizingitini ECD | Construction of ECDE classrooms at Kizingitini | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | 2.04'23''S 41.08'30''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2018/2019 | 2019-06-24 | 2019-06-24 | 3448772.8 | 3448772.8 |  | CGL | n/a | 3448772.8 | 0 | 3448772.8 | 100% | 3448772.8 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
107 | Shanga Rubu ECDE classroom and toilet | Construction of ECDE classrooms at Shanga | To improve access to ECDE services | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1265902, 41.0697298 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2019/2020 | 2019-11-29 | 2019-11-29 |  | 3689554 |  | CGL |  | 3689554 | 0 | 3689554 | 100% | 3689554 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | Insecurity due to the lack of a perimeter wall or fence around the school. | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational but it needs a fence to improve the security of the students.
108 | Bahamisi ECD | Construction of ECDE classrooms at Bahamisi | To improve access to ECDE services | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1074935, 40.9851858 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2017-02-10 | 2017-02-10 |  | 1999695.5 |  | CGL |  | 1999695.5 | 0 | 1999695.5 | 100% | 1999695.5 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
110 | Mtangawanda Primary ECD | Construction of ECDE classrooms at Mtangawanda Primary | To improve access to ECDE services | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1185061, 40.9740537 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2014/2015 | 2014-10-01 | 2014-10-01 |  | 1745927.6 |  | CGL |  | 1745927.6 | 0 | 1745927.6 | 100% | 1745927.6 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
111 | Shanga Rubu Social Hall | Construction of Shanga Rubu Social Hall | To enhance access to community meeting space | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1263283, 41.0706589 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2020/2021 | 2021-06-19 | 2021-06-19 |  | 4690555 |  | CGL |  | 4690555 | 0 | 4690555 | 100% | 4690555 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | Electrification of the social hall | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Electrification of the social hall
112 | Siyu ECDE and toilet | Construction of ECDE and 2 door VIP toilet at Siyu | To improve learning and sanitation conditions | ECDE and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0989199, 41.0601664 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2020/2021 | 2021-06-22 | 2021-06-22 |  | 2998590 |  | CGL |  | 2998590 | 0 | 2998590 | 100% | 2998590 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
113 | Social Hall Shanga Ishakani | Construction of social hall at Shanga Ishakani Phase II | To enhance access to community meeting space | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1378933, 41.0568900 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 2495334 |  | CGL |  | 2495334 | 0 | 2495334 | 100% | 2495334 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
114 | Shanga Ishakani ECDE classroom and toilet | Construction of 2 ECDE classrooms and 2 door toilet at Shanga Ishakani | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1374767, 41.0566950 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2021/2022 | 2022-04-28 | 2022-04-28 |  | 3299846.2 |  | CGL |  | 3299846.2 | 0 | 3299846.2 | 100% | 3299846.2 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
115 | Shanga Rubu ECDE classroom and toilet | Construction of 2 ECDE classrooms and 2 door toilet at Shanga Rubu | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1265902, 41.0697298 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2021/2022 | 2022-03-16 | 2022-03-16 |  | 3294069.4 |  | CGL |  | 3294069.4 | 0 | 3294069.4 | 100% | 3294069.4 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
116 | Mtangawanda Social Hall | Construction of social hall at Mtangawanda Phase 1 | To enhance access to community meeting space | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1197808, 40.9750149 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2022/2023 | 2023-03-07 | 2023-03-07 |  | 2248480 |  | CGL |  | 2248480 | 0 | 2248480 | 100% | 2248480 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
117 | Pate ECDE classroom and toilet | Construction of ECDE classrooms and 2 doors VIP toilets at Pate | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1369946, 41.0016053 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 3298866 |  | CGL |  | 3298866 | 0 | 3298866 | 100% | 3298866 |  | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
118 | Fencing of playground Faza | Fencing of playground Faza | To secure the Faza playground and ensure safety for users. | Faza playground fenced | 3110202 |  | Lamu East | Faza | -2.0563681, 41.1095054 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 2000000 |  |  |  | 2000000 |  | 2000000 | 100% | 0 |  |  |  | 0% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Some parts of the wall have collapsed
119 | Levelling of Faza ground | Levelling of Faza ground | To provide a level football playing ground. | Faza Ground levelled. | 3110202 |  | Lamu East | Faza | -2.0556761, 41.1096205 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 700000 |  |  |  | 700000 |  | 700000 | 100% | 300000 |  |  | Completed | 42.86% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and the ground is being used but the perimeter wall has collapsed
120 | Tchundwa disabled unit | Tchundwa disabled unit | To provide facilities for children with disabilities | Tchundwa disabled unit constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0792567, 41.1141314 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 300000 |  |  |  | 300000 |  | 300000 | 100% | 2867000 |  |  | Completed | 955.7% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
122 | Social Hall at Mtangawada- Phase 1 | Social Hall at Mtangawada- Phase 1 | To enhance access to community meeting space | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1197808, 40.9750149 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 2500000 |  |  |  | 2500000 |  | 2500000 | 100% | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
123 | levelling of siyu football stadia | levelling of siyu football stadia | To provide a level football playing ground. | Siyu Ground levelled. | 3110202 |  | Lamu East | Faza | -2.1036150, 41.0628705 | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 1500000 |  |  |  | 1500000 |  | 1500000 | 100% | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ground has been levelled and is being used
124 | levelling of Tchundwa football stadia | levelling of Tchundwa football stadia | To provide a level football playing ground. | Tchundwa Ground levelled. | 3110202 |  | Lamu East | Faza | -2.0822866, 41.1145974 | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 1062757 |  |  |  | 1062757 |  | 1062757 | 100% | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ground has been levelled and is being used
126 | Renovation of Faza social hall | Renovation of Faza social hall | To enhance access to community meeting space | Social hall renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.0552189, 41.1131074 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 5000000 |  |  |  | 5000000 |  | 5000000 | 100% | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The social hall has been renovated and is currently in use.
127 | Renovation of pate social hall | Renovation of pate social hall | To enhance access to community meeting space | Social hall renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.1435259, 40.9973770 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 5000000 |  |  |  | 5000000 |  | 5000000 | 100% | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The social hall has been renovated and is currently in use.
128 | Construction of two door toilet for ECDE Tchundwa | Construction of two door toilet for ECDE Tchundwa | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0815650, 41.1136383 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 3493152 |  |  |  | 3493152 |  | 3493152 | 100% | 2389398.8 |  |  | Completed | 68.4% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete, and the toilets are currently in use.
129 | Rehabilitation of Siyu Social Hall | Rehabilitation of Siyu Social Hall | To enhance access to community meeting space | Social hall renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.1032631, 41.0621172 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 4997899 |  |  |  | 4997899 |  | 4997899 | 100% | 4996607.2 |  |  | Completed | 99.97% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and in use.
130 | CONSTRUCTION OF ECD CLASSROOM AND 2 DOOR TOILET AT SIYU | CONSTRUCTION OF ECD CLASSROOM AND 2 DOOR TOILET AT SIYU | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0989199, 41.0601664 | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | 2998590 |  |  |  | 2998590 |  | 2998590 | 100% | 2898110.36 |  |  | Completed | 96.65% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete ,and both the classroms and toilets are currently in use.
131 | Renovation of Ward Admin Office Converting to Faza Information Center | Renovation of Ward Admin Office Converting to Faza Information Center | Digital leteracy | Ward Admin office renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.0551817, 41.1127457 | ICT & E-governance | ICT | ICT & E-governance | - | - | - | - |  | 2490182 |  |  |  | 2490182 |  | 2490182 | 100% | 0 |  |  |  | 0% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
134 | R.O Plant House in Siyu Desalination plant | Construcution of R.O Plant House | Clean and safe water | R.O Plant House | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | -2.1045279, 41.0622373 | Water and Energy | Water and Energy | Water and Energy | - | - | 2022/2023 | 2022/2023 | 16001452 | 16001452 |  | GOK - LCG | N/A | 16001452 | N/A | - | - | 16001452 |  | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational.
135 | Supply of desalination plant unit and its accessories-siyu | Supply of desalination plant unit and its accessories-siyu | Clean and safe water | Desalination plant unit and its accessories | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | -2.1045279, 41.0622373 | Water and Energy | Water and Energy | Water and Energy | - | - | 2017/2018 | 2017/2018 | 6098024 | 6098024 |  | GOK - LCG | N/A | 6098024 | N/A | - | - | 6098024 |  | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational.
137 | Siyu -Pate -Mtangawada pipeline extension, Pate households connections 25KMS | Siyu -Pate -Mtangawada pipeline extension, Pate households connections 25KMS | Clean and safe water | Siyu -Pate -Mtangawada pipeline extension, Pate households connections 25KMS | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | -2.1085970, 41.0617757 | Water and Energy | Water and Energy | Water and Energy | 2021/2022 | - | - | - | 8749891 | 8749891 |  | GOK - LCG | N/A | 8749891 | N/A | - | - | 8749891 |  | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete but is currently not operational.
138 | Faza Desalination Plant | Faza Desalination Plant | Clean and safe water | Faza Desalination Plant | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | -2.0553383, 41.1101233 | Water and Energy | Water and Energy | Water and Energy | 2021/2022 | - | - | - | 20000000 | 20000000 |  | GOK - LCG | N/A | 20000000 | N/A | - | - | 20000000 |  | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational.
139 | Improvement of Pate Island Road | Improvement of Pate Island Road | Improve infrastructure | Improvement of Pate Island Road | 3110402 | Access Roads | Lamu East | Faza | -2.1415715, 40.9969995 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2014/2015 | 2015-04-01 | 2015-04-01 | 1992787.2 | 1992787.2 |  | GOK - LCG | N/A | 1992787.2 | N/A | - | - | 1992787.2 |  | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The road has been impoved and is in good condition
140 | Cabro Paving at Siyu | Cabro Paving at Siyu | Improve infrastructure | Cabro Paving at Siyu | 3110402 | Access Roads | Lamu East | Faza | -2.1017438, 41.0597472 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2017/2018 | 2017-10-06 | 2017-10-06 | 4486580 | 4486580 |  | GOK - LCG | N/A | 4486580 | N/A | - | - | 4486580 |  | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Cabro paving completed and in good condition.
141 | Concrete Paving Blocks at Faza | Concrete Paving Blocks at Faza | Improve infrastructure | Concrete Paving Blocks at Faza | 3110402 | Access Roads | Lamu East | Faza | -2.0551767, 41.1131563 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2017/2018 | 2018-03-01 | 2018-03-01 | 6102702 | 6102702 |  | GOK - LCG | N/A | 6102702 | N/A | - | - | 6102702 |  | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Cabro paving completed and in good condition.
142 | Siyu Dispansary | construction of dispensary in siyu | improve health service | dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1013314, 41.0599166 | Medical Service | Medical Service | Medical Service | - | 2023/2024 | 2024-01-09 | 2024-01-09 | 1999994.28 | 1999994.28 |  | CGL |  | 1999994.28 |  | 1999994.28 | 100% | 1999994.28 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Dispensary extension completed and operational
143 | Extension of Siyu Dispensary | extension of siyu dispensary | improve health service | dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1013314, 41.0599166 | Medical Service | Medical Service | Medical Service | - | 2021/2022 | 2021-07-07 | 2021-07-07 | 17473870 | 17473870 |  | CGL |  | 17473870 |  | 17473870 | 100% | 17473870 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Dispensary extension completed and operational
144 | Extension of Maternity Wing at Faza Sub-County Hospital | construction of maternity wing at Faza hospital | improve health service | maternity wing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0569991, 41.1109948 | Medical Service | Medical Service | Medical Service | - | 2020/2021 | 2020-08-18 | 2020-08-18 | 11904482 | 11904482 |  | CGL |  | 11904482 |  | 11904482 | 100% | 11904482 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
145 | Construction of OPD at Faza SCH | Construction of OPD at Faza SCH | improve health service | opd facility constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0579364, 41.1112298 | Medical Service | Medical Service | Medical Service | - | - | 2022/2023 | 2022/2023 | 3000000 | 3000000 |  | CGL |  | 3000000 |  | 3000000 | 100% | 3000000 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
146 | Completion of siyu Health centre | completion of health center at siyu | improve health service | health center completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1013314, 41.0599166 | Medical Service | Medical Service | Medical Service | - | - | 2019/2020 | 2019/2020 | 10000000 | 10000000 |  |  |  | 10000000 |  | 10000000 | 100% | 10000000 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
147 | Renovation of H/facilities-Pate | renovation of pate facility | improve health service | hospital renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.1396858, 40.9970513 | Medical Service | Medical Service | Medical Service | - | - | 2015/2019 | 2015/2019 | 638000 | 638000 |  | GOK |  | 638000 |  | 638000 | 100% | 638000 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
148 | Renovation of H/facilities-Siyu | renovation of siyu facility | improve health service | hospital renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.1013314, 41.0599166 | Medical Service | Medical Service | Medical Service | - | - | 2015/2020 | 2015/2020 | 0 | 0 |  | GOK |  | 0 |  | 0 | - | 0 |  |  | completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
149 | Renovation of Faza Hospital | renovation of hospital in Faza | improve health service | hospital renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.0569991, 41.1109948 | Medical Service | Medical Service | Medical Service | - | - | 2015/2016 | 2015/2016 | 1737448 | 1737448 |  | GOK |  | 1737448 |  | 1737448 | 100% | 1737448 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
150 | Completion of Faza Hospital renovations, Construction of Parameter wall and service block | Completion of Faza Hospital renovations, Construction of Parameter wall and service block | improve health service | hospital renovated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0579364, 41.1112298 | Medical Service | Medical Service | Medical Service | - | - | 2015/2016 | 2015/2016 | 0 | 0 |  | GOK |  | 0 |  | 0 | - | 0 |  |  | completed | - | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Project completed and operational
151 | Renovation of Laboratories Faza, | Renovation of Laboratories Faza, | improve health service | laboratory renovated | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.0569991, 41.1109948 | Medical Service | Medical Service | Medical Service | - | - | 2015/2016 | 2015/2016 | 0 | 0 |  | GOK |  | 0 |  | 0 | - | 0 |  |  | completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
152 | Construction of incinerators:Faza | Construction of incinerators: Witu, Mokowe, Faza and Kiunga@1,000,000 | improve health service | incinerator constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0578158, 41.1102021 | Medical Service | Medical Service | Medical Service | - | - | 2015/2016 | 2015/2016 | 1620261.87 | 1620261.87 |  | GOK |  | 1620261.87 |  | 1620261.87 | 100% | 1620261.87 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Incinerator constructed, but it does not fully meet the required specifications and requires modifications.
153 | Proposed laundry and kitchen at Faza subcounty hospital | Proposed laundry and kitchen at Faza subcounty hospital | improve health service | laundry constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0581317, 41.1105133 | Medical Service | Medical Service | Medical Service | - | - | 2018/2019 | 2018/2019 | 5853335.9 | 5853335.9 |  | CGL |  | 5853335.9 |  | 5853335.9 | 100% | 5853335.9 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Projected completed and in use.
154 | Proposed out patient wing at Faza subcounty hospital | Proposed out patient wing at Faza subcounty hospital | improve health service | patient wing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0569991, 41.1109948 | Medical Service | Medical Service | Medical Service | - | - | 2018/2019 | 2018/2019 | 6131694 | 6131694 |  | CGL |  | 6131694 |  | 6131694 | 100% | 6131694 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
155 | Proposed extention of maternity wing at Faza Sub-County Hospital | Proposed extention of maternity wing at Faza Sub-County Hospital | improve health service | maternity wing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0569991, 41.1109948 | Medical Service | Medical Service | Medical Service | - | - | 2018/2019 | 2018/2019 | 2485472.85 | 2485472.85 |  | CGL |  | 2485472.85 |  | 2485472.85 | 100% | 2485472.85 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
156 | Proposed extention of Siyu Dispensary | Proposed extention of Siyu Dispensary | improve health service | dispensary extended | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1013314, 41.0599166 | Medical Service | Medical Service | Medical Service | - | - | 2018/2019 | 2018/2019 | 1716573.97 | 1716573.97 |  | CGL |  | 1716573.97 |  | 1716573.97 | 100% | 1716573.97 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
157 | Construction of Faza sub-county hospital permeter wall | Construction of Faza sub-county hospital permeter wall | improve health service | perimeter wall constructed | 3110202 |  | Lamu East | Faza | -2.0579234, 41.1112109 | Medical Service | Medical Service | Medical Service | - | - | 2018/2019 | 2018/2019 | 1501625.8 | 1501625.8 |  | CGL |  | 1501625.8 |  | 1501625.8 | 100% | 1501625.8 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
158 | Construction of Open Air Market at Mtangawanda Phase 1 | Construction of Open Air Market at Mtangawanda Phase 1 | promote trade and economic activity | market constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1113977, 40.9737147 | Trade ,tourism,investment and culture | Trade | Trade ,tourism,investment and culture | - | - | - | - | 6000000 | 6000000 |  | CGL |  | 6000000 |  | 6000000 | 100% | 6000000 |  |  | ongoing | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Completion of the project.
159 | Construction of Boda Boda Shed at Mtangawanda | construction of boda shade in mtangawanda | promote order and reduce congestion | shades constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1106240, 40.9725695 | Trade ,tourism,investment and culture | Trade | Trade ,tourism,investment and culture | - | - | 2019/2020 | 2019/2020 | 1986500 | 1986500 |  | CGL |  | 1986500 |  | 1986500 | 100% | 1986500 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and currently in use.
160 | Modern Toilet Mtangawanda Jetty | Modern Toilet Mtangawanda Jetty | improve hygiene | toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1110345, 40.9724666 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2020/2021 | 2020-12-16 | 2020-12-16 | 1277995.2 | 1277995.2 |  | CGL |  | 1277995.2 |  | 1277995.2 | 100% | 1277995.2 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is completed but currently it lacks doors
161 | Modern Toilet at Faza Village | Modern Toilet at Faza Village | improve hygiene | toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0584173, 41.1106486 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2019/2020 | 2020-02-04 | 2020-02-04 | 1250640.4 | 1250640.4 |  | CGL |  | 1250640.4 |  | 1250640.4 | 100% | 1250640.4 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
162 | Modern Toilet Siyu | Modern Toilet Siyu | improve hygiene | toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1045495, 41.0621227 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2019/2020 | 2019-10-14 | 2019-10-14 | 1250640.4 | 1250640.4 |  | CGL |  | 1250640.4 |  | 1250640.4 | 100% | 1250640.4 |  |  | completed | 100% | n/a | n/a | n/a | n/a | n/a | No | NA | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is complete and operational
163 | Sub County Head quarters | Sub County Head quarters | To provide office space for effective sub-county administration. | Sub-county headquarter constructed. | 3110202 | construction of building | Lamu East | Faza | -2.0666967, 41.1076184 |  |  |  | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Ongoing | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The project is ongoing
164 | Renovation of Pate Cattle dip | Renovation of Pate Cattle dip | To improve livestock disease control. | Pate cattle dip renovated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1381260, 41.0013346 |  |  |  | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
165 | Siyu Birika la taka | Construction of Siyu Birika la taka | To improve solid waste management. | Waste collection pit constructed at Siyu. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1030108, 41.0597210 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
166 | Shanga rubu Jabia (Flocca) | Construction of Jabia (Flocca) in Shanga Rubu | To enhance water storage and access. | Jabia constructed at Shanga Rubu. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.1316533, 41.0606659 |  |  |  | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
167 | Tchundwa birika la taka | Construction of birika la taka in Tchundwa | To improve solid waste disposal. | Waste collection pit constructed at Tchundwa. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0788468, 41.1126824 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
168 | Myabogi bridge | Construction of Myabogi bridge | To improve accessibility and connectivity. | Myabogi bridge constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0754439, 41.1286045 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Stalled | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
169 | Agricultural office Faza | Construction of Agricultural office Faza | To provide office space for agricultural services. | Agricultural office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0551860, 41.1103292 |  |  |  | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
170 | Renovation of theatre Faza Hospital | Renovation of theatre Faza Hospital | To improve surgical service delivery. | Hospital theatre renovated at Faza Hospital. | 3110202 | Refurbishment of Non-Residential Buildings | Lamu East | Faza | -2.0567394, 41.1111679 | Medical Service | Medical Service | Medical Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
171 | Ice plant- Faza | Ice plant- Faza | To support fish preservation and the fishing industry. | Ice plant constructed/installed at Faza. | 3112299 | Purchase of Specialised Plant | Lamu East | Faza | -2.0581407, 41.1133269 | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
172 | Faza fish and meat market | Construction of Faza fish and meat market | To provide a hygienic market for fish and meat trade. | Fish and meat market constructed at Faza. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0555802, 41.1133099 | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
173 | Old Incinerator Faza hosp | Old Incinerator Faza hosp | To improve medical waste management. | Incinerator constructed at Faza Hospital. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0578622, 41.1102549 | Medical Service | Medical Service | Medical Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
174 | Tchundwa Ground Stage | Tchundwa Ground Stage | To provide a platform for public events. | Stage constructed at Tchundwa Ground. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0820555, 41.1146132 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
175 | Faza Birika la taka | Construction of Birika la taka in Faza | To enhance solid waste management. | Waste collection pit constructed at Faza. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0562869, 41.1101664 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
176 | Faza bridge | Construction of Faza bridge | To improve accessibility and connectivity. | Faza bridge constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0589517, 41.1111517 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
177 | Tchundwa goalpost | Tchundwa goalpost | To promote sports and youth engagement. | Football goalposts installed at Tchundwa. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0824196, 41.1142253 | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
178 | Old dumping site Faza | Old dumping site Faza | To improve waste management. | Dumping site constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0587977, 41.1110343 | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
179 | Cabro paving at Tchundwa | Cabro paving at Tchundwa | To improve access | Cabro paving completed at Tchundwa. | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Faza | -2.0808783, 41.1140183 | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
180 | Mkokoni ECD | Construction of ECDE classrooms at Mkokoni | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.58'26''S 41.18'01''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2018/2019 | 2018-08-07 | 2018-08-07 | 2162389.64 | 2162389.64 |  | CGL | n/a | 2162389.64 | 0 | 2162389.64 | 100% | 2162389.64 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Lack of perimeter wall affects learners concentration and security of funitures at night
181 | Mkokoni Social Hall | Renovation of Social Hall at Mkokoni | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.58'26''S 41.18'01''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 3991212 | 3991212 |  | CGL | n/a | 3991212 | 0 | 3991212 | 100% | 3991212 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Hall in operation but lacks electricty and water connection
182 | Modern Toilet at Mkokoni | construction of Modern Toilet at Mkokoni | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.58'26''S 41.18'01''E | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2021/2022 | 2021-11-22 | 2021-11-22 | 1291590.4 | 1291590.4 |  | CGL | n/a | 1291590.4 | 0 | 1291590.4 | 100% | 1291590.4 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | M/s Skylight Green Supplies - Toilet not functional
183 | Desalination plant Mkokoni | Desalination plant Mkokoni | To enhance public health outcomes by reducing waterborne diseases through provision of treated and safe drinking water. | Desalination plant Mkokoni | 3112299 | Purchase of Specialised Plant | Lamu East | Kiunga | 1.58'20''S 41.17'39''E | Water and Energy | Water and Energy | Water and Energy | 2021/2022 | 2022/2023 | 2022-07-15 | 2022-07-15 | 2261485 | 2261485 |  | CGL | n/a | 2261485 | 0 | 2261485 | 100% | 2261485 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
184 | Improvement Mkokoni - AP Road | Improvement Mkokoni - AP Road | To improve connectivity and accessibility between communities, markets, public institutions, and service centres within the county | Improvement Mkokoni - AP Road | 3110402 | Access Roads | Lamu East | Kiunga | 1.57'48''S 41.17'46''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - | 2999818.4 | 2999818.4 |  | CGL | n/a | 2999818.4 | 0 | 2999818.4 | 100% | 2999818.4 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
185 | Madina ECDE | Construction of ECDE classrooms at Mkokoni | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.57'48''S 41.17'46''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2017/2018 | 2018-01-12 | 2018-01-12 | 2253126 | 2253126 |  | CGL | n/a | 2253126 | 0 | 2253126 | 100% | 2253126 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
186 | Mkokoni Sea Wall | Construction of mkokoni sea wall | To protect coastal communities, infrastructure, and property from erosion, storm surges, and wave action. | Sea wall constructed | 3110505 | Construction of civil works seawall and jetties | Lamu East | Kiunga | 1.58'18''S 41.17'44''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Need Rehabiliation the seawall is broken
187 | Modern Toilet at Ishakani | construction of Modern Toilet at Ishakani | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'38''S 41.31'36'' E | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2020/2021 | 2021-06-24 | 2021-06-24 | 1482874 | 1482874 |  | CGL | n/a | 1482874 | 0 | 1482874 | 100% | 1482874 | 0 | 0 | completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
188 | Ishakani Fish Landing | Construction of Ishakani fish landing | To support the local blue economy by facilitating fishing, tourism, and small-scale marine trade activities. | Ishakani fish landing | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'39''S 41.31'38''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2018/2019 | - | 2018/2019 | 2018/2019 | 2356966.3 | 2356966.3 |  | CGL | n/a | 2356966.3 | 0 | 2356966.3 | 100% | 2356966.3 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
189 | Ishakani water kiosk | Constuction of water kiosk and installation of 5000 ltrs tank | To provide regulated and equitable water access through well-managed water kiosks serving densely populated and low-income areas. | Ishakani water kiosk | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'37''S 41.31'35''E | Water and Energy | Water and Energy | Water and Energy | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
190 | Ishakani Dispensary | Construction of Ishakani dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'43''S 41.31'30''E | Medical Service | Medical | Medical service | - | 2016/2017 | 2017-04-11 | 2017-04-11 | 4992292 | 4992292 |  | CGL | n/a | 4992292 | 0 | 4992292 | 100% | - | 0 | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
191 | Ishakani 4 door VIP toilet | Construction of 4 door VIP Toilet at Ishakani Dispensary | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'43''S 41.31'30''E | Medical Service | Medical | Medical service | - | 2016/2017 | 2017-04-11 | 2017-04-11 | 1043420 | 1043420 |  | CGL | n/a | 1043420 | 0 | 1043420 | 100% | - | 0 | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
192 | Ishakani ECDE | Construction of ECDE classrooms at Mkokoni | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.41'43''S 41.31'30''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | 2019/2020 | 2019/2020 | 2020-06-09 | 2020-06-09 | 5462930.2 | 5462930.2 |  | CGL | n/a | 5462930.2 | 0 | 5462930.2 | 100% | 5462930.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
193 | Kunga Ishakani Water pipeline project | Construction Of Kiunga Ishakani Water Pipeline Project | To strengthen water supply infrastructure by extending and rehabilitating water pipelines to ensure efficient distribution and reduced water losses | Ishakani water pipeline | 3110502 | Water Supplies and Sewerage | Lamu East | Kiunga | 1.41'43''S 41.31'30''E | Water and Energy | Water and Energy | Water and Energy | 2024/2025 | - | 2024/2025 | 2024/2025 | 13338315.7 | 13338315.7 |  | CGL | n/a | 13338315.7 | 0 | 13338315.7 | 100% | 13338315.7 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
194 | Kiwayuu chandani stairways | Construction of step ladders at kiwayu chandani Jetty | To improve safe and reliable access between boats and the shoreline for fishermen, passengers, and goods. | Construction of step ladders at kiwayu Jetty | 3110505 | Construction of civil works seawall and jetties | Lamu East | Kiunga | 1.59'04''S 41.17'21''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2020/2021 | - | 2019/2020 | 2019/2020 | 1500000 | 1500000 |  | CGL | n/a | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
195 | Chandani pipeline extension | Chandani pipeline extension | To strengthen water supply infrastructure by extending and rehabilitating water pipelines to ensure efficient distribution and reduced water losses | Chandani pipeline extension | 3110502 | Water Supplies and Sewerage | Lamu East | Kiunga | 1.59'55''S 41.16'51''E | Water and Energy | Water and Energy | Water and Energy | 2023/2024 | - | - | - | 4905000 | 4905000 |  | CGL | n/a | 4905000 | 0 | 4905000 | 100% | 4905000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
196 | Kiwayu chandani water project and pump station house | Kiwayu chandani water project and pump station house | To provide regulated and equitable water access through well-managed water kiosks serving densely populated and low-income areas. | Kiwayu chandani water project and pump station house | 3110502 | Water Supplies and Sewerage | Lamu East | Kiunga | 1.59'55''S 41.16'51''E | Water and Energy | Water and Energy | Water and Energy | 2023/2024 | 2023/2024 | 2024-06-07 | 2024-06-07 | 4900814.4 | 4900814.4 |  | CGL | n/a | 4900814.4 | 0 | 4900814.4 | 100% | 4900814.4 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
197 | Kiwayuu desalination plant | Kiwayuu desalination plant | To enhance public health outcomes by reducing waterborne diseases through provision of treated and safe drinking water. | Kiwayuu desalination plant | 3112299 | Purchase of Specialised Plant | Lamu East | Kiunga | 1.58'18''S 41.17'38''E | Water and Energy | Water and Energy | Water and Energy | 2022/2023 | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
198 | Kiwayu social Hall | Construction of Kiwayu social Hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Kiwayuu social hall | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.01'10''S 41.15'41''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2025/2026 | 2025-08-22 | 2025-08-22 | 5133145.6 | 5133145.6 |  | CGL | n/a | 5133145.6 | 0 | 5133145.6 | 100% | 5133145.6 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
199 | Kiwayuu water supply | Kiwayuu Water Supply Project (Construction Of 8.984km Pipeline And Construction Of Chlorination Tower) | To strengthen water supply infrastructure by extending and rehabilitating water pipelines to ensure efficient distribution and reduced water losses | Kiwayuu pipeline installed | 3110502 | Water Supplies and Sewerage | Lamu East | Kiunga | 2.00'58''S 41.15'48''E | Water and Energy | Water and Energy | Water and Energy | - | 2022/2023 | 2022-07-15 | 2022-07-15 | 4600000 | 4600000 |  | CGL | n/a | 4600000 | 0 | 4600000 | 100% | 4600000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
200 | Kiwayuu Fishermen Shade | Construction Of Fishermen Shade At Kiwayuu Landing Site | To support the local blue economy by facilitating fishing, tourism, and small-scale marine trade activities. | Ishakani fish landing | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.01'12''S 41.15'41''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | 2021/2022 | 2022-06-20 | 2022-06-20 | 1499940 | 1499940 |  | CGL | n/a | 1499940 | 0 | 1499940 | 100% | 1499940 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
201 | Kiwayuu ECDE | Construction of Kiwayuu ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.00'06''S 41.16'31''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2024/2025 | 2025-04-17 | 2025-04-17 | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
202 | Kiwayuu ICE plant | Construction of Kiwayuu solarised ICE plant | To support the blue economy and agricultural value chains by strengthening cold-chain infrastructure at landing sites, markets, and aggregation centres. | Ice plant constructed and solars installed | 3112299 | Purchase of Specialised Plant | Lamu East | Kiunga | 2.01'12''S 41.15'41''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | 2025/2026 | 2025-08-22 | 2025-08-22 | - | - |  | CGL | Al-Kheir Foundation | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
203 | Kiwayuu water kiosk | Construction of water kiosk and installation of 5000 ltrs tank | To provide regulated and equitable water access through well-managed water kiosks serving densely populated and low-income areas. | Ishakani water kiosk | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.01'13''S 41.15'40''E | Water and Energy | Water and Energy | Water and Energy | - | 2016/2017 | 2017-01-27 | 2017-01-27 | 2500000 | 2500000 |  | CGL | n/a | 2500000 | 0 | 2500000 | 100% | 2499714 | 0 | 0 | Completed | 99.99% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
204 | Kiwayuu dispensary | Construction of Kiwayuu dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.00'58''S 41.15'48''E | Medical Service | Medical | Medical service | - | 2022/2023 | 2023-05-25 | 2023-05-25 | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
205 | Kiwayuu solar frezer project | Kiwayuu solar frezer project | To support the blue economy and agricultural value chains by strengthening cold-chain infrastructure at landing sites, markets, and aggregation centres. | Solar freezers installed and house constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.01'12''S 41.15'41''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | - | 2016/2017 | 2017-01-27 | 2017-01-27 | - | - |  | CGL | Al-Kheir Foundation | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
206 | Ndau water supply project | Construction of Desalination Plant | To enhance public health outcomes by reducing waterborne diseases through provision of treated and safe drinking water. | Ndau desalination plant | 3112299 | Purchase of Specialised Plant | Lamu East | Kiunga | 2.00'46''S 41.12'44''E | Water and Energy | Water and Energy | Water and Energy | - | 2021/2022 | 2022-06-17 | 2022-06-17 | 9300000 | 9300000 |  | CGL | n/a | 9300000 | 0 | 9300000 | 100% | 9300000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
207 | Ndau concrete paving | Concrete Paving Blocks at Ndau | To improve accessibility and mobility within urban centres, markets, bus parks, and public facilities through durable paved surfaces | Concrete Paving Blocks at Ndau | 3110402 | Access Roads | Lamu East | Kiunga | 2.00'46''S 41.12'44''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2017/2018 | 2018-03-28 | 2018-03-28 | 6199620 | 6199620 |  | CGL | n/a | 6199620 | 0 | 6199620 | 100% | 6199620 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
208 | Ndau cabro works | Cabro paving at Ndau | To improve accessibility and mobility within urban centres, markets, bus parks, and public facilities through durable paved surfaces | Cabro paved road | 3110402 | Access Roads | Lamu East | Kiunga | 2.00'05''S 41.16'32''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2024/2025 | 2025-02-13 | 2025-02-13 | 9674469 | 9674469 |  | CGL | n/a | 9674469 | 0 | 9674469 | 100% | 9674469 |  |  | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
209 | Ndau ECD | Construction of Kiwayuu ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.00'02''S 41.16'31''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2014/2015 | 2014-09-30 | 2014-09-30 | 1808405.2 | 1808405.2 |  | CGL | n/a | 1808405.2 | 0 | 1808405.2 | 100% | 1808405.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
210 | Ndau Dispensary | Construction of Ndau dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.00'02''S 41.16'31''E | Medical Service | Medical | Medical service | - | - | - | - | - | - |  | CGL | n/a | - | 0 | - | - | - | 0 | - | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
211 | Ndau Dispensary | Renovation of Ndau Dispensary | To improve access to essential primary healthcare services by establishing a functional dispensary within the community. | Dispensary constructed | 3110302 | Refurbishment of Non-Residential Buildings | Lamu East | Kiunga | 2.00'02''S 41.16'31''E | Medical Service | Medical | Medical service | - | 2023/2024 | 2024-02-14 | 2024-02-14 | 4000000 | 4000000 |  | CGL | n/a | 4000000 |  | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
212 | Ndau Social Hall | Construction of ndau social hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Kiwayuu social hall | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 2.00'05''S 41.16'32''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | - | - |  | KEMSFED | KEMSFED | - |  | - | - | - | 0 |  | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
213 | Kiunga Wad Admin Office |  | To decentralize county government services by providing a functional administrative centre at the ward level. | Ward Admin office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'45''S 41.29'22''E | Public Service Management/ Adminstration | Administration | Public Service Management/ Adminstration | - | 2016/2017 | 2017-01-29 | 2017-01-29 | 4998277.6 | 4998277.6 |  | CGL | n/a | 4998277.6 | 0 | 4998277.6 | 100% | - | 0 | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
214 | Kiunga Information Center | Renovation of information center at Kiunga | To build youth and professional capacity in emerging technologies and digital innovation. | Information center renovated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'45''S 41.29'22''E | ICT & E-governance | ICT | ICT & E-governance | - | 2024/2025 | 2025-01-21 | 2025-01-21 | 1490078 | 1490078 |  | CGL | n/a | 1490078 | 0 | 1490078 | 100% | 1490078 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
215 | 2 Door VIP Toilet Kiunga | 2 Door VIP Toilet Kiunga | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'45''S 41.29'22''E | Public health, environment and sanitation | sanitation and environment | Public health, environment and sanitation | - | 2018/2019 | 2018-10-31 | 2018-10-31 | 1670951 | 1670951 |  | CGL | n/a | 1670951 | 0 | 1670951 | 100% | 1670951 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
216 | Kiunga Cabro Works | Cabro paved Walkways In Kiunga Town | To improve accessibility and mobility within urban centres, markets, bus parks, and public facilities through durable paved surfaces | Cabro paved road | 3110402 | Access Roads | Lamu East | Kiunga | 1.44'45''S 41.29'22''E | Infrastructure,Roads,Transport and Public Works | Road and Transport | Infrastructure,Roads,Transport and Public Works | - | 2023/2024 | 2024-06-21 | 2024-06-21 | 13467948 | 13467948 |  | CGL | n/a | 13467948 | 0 | 13467948 | 100% | 13467948 |  |  | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
217 | R.O Plant House Kiunga | Construction of R.O Plant House | To enhance public health outcomes by reducing waterborne diseases through provision of treated and safe drinking water. | R.O Plant House constructed | 3112299 | Purchase of Specialised Plant | Lamu East | Kiunga | 1.44'41''S 41.29'24''E | Water and Energy | Water and Energy | Water and Energy | - | 2017/2018 | 2017-09-06 | 2017-09-06 | 10606484.52 | 10606484.52 |  | CGL | n/a | 10606484.52 | 0 | 10606484.52 | 100% | 10362028 | 0 | 0 | Completed | 97.7% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
218 | Kiunga Social Hall | Construction of Kunga social hall | To promote social cohesion and cultural integration by facilitating social, cultural, and recreational events within the county | Social hall constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'42''S 41.29'19''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - |  | - |  |  |  | - |  | - | - | - |  |  |  | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
219 | Kiunga ECD | Construction of Kiunga ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'42''S 41.29'19''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2016/2017 | 2017-05-05 | 2017-05-05 | 2000000 | 2000000 |  | CGL | n/a | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
220 | Renovation of H/facilities-Kiunga | renovation of Kiunga facility | To improve access to comprehensive primary healthcare services for residents within the catchment area | hospital renovated | 3110302 | Refurbishment of Non-Residential Buildings | Lamu East | Kiunga | 1.44'38''S 41.29'18E | Medical Service | Medical Service | Medical Service | - | - | 2015/2021 | 2015/2021 | 1735887.8 | 1735887.8 |  | CGL | n/a | 1735887.8 | 0 | 1735887.8 | 100% | 1735887.8 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
221 | Radiology unit at Kiunga health centre(x-ray and ultrasound) | construction of radiology unit at Kiunga hospital | To improve access to comprehensive primary healthcare services for residents within the catchment area | radiology constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'38''S 41.29'18E | Medical Service | Medical Service | Medical Service | - | - | 2019/2020 | 2019/2020 | 5000000 | 5000000 |  | CGL | n/a | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
222 | Kiunga Health Center Thearter | construction of thearter at Kiunga health center | To improve access to comprehensive primary healthcare services for residents within the catchment area | Theater constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'38''S 41.29'18''E | Medical Service | Medical Service | Medical Service | - | 2023/2024 | 2023-07-19 | 2023-07-19 | 14454220 | 14454220 |  | CGL | n/a | 14454220 | 0 | 14454220 | 100% | 14454220 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
223 | Kiunga Radiology Unit | Construction of Kiunga Radiology Unit | To improve access to comprehensive primary healthcare services for residents within the catchment area | Radiology Unit constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Kiunga | 1.44'38''S 41.29'18''E | Medical Service | Medical Service | Medical Service | - | 2024/2025 | 2025-04-30 | 2025-04-30 | 7907000 | 7907000 |  | KEMFSED | KEMSFED | 7907000 | 0 | 7907000 | 100% | 7907000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
224 | Kiunga Fish Market | Construction of Kiunga Fish Market phase II | To provide a modern, hygienic, and organized marketplace for trading fish and other marine products | Fish market constructed |  | Construction of Kiunga Fish Market phase II | Lamu East | Kiunga | 1.44'47''S 41.29'26''E | Fisheries livestock and co-operative | Fisheries | Fisheries livestock and co-operative | 2016/2017 | - | 2016/2017 | 2016/2017 | 7000000 | 7000000 |  | CGL | n/a | 7000000 | 0 | 7000000 | 100% | 7000000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
225 | Kiunga Fisheries Office | Rehabilitation Of Kiunga Fisheries Office | To provide an administrative and operational base for delivery of fisheries services at the county or sub-county level | Fisheries office rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Lamu East | Kiunga | 1.44'47''S 41.29'26''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | - | - | - | 1391675.2 | 1391675.2 |  | CGL | n/a | 1391675.2 | 0 | 1391675.2 | 100% | 1391675.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
226 | Fencing of playground Kiunga | Fencing of playground Kiunga | To secure the Kiunga playground and ensure safety for users. | Kiunga Playgroung fenced | 3110299 |  | Lamu East | Kiunga | 1.44'42''S 41.29'19''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 2000000 | 2000000 |  | CGL | n/a | 2000000 | 0 | 2000000 | 100% | 0 | 0 | 0 | Completed | 0% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
227 | Kiunga stadium levelling and goalposts | Kiunga stadium levelling and goalposts | To provide a level playing surface and football goalposts to promote sports | Kiunga Stadium levelled | 3110299 |  | Lamu East | Kiunga | 1.44'42''S 41.29'19''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Sports | Education ,Gender,Youth, Sports,Community Development and Social Service | - | - | - | - | 300000 | 300000 |  | CGL | n/a | 300000 | 0 | 300000 | 100% | 300000 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
228 | Construction of 2doors VIP toilet and fencing of Kiunga slaugher house | Construction of 2doors VIP toilet and fencing of Kiunga slaugher house | To improve public health and sanitation by providing safe, hygienic, and well-maintained public toilet facilities in high-traffic public areas. | VIP toilets constructed and Slaughter house fenced. | 3110299 | Construction of building | Lamu East | Kiunga | 1.44'47''S 41.29'26''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | - | - | - | 497698 | 497698 |  | CGL | n/a | 497698 | 0 | 497698 | 100% | - | 0 | 0 | Completed | - | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
229 | Construction of Kiunga slaughter house | Construction of slaughter house at Kiunga | To promote safe meat processing | Slaughter house constructed | 3110299 | Construction of building | Lamu East | Kiunga | 1.44'47''S 41.29'26''E | Fisheries livestock and co-operative | Livestock | Fisheries livestock and co-operative | - | 2016/2017 | 2017-03-04 | 2017-03-04 | 1447587.2 | 1447587.2 |  | CGL | n/a | 1447587.2 | 0 | 1447587.2 | 100% | 1447587.2 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
230 | Kiangwe Primary ECD | Construction of Kiwayuu ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Basuba |  | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2014/2015 | 2015-01-25 | 2015-01-25 | 1847711.8 | 1847711.8 |  | CGL | n/a | 1847711.8 | 0 | 1847711.8 | 100% | 1847711.8 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
231 | Basuba ECD | Construction of Kiwayuu ECDE | To expand access to quality Early Childhood Development and Education (ECDE) by providing adequate, safe, and child-friendly learning spaces | ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, etc..) | Lamu East | Basuba |  | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education ,Gender,Youth, Sports,Community Development and Social Service | - | 2015/2016 | 2015-10-02 | 2015-10-02 | 1792800.88 | 1792800.88 |  | CGL | n/a | 1792800.88 | 0 | 1792800.88 | 100% | 1792800.88 | 0 | 0 | Completed | 100% | n/a | n/a | n/a | n/a | n/a | No |  | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
232 | Inpatient Wards for Mpeketoni Sub-County Hospital | construction of ward at mpeketoni sub-county hospital | improve health service | wards constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'30"S 40°41'50"E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 19/07/2023 | 14622774 | 14622774 | 14622774 | CGL | - | 14622774 | - | 14622774 | 100% | 14622774 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
233 | OPD Facility at Mpeketoni Hospital | construction of opd facility at mpeketoni hospital | improve health service | opd facility constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'30"S 40°41'50"E | medical services | medical services | medical services | 2020/2021 | 2020/2021 | 2020/2021 | 22/02/2021 | 76939220.2 | 76939220.2 | 76939220.2 | CGL | - | 76939220.2 | - | 76939220.2 | 100% | 76939220.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
234 | 4 door VIP Toilet at Uziwa Dispensary | construction of 4 door VIP Toilet at Uziwa Dispensary | improve health serviceand sanitation | 4 door VIP toilet constructed | 3218 | construction of building | Lamu West | BAHARI | 2°21'34"S 40°44'25"E | medical services | medical services | medical services | 2017/2018 | 2017/2018 | 2017/2018 | 25/04/2017 | 999989.6 | 999989.6 | 999989.6 | CGL | - | 999989.6 | - | 999989.6 | 100% | 999989.6 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
235 | Uziwa Dispensary | construction of dispensary at uziwa | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | BAHARI | 2°21'33"S 40°44'25"E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 2016/2017 | 2017-11-01 | 4997802 | 4997802 | 4997802 | CGL | - | 4997802 | - | 4997802 | 100% | 4997802 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
236 | 12 Body Mortuary at Mpeketoni Sub-District Hospital | construction of Body Mortuary at Mpeketoni Sub-District Hospital | improve health service | mortuary constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'28"S 40°41'47"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2016-06-09 | 18857618.9 | 18857618.9 | 18857618.9 | CGL | - | 18857618.9 | - | 18857618.9 | 100% | 18857618.9 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
237 | Construction of Laundry unit at Mpeketoni | Construction of Laundry unit at Mpeketoni | improve health service | laundry constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'28"S 40°41'46"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 0 | 0 | 0 | CGL | - | 0 | - | 0 | 100% | 0 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
238 | Fencing at Mpeketoni Hospital | Fencing at Mpeketoni Hospital | improve health service | hospital fenced | 3218 | construction of building | Lamu West | BAHARI | 2°23'30"S 40°41'50"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 4396493.7 | 4396493.7 | 4396493.7 | CGL | - | 4396493.7 | - | 4396493.7 | 100% | 4396493.7 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
239 | Renovation of Laboratories Mpeketoni | Renovation of Laboratories Mpeketoni | improve health service | laboratory renovated | 3218 | construction of building | Lamu West | BAHARI | 2°23'30"S 40°41'50"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 0 | 0 | 0 | CGL | - | 0 | - | 0 | 100% | 0 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
240 | Construction of Perimeter wall at Mpeketoni Sub-County HospitalnPhase II | Construction of Perimeter wall at Mpeketoni Sub-County HospitalnPhase II | improve health service | perimeter wall constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'29"S 40°41'50"E | medical services | medical services | medical services | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 1580442 | 1580442 | 1580442 | CGL | - | 1580442 | - | 1580442 | 100% | 1580442 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
241 | Proposed maternity wing and renovations of existing building at mpeketoni sub-county hospital | Proposed maternity wing and renovations of existing building at mpeketoni sub-county hospital | improve health service | maternity wing constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'27"S 40°41'49"E | medical services | medical services | medical services | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 6494204.2 | 6494204.2 | 6494204.2 | CGL | - | 6494204.2 | - | 6494204.2 | 100% | 6494204.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
242 | Kiongwe Dispensary | Kiongwe Dispensary | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | BAHARI | 2°22'03"S 40°45'37"E | medical services | medical services | medical services | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 6494204.2 | 6494204.2 | 6494204.2 | CGL | - |  | - |  |  |  | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
243 | Proposed maternity wing at Mkunumbi Dispensary | Proposed maternity wing at Mkunumbi Dispensary | improve health service | maternity wing constructed | 3218 | construction of building | Lamu West | BAHARI | 2°18'16"S 40°42'06"E | medical services | medical services | medical services | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 6494204.2 | 6494204.2 | 6494204.2 | CGL | World Bank, KCDP |  | - |  | 100% | 6494204.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
244 | Pit Latrin at Mpeketoni | Pit Latrin at Mpeketoni | promote proper sanitation around the market | toilet constructed | 3218 | construction of building | Lamu West | BAHARI | 2°23'30"S 40°41'50"E | trade and tourism | trade | trade and tourism | 2015/2016 | 2015/2016 | 2015/2016 | 2016-02-23 | 1160856.54 | 1160856.54 | 1160856.54 | CGL | - | 1160856.54 | - | 1160856.54 | 100% | 1160856.54 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
245 | Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | Construction of Jua Kali shed and Purchase of welding equipment, Kiongwe | promote trade and economic activity | shades constructed | 3218 | construction of building | Lamu West | BAHARI | 2°22'59"S 40°44'22"E | trade and tourism | trade | trade and tourism | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 5849047 | 5849047 | 5849047 | CGL | - | 5849047 | - | 5849047 | 97% | 5849047 | - | 0 | completed | 97% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
246 | Construction of Women Shade at Ngoi | Construction of Women Shade at Ngoi | promote trade and economic activity | Shade constructed | 3219 | construction of building | Lamu West | BAHARI | 2°23'15"S 40°45'42"E | trade and tourism | trade | trade and tourism | [7 empty] | CGL | - |  | - |  |  |  | - | 0 |  |  | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
247 | Pit Latrin at Mpeketoni | Pit Latrin at Mpeketoni | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | BAHARI |  | public health | sanitation and environment | public health | 2015/2016 | 2015/2016 | 2015/2016 | 2016-02-23 | 1160856.54 | 1160856.54 | 1160856.54 | CGL | - | 1160856.54 | - | 1160856.54 | 100% | 1160856.54 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
248 | Construction of public toilets at tewe centre and sikomani primary | Construction of public toilets at tewe centre and sikomani primary | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | BAHARI | 2°24'06"S 40°45'30"E 2°22'23"S 40°43'12"E | public health | sanitation and environment | public health | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | - | 6000000 | - | 6000000 | 100% | 6000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
249 | Construction of public toilets at Tewe and Ngoi Centres | Construction of public toilets at Tewe and Ngoi Centres | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | BAHARI | 2°24'06"S 40°45'30"E 2°23'15"S 40°45'42"E | public health | sanitation and environment | public health | 2021/2022 | 2021/2022 | 2021/2022 | 2021/022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
250 | Kiongwe Public Toilet | Kiongwe Public Toilet | improve hygiene | toilet constructed | 3226 | construction of building | Lamu West | BAHARI | 2°23'06"S 40°44'24"E | public health | sanitation and environment | public health | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
251 | Uziwa Public Toilet | Uziwa Public Toilet | improve hygiene | toilet constructed | 3227 | construction of building | Lamu West | BAHARI | 2°21'33"S 40°44'25"E | public health | sanitation and environment | public health | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
252 | Construction 2 ECDE classrooms and 2 doors VIP toilets at Muungano | Construction 2 ECDE classrooms and 2 doors VIP toilets at Muungano | To improve access to ECDE services | ECDE classrooms and Toilet constructed | 3110299 | ECDE classrooms and Toilet constructed | Lamu West | BAHARI | 2°24'12"S 40°43'35"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
253 | Construction of 2 ECDE classrooms and 2 doors VIP toilets at Tewe | Construction of 2 ECDE classrooms and 2 doors VIP toilets at Tewe | To improve access to ECDE services | ECDE classrooms and Toilet constructed | 3110299 | ECDE classrooms and Toilet constructed | Lamu West | BAHARI | 2°24'09"S 40°45'05"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
254 | Construction 2 ECDE classrooms and 2 doors VIP toilets at Mangu | Construction 2 ECDE classrooms and 2 doors VIP toilets at Mangu | To improve access to ECDE services | ECDE classrooms and Toilet constructed | 3110299 | ECDE classrooms and Toilet constructed | Lamu West | BAHARI | 2°21'57"S 40°45'57"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
255 | Bahati Njema ECD | Construction of ECDE classrooms at Bahati Njema | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | BAHARI | 2°17'50"S 40°40'23"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2015/2016 | 2015/2016 | 2015/2016 | 13/9/2016 | 6579972 | 6579972 | 6579972 | CGL | - | 6579972 | - | 6579972 | 100% | 6579972 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
256 | Lake Kenyatta ECD | Construction of ECDE classrooms at Lake Kenyatta | To improve access to ECDE services | ECDE classrooms and Toilets constructed | 3110299 | Construction of building | Lamu West | BAHARI | 2°23'23"S 40°41'44"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  |  |  | 3276295 | 3276295 | 3276295 | CGL | - | 3276295 | - | 3276295 | 100% | 3276295 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
257 | Ndambwe ECD | Construction of ECDE classrooms at Ndambwe | To improve access to ECDE services | ECDE classrooms and toilets constructed | 3110299 | Construction of building | Lamu West | BAHARI | 2°18'55"S 40°43'32"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2018/2019 | 2018/2019 | 2018/2019 | 15/1/2019 | 3475046.8 | 3475046.8 | 3475046.8 | CGL | - | 3475046.8 | - | 3475046.8 | 100% | 3475046.8 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
258 | Mapenya ECD | Construction of ECDE classrooms at Mapenya | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | BAHARI | 2°21'41"S 40°42'36"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2015/2016 | 2015/2016 | 2015/2016 | 2016-11-01 | 1772142.13 | 1772142.13 | 1772142.13 | CGL | - | 1772142.13 | - | 1772142.13 | 100% | 1772142.13 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
259 | Mapenya Social Hall | Construction of Mapenya Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu West | BAHARI | 2°21'33"S 40°42'22"E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education | 2016/2017 | 2016/2017 | 2016/2017 | 2017-07-02 | 1136781.44 | 1136781.44 | 1136781.44 | CGL | - | 1136781.44 | - | 1136781.44 | 100% | 1136781.44 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
260 | Renovation of ATC | Renovation of ATC | ATC Mpeketoni | ATC Mpeketoni |  | Renovation of ATC | Lamu West | BAHARI | 2°22'43"S 40°41'18"E | Agriculture | Agriculture | Agriculture | [7 empty] | CGL | - |  | - |  |  |  | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
261 | PARTITIONING AND CONSTRUCTION OF MODERN GIS LAB | PARTITIONING AND CONSTRUCTION OF MODERN GIS LAB | PARTITIONING AND CONSTRUCTION OF MODERN GIS LAB | CONSTRUCTION OF MODERN GIS LAB | 3110299 | CONSTRUCTION OF MODERN GIS LAB | Lamu West | HINDI | 2°13'41.9"S 40°50'53.4"E | 3215 | sanitation and environment | public health | 2019/2020 | 2019/2020 | 2019/2020 | 2020-03-11 | 1453955.6 | 1453955.6 | 1453955.6 | CGL | - | 1453955.6 | - | 1453955.6 | 100% | 1453955.6 | - | 0 | completed | 100% | -: -; no: no; n/a: n/a; n/a: n/a; No: No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
262 | 4 door VIP toilet at Tewe Dispensary | construction of 4 door vip toilet at tewe dispensary | improve health service and sanitation | 4 door VIP toilet constructed | 3218 | construction of building | Lamu West | HONGWE | 2°21'33"S 40°44'25"E | medical services | Lands | Lands | 2023/2024 | 2023/2024 | 2023/2024 | 2024-06-03 | 4943710 | 4943710 | 4943710 | CGL | - |  | - | 4943710 | 100% |  | - | 0 | Completed | N/A | - | N/A | N/A | N/A | N/A | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
263 | Tewe Dispensary | construction of dispensary at tewe | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | HONGWE | 2°24'22"S 40°45'31"E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 2016/2017 | 19/01/2017 | 996058.36 | 996058.36 | 996058.36 | CGL | - | 996058.36 | - | 996058.36 | 100% | 996058.36 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
264 | Delivery unit at Muhamarani | construction of delivery unit at muhamarani | improve health service | delivery unit constructed | 3218 | construction of building | Lamu West | HONGWE | 2°19'30"S 40°39'10"E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 2016/2017 | 17/03/2017 | 4899212.44 | 4899212.44 | 4899212.44 | CGL | - | 4899212.44 | - | 4899212.44 | 100% | 4899212.44 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
265 | construction of hongwe dispensary | construction of dispensary at hongwe | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | HONGWE | 2°20'53"S 40°39'54"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 30/11/2016 | 3932330.4 | 3932330.4 | 3932330.4 | CGL | - | 3932330.4 | - | 3932330.4 | 100% | 3932330.4 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
266 | Completion of Bomani Dispensary | construction of dispensary in bomani | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | HONGWE |  | medical services | medical services | medical services | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | - | 6000000 | - | 6000000 | 100% | 6000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
267 | Construction of Bomani public toilet | construction of public toilet in bomani | improve health service | toilet constructed | 3218 | construction of building | Lamu West | HONGWE |  | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | - | 0 | 0 | CGL | - | 0 | - | 0 | 100% | 0 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
268 | Construction of public toilerts at Muamarani | Construction of public toilerts at Muamarani | improve health service | toilet constructed | 3218 | construction of building | Lamu West | HONGWE | 2°19'36"S 40°39'00"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | - | 0 | 0 | CGL | - | 0 | - | 0 | 100% | 0 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
269 | 4 Door VIP Toilet at Bomani | 4 Door VIP Toilet at Bomani | promote trade and economic activity | toilet constructed | 3218 | construction of building | Lamu West | HONGWE |  | trade and tourism | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 951987.2 | 951987.2 | 951987.2 | CGL | - | 951987.2 | - | 951987.2 | 100% | 951987.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
270 | Hongwe Market Phase II | Hongwe Market Phase II | promote trade and economic activity | market constructed | 3218 | construction of building | Lamu West | HONGWE |  | trade and tourism | trade | trade and tourism | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 947221.2 | 947221.2 | 947221.2 | CGL | - | 947221.2 | - | 947221.2 | 100% | 947221.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
271 | Boda Boda shades in Hongwe | Boda Boda shades in Hongwe | promote trade and economic activity | shades constructed | 3218 | construction of building | Lamu West | HONGWE |  | trade and tourism | trade | trade and tourism | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | - | 6000000 | - | 6000000 | 100% | 6000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
272 | Boda Boda shades in Bomani | Boda Boda shades in Bomani | promote trade and economic activity | shades constructed | 3218 | construction of building | Lamu West | HONGWE | 2°22'50"S 40°38'53"E | trade and tourism | trade | trade and tourism | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 1751268 | 1751268 | 1751268 | CGL | - | 1751268 | - | 1751268 | 88% | 1751268 | - | 0 | ongoing | 88% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
273 | 4 Door VIP Toilet at Bomani | 4 Door VIP Toilet at Bomani | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | HONGWE |  | public health | trade | trade and tourism | 2024/2025 | 2024/2025 | 2024/2025 | 2024/2025 |  |  |  | CGL | - |  | - |  | 100% |  | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
274 | Construction of public toilets at Sinambio town and Baraka town | Construction of public toilets at Sinambio town and Baraka town | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | HONGWE |  | public health | sanitation and environment | public health | 2015/2016 | 2015/2016 | 2015/2016 | 2016-05-07 | 947221.2 | 947221.2 | 947221.2 | CGL | - | 947221.2 | - | 947221.2 | 100% | 947221.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
275 | Construction of 2 ECDE classrooms at Sese | Construction of 2 ECDE classrooms at Sese | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | HONGWE | 2°19'56"S 40°40'11"E | Education ,Gender,Youth, Sports,Community Development and Social Service | sanitation and environment | public health | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | - | 6000000 | - | 6000000 | 100% | 6000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
276 | Hongwe Social Hall | Construction of Hongwe Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu West | HONGWE | 2°20'56"S 40°40'01"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2018/2019 | 2018/2019 | 2018/2019 | 16/1/2019 | 3461672 | 3461672 | 3461672 | CGL | - | 3461672 | - | 3461672 | 100% | 3461672 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The ECDE was turned to Hongwe VTC
277 | Construction of 2 Ecde Classrooms And 2 Door Toilet At Kangaja | Construction of 2 Ecde Classrooms And 2 Door Toilet At Kangaja | To improve access to ECDE services | ECDE classrooms and toilets constructed | 3110299 | Construction of building | Lamu West | HONGWE | 2°18'59"S 40°38'03"E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education | 2015/2016 | 2015/2016 | 2015/2016 | 21/9/2016 | 1155655.8 | 1155655.8 | 1155655.8 | CGL | - | 1155655.8 | - | 1155655.8 | 100% | 1155655.8 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
278 | Uziwa Social Hall | Construction of Uziwa Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu West | HONGWE | 2°21'33"S 40°44'26"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3150000 | 3150000 | 3150000 | CGL | - | 3150000 | - | 3150000 | 100% | 3150000 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
279 | Construction of Hongwe Information Centre | Construction of Hongwe Information Centre | Hongwe Information centre | Construction of Hongwe Information centre | 3110299 | Construction of Hongwe Information Centre | Lamu West | HONGWE | 2°20'57"S 40°40'00"E | Construction of Hongwe Information Centre | Social Service | Education | 2015/2016 | 2015/2016 | 2015/2016 | 13/6/2016 | 1153225.6 | 1153225.6 | 1153225.6 | CGL | - | 1153225.6 | - | 1153225.6 | 100% | 1153225.6 | - | 0 | Completed | 1 | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
280 | Construction of Hongwe ward admins office | Construction of Hongwe ward admins office |  |  |  |  | Lamu West | HONGWE | 2°20'59"S 40°41'54"E | Devolution | ICT | ICT | 2024/2025 | 2024/2025 | 2024/2025 | 2025-09-10 | 2999229 | 2999229 | 2999229 | CGL | - | 2999229 | - | 2999229 | 100% | 2999229 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
281 | Mwangaza Boreholes | Mwangaza Boreholes | Mwangaza Boreholes | Mwangaza Boreholes |  | Mwangaza Boreholes | Lamu West | Mkunumbi | 2°21'22"S 40°35'26"E | 3223 | Devolution | Devolution | [7 empty] | CGL | - |  | - |  |  |  | - | 0 |  |  | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
282 | construction of Uziwa Dispensary Laboratory | construction of laboratory at uziwa dispensary | improve health service | laboratory constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°21'33"S 40°44'25"E | medical services | Water and Energy | Water | 2023/2024 | 2023/2024 | 2023/2024 |  | 1744250 | 1744250 | 1744250 | CGL | - |  | - | 1744250 | 100% | 1744250 | - | 0 | Completed | N/A | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
283 | Construction of Dispensary at Mavuno whitehouse | Construction of Dispensary at Mavuno whitehouse | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°20'40"S 40°34'02"E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 2000000 | 2000000 | 2000000 | CGL | - | 2000000 | - | 2000000 | 100% | 2000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
284 | Renovation of H/facilities-Mkunumbi | renovation of health facility in mkunumbi | improve health service | hospital renovated | 3218 | construction of building | Lamu West | MKUNUMBI | 2°18'15"S 40°42'05"E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3000000 | 3000000 | 3000000 | CGL | - | 3000000 | - | 3000000 | 100% | 3000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
285 | Completion and operationalisation of Sina mbio Dispensary | Completion and operationalisation of Sina mbio Dispensary | improve health service | dispensary constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°23'14"S 40°37'15"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 1798252 | 1798252 | 1798252 | CGL | - | 1798252 | - | 1798252 | 100% | 1798252 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
286 | Muhamarani Dispensary | Muhamarani Dispensary | improve health service | dispensary constructed | 3219 | construction of building | Lamu West | MKUNUMBI | 2°19'30"S 40°39'10"E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 6453524 | 6453524 | 6453524 | CGL | - | 6453524 | - | 6453524 | 100% | 6453524 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
287 | Pangani Dispensary (Mavuno) | Pangani Dispensary (Mavuno) | improve health service | dispensary constructed | 3220 | construction of building | Lamu West | MKUNUMBI | 2°20'40"S 40°34'02"E | medical services | medical services | medical services | [7 empty] | CGL | - |  | - |  |  |  | - | 0 |  |  | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
288 | Majembeni Fresh Produce Market | construction of market in majembeni | promote trade and economic activity | market constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°20'18"S 40°37'00"E | trade and tourism | medical services | medical services | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 |  |  |  | CGL | - |  | - |  |  |  | - | 0 |  |  | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
289 | Construction of market and shades in uziwa | Construction of market and shades in uziwa | promote order and reduce congestion | shades constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°21'33"S 40°44'23"E | trade and tourism | trade | trade and tourism | 17/10/2017 | 17/10/2017 | 17/10/2017 | 17/10/2017 | 19566192 | 19566192 | 19566192 | CGL | - | 19566192 | - | 19566192 | 100% | 19566192 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
290 | Construction of Chainlink Fence at Kibaoni Open Market | Construction of Chainlink Fence at Kibaoni Open Market | promote trade and economic activity | chainlink fence constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°19'31"S 40°38'53"E | trade and tourism | trade | trade and tourism | 2016/2017 | 2016/2017 | 2016/2017 | 2016/2017 | 2612500 | 2612500 | 2612500 | CGL | - | 2612500 | - | 2612500 | 100% | 2612500 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the area only consists of a chainlink fence and existing building but not market stalls.
291 | Construction of Majembeni Open Air Market phase II | Construction of Majembeni Open Air Market phase II | promote trade and economic activity | market constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°20'18"S 40°37'00"E | trade and tourism | trade | trade and tourism | 2017/2018 | 2017/2018 | 2017/2018 | 2017/2018 | 1614140 | 1614140 | 1614140 | CGL | - | 1614140 | - | 1614140 | 100% | 1614140 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | The area is bushy but there is presence of the chainlink
292 | Completion of Mpeketoni Market | construction of market in mpeketoni | promote trade and economic activity | market constructed | 3218 | construction of building | Lamu West | MKUNUMBI |  | trade and tourism | trade | trade and tourism | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 3517940.5 | 3517940.5 | 3517940.5 | CGL | - | 3517940.5 | - | 3517940.5 | 100% | 3517940.5 | - | 0 | completed | 54% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
293 | Construction of Majembeni Open Air Market phase III | Construction of Majembeni Open Air Market phase III | promote trade and economic activity | market constructed | 3218 | construction of building | Lamu West | MKUNUMBI | 2°20'18"S 40°37'00"E | trade and tourism | trade | trade and tourism | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | - | 6000000 | - | 6000000 | 100% | 6000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
294 | 4 Door Toilet Muhamarani | 4 Door Toilet Muhamarani | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | MKUNUMBI | 2°19'36"S 40°39'00"E | public health | trade | trade and tourism | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-07-28 |  |  |  | CGL | - |  | - |  | 100% |  | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
295 | Construction of public toilets at Sinambio Town and Baraka Town | Construction of public toilets at Sinambio Town and Baraka Town | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | MKUNUMBI |  | public health | sanitation and environment | public health | 2015/2016 | 2015/2016 | 2015/2016 | 2016-11-02 | 958995.2 | 958995.2 | 958995.2 | CGL | - | 958995.2 | - | 958995.2 | 100% | 958995.2 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
296 | Perimeter Wall at Muhamarani Waste Disposal Site | Perimeter Wall at Muhamarani Waste Disposal Site | improve hygiene | perimeter wall constructed | 3225 | construction of building | Lamu West | MKUNUMBI | 2°19'18"S 40°38'51"E | public health | sanitation and environment | public health | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | 2600000 | 2600000 | 2600000 | CGL | - | 2600000 | - | 2600000 | 100% | 2600000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
297 | Construction of public toilet at widho | Construction of public toilet at widho | improve hygiene | toilet constructed | 3225 | construction of building | Lamu West | MKUNUMBI |  | public health | sanitation and environment | public health | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3000000 | 3000000 | 3000000 | CGL | - | 3000000 | - | 3000000 | 100% | 3000000 | - | 0 | completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
298 | Baraka Public Toilet | Baraka Public Toilet | improve hygiene | toilet constructed | 3226 | construction of building | Lamu West | MKUNUMBI | 2°20'39"S 40°36'51"E | public health | sanitation and environment | public health | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 1500000 | 1500000 | 1500000 | CGL | - | 1500000 | - | 1500000 | 100% | 1500000 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
299 | Construction 2 ECDE classrooms and 2 doors VIP toilets at SHEKALE | Construction 2 ECDE classrooms and 2 doors VIP toilets at SHEKALE | To improve access to ECDE services | ECDE classrooms and Toilet constructed | 3110299 | ECDE classrooms and Toilet constructed | Lamu West | MKUNUMBI | 2°21'07"S 40°42'49"E | Education ,Gender,Youth, Sports,Community Development and Social Service | sanitation and environment | public health |  |  | 2017/2018 | 2017/2018 | 2800000 | 2800000 | 2800000 | CGL | - |  | - |  |  |  | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
300 | Construction 2 ECDE classrooms at TELELANI | Construction 2 ECDE classrooms at TELELANI | To improve access to ECDE services | ECDE classrooms and constructed | 3110299 | ECDE classrooms | Lamu West | MKUNUMBI | 2°20'43"S 40°42'33"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  | 2017/2018 | 2017/2018 | 2800000 | 2800000 | 2800000 | CGL | - |  | - |  |  |  | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
301 | Construction of 2 ECDE classrooms and 2 doors VIP toilets at Muhamarani | Construction of 2 ECDE classrooms and 2 doors VIP toilets at Muhamarani | To improve access to ECDE services | ECDE classrooms and Toilet constructed | 3110299 | Construction of building | Lamu West | MKUNUMBI | 2°19'12"S 40°40'05"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  | 2017/2018 | 2017/2018 | 2800000 | 2800000 | 2800000 | CGL | - |  | - |  |  |  | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
302 | Construction of 2 ECD classrooms and 2 doors VIP toilets at Mwangaza | Construction of 2 ECD classrooms and 2 doors VIP toilets at Mwangaza | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | MKUNUMBI | 2°21'22"S 40°35'23"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  | 2017/2018 | 2017/2018 | 2800000 | 2800000 | 2800000 | CGL | - | 2800000 | - | 2800000 | 100% | 2800000 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
303 | Pangani ECD | Construction of ECDE classrooms at Pangani | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | MKUNUMBI | 2°20'20"S 40°33'03"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  | 2017/2018 | 2017/2018 | 2800000 | 2800000 | 2800000 | CGL | - | 2800000 | - | 2800000 | 100% | 2800000 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
304 | Koreni ECD | Construction of ECDE classrooms at Koreni | To improve access to ECDE services | ECDE classrooms and Toilets constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°16'05"S 40°41'31"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 2016/2017 | 24/3/2017 | 3440050 | 3440050 | 3440050 | CGL | - | 3440050 | - | 3440050 | 100% | 3440050 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
305 | CONSTRUCTION OF 2 ECDE CLASSROOMS AND 2 DOOR TOILET AT MKUNUMBI | CONSTRUCTION OF 2 ECDE CLASSROOMS AND 2 DOOR TOILET AT MKUNUMBI | To improve access to ECDE services | ECDE classrooms and Toilets constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°18'06"S 40°42'00"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  |  |  | 2981686.04 | 2981686.04 | 2981686.04 | CGL | - | 2981686.04 | - | 2981686.04 | 100% | 2981686.04 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
306 | Mkunumbi Social Hall | Construction of Mkunumbi Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°18'05"S 40°42'07"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education |  |  |  |  | 898923 | 898923 | 898923 | CGL | - | 898923 | - | 898923 | 100% | 898923 | - | 0 | Completed | 100% | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
307 | Mkunumbi Social Hall | Construction of Mkunumbi Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°18'05"S 40°42'07"E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education | 2016/2017 | 2016/2017 | 2016/2017 | 15/6/2017 | 7239529.6 | 7239529.6 | 7239529.6 | CGL | - | 7239529.6 | - | 7239529.6 | 100% | 7239529.6 | - | 0 | Completed | 1 | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
308 | Mkunumbi Information center | Renovation of information center at Mkunumbi | To improve access to information services | Information center renovated | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°18'19"S 40°42'07"E | Mkunumbi Information center | Social Service | Education | 2016/2017 | 2016/2017 | 2016/2017 | 15/6/2017 | 7239529.6 | 7239529.6 | 7239529.6 | CGL | - | 7239529.6 | - | 7239529.6 | 100% | 7239529.6 | - | 0 | Completed | 1 | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
309 | Construction of Mkunumbi ward admins office | Construction of Mkunumbi ward admins office | To improve Service Delivary | ward office constructed |  | Construction of building | Lamu West | Mkunumbi | 2°18'19"S 40°42'07"E | Devolution | ICT | ICT | 2016/2017 | 2016/2017 | 2016/2017 | 15/6/2017 | 999908.4 | 999908.4 | 999908.4 | CGL | - | 999908.4 | - | 999908.4 | 100% | 999908.4 | - | 0 | Completed | 1 | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
310 | Sikomani Primary ECD | Construction of ECDE classrooms at Sikomani Primary | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°22'23"S 40°43'12"E | Education ,Gender,Youth, Sports,Community Development and Social Service | Devolution | Devolution | 2016/2017 | 2016/2017 | 2016/2017 | 15/6/2017 | 999908.4 | 999908.4 | 999908.4 | CGL | - | 999908.4 | - | 999908.4 | 100% | 999908.4 | - | 0 | Completed |  | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
311 | Construction of 2 ECDE Classrooms and 2 door toilet at Majembeni primary | Construction of 2 ECDE Classrooms and 2 door toilet at Majembeni primary | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu West | Mkunumbi | 2°19'20"S 40°36'40"E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2019/2020 | 2019/2020 | 2019/2020 | 31/7/2020 | 3146200 | 3146200 | 3146200 | CGL |  | 3146200 | 0 | 3146200 | 100% | 3146200 |  | 0 | Completed | 1 | - | n/a | n/a | n/a | n/a | no | n/a | n/a | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | No | Formal screening not done; safeguards will be incorporated in future project planning. | No | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation.
312 | Weigh Bridge | Construction of a weighbridge facility | To improve vehicle load control and enhance road safety | Weighbridge facility constructed | 3213 | construction | lamu west | WITU | 2 23'11''S 40 25'59''E | FINANCE | FINANCE | FINANCE | 2013/2014 | 2013/2014 | 2014-10-04 | 2014-10-04 | 5000000 | 5000000 | 5000000 | CGL | N/A | 50000000 | N/A | 4996932 | 100% | 4996932 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
313 | revenue staff shade in witu | construction of revenue staff shade | to improve revenue collection | shade constructed | 3213 | construction of building | lamu west | WITU | 2 23'19''S 40 26'9''E | FINANCE | FINANCE | FINANCE | 2013/2014 | 2013/2014 | 2014-10-04 | 2014-10-04 | 1500000 | 1500000 | 1500000 | CGL | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
314 | Pangani cattle dip | Construction of cattle dip at Pangani | To control livestock diseases | Cattle dip constructed | 3110299 | Construction of building | Lamu west | Witu | 2 20'43''S 40 34'0''E | Livestock | Livestock | Livestock | 2016/2017 | 2016/2017 | 2017 | 2017 | 2921663 | 2921663 | 2921663 | CGL | N/A | 2921663 | N/A | 2921663 | 100% | 2921663 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
315 | Moa cattle dip | Construction of cattle dip at Moa | To control livestock diseases | Cattle dip constructed | 3110299 | Construction of building | Lamu west | Witu | 2 21'51''S 40 19'24''E | Livestock | Livestock | Livestock | 2016/2017 | 2016/2017 | 2017 | 2017 | 3109454 | 3109454 | 3109454 | CGL | N/A | 3109454 | N/A | 3109454 | 100% | 3109454 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
316 | Chalaluma cattle dip | Construction of cattle dip at Chalaluma | To control livestock diseases | Cattle dip constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'21''S 40 21'3''E | Livestock | Livestock | Livestock | 2016/2017 | 2016/2017 | 13/10/2016 | 13/10/2016 | 808612.8 | 808612.8 | 808612.8 | CGL | N/A | 808612.8 | N/A | 808612.8 | 100% | 808612.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
317 | Kitumbini cattle dip | Construction of cattle dip at Kitumbini | To control livestock diseases | Cattle dip constructed | 3110299 | Construction of building | Lamu west | Witu | 2 23'46''S 40 26'38''E | Livestock | Livestock | Livestock | 2020/2021 | 2020/2021 | 17/06/2021 | 17/06/2021 | 3958094 | 3958094 | 3958094 | CGL | N/A | 3958094 | N/A | 3958094 | 100% | 3958094 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
318 | Rehabilitaion of Nagele Livestock Market | Rehabilitation of livestock market at Nagele | To improve livestock trading environment | Livestock market rehabilitated | 3110299 | Construction of building | Lamu west | Witu | 2 22'13''S 40 22'20''E | Livestock | Livestock | Livestock | 2023/2024 | 2023/2024 | 29/12/2023 | 29/12/2023 | 2999850 | 2999850 | 2999850 | CGL | N/A | 2999850 | N/A | 2999850 | 100% | 2999850 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
319 | Witu Information center | Renovation and equipping of information center at Witu | To improve access to information services | Information center renovated and equipped | 3110299 | Construction of building | Lamu west | Witu | 2 23'17''S 40 26'30''E | ICT | ICT | ICT | 2016/2017 | 2016/2017 | 2017-05-04 | 2017-05-04 | 580011.8 | 580011.8 | 580011.8 | CGL | N/A | 580011.8 | N/A | 580011.8 | 100% | 580011.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
320 | witu public WIFI | public wifi installed at witu | To improve access to information services | WIFI installed | 3110299 | WIFI installed | Lamu west | Witu | 2 23'18''S 40 26'25''E | ICT | ICT | ICT | 2022/2023 | 2022/2023 | 22/4/2023 | 22/4/2023 | 1000000 | 1000000 | 1000000 | CGL | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
321 | Katsaka Kairu ECD | Construction of ECDE classrooms at Katsaka Kairu | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 20'45''S 40 21'13''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2021/2022 | 2021/2022 | 30/5/2022 | 30/5/2022 | 3299057.4 | 3299057.4 | 3299057.4 | CGL | N/A | 3299057.4 | N/A | 3299057.4 | 100% | 3299057.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
322 | Tangeni ECD | Construction of ECDE classrooms at Tangeni | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | witu | 2 21'36''S 40 24'53''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2020/2021 | 2020/2021 | 15/3/2021 | 15/3/2021 | 2995226 | 2995226 | 2995226 | CGL | N/A | 2995226 | N/A | 2995226 | 100% | 2995226 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
323 | Amkeni ECD | Construction of ECDE classrooms at Amkeni | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 22'37''S 40 34'5''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2019/2020 | 2019/2020 | 28/2/2020 | 28/2/2020 | 3440000 | 3440000 | 3440000 | CGL | N/A | 3440000 | N/A | 3440000 | 100% | 3440000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
324 | Moa ECD | Construction of ECDE classrooms at Moa | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 21'29''S 40 18'57''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2018/2019 | 2018/2019 | 2019-09-05 | 2019-09-05 | 2200000.32 | 2200000.32 | 2200000.32 | CGL | N/A | 2200000.32 | N/A | 2200000.32 | 100% | 2200000.32 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
325 | Pangani ECD | Construction of ECDE classrooms at Pangani | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 20'21''S 40 33'5''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 24/3/2017 | 24/3/2017 | 3440050 | 3440050 | 3440050 | CGL | N/A | 3440050 | N/A | 3440050 | 100% | 3440050 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
326 | Chalaluma ECD | Construction of ECDE classrooms at Chalaluma | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'28''S 40 21'31''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 24/3/2017 | 24/3/2017 | 1891101.6 | 1891101.6 | 1891101.6 | CGL | N/A | 1891101.6 | N/A | 1891101.6 | 100% | 1891101.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
327 | Sendemke ECD | Construction of ECDE classrooms at Sendemke | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 21'37''S 40 24'18''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 24/1/2017 | 24/1/2017 | 1997288 | 1997288 | 1997288 | CGL | N/A | 1997288 | N/A | 1997288 | 100% | 1997288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
328 | Maisha Masha ECD | Construction of ECDE classrooms at Maisha Masha | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'40''S 40 32'22''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2015/2016 | 2015/2016 | 2016-11-01 | 2016-11-01 | 1728968.4 | 1728968.4 | 1728968.4 | CGL | N/A | 1728968.4 | N/A | 1728968.4 | 100% | 1728968.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
329 | Lumshi ECD | Construction of ECDE classrooms at Lumshi | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'40''S 40 33'35''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2015/2016 | 2015/2016 | 2016-09-05 | 2016-09-05 | 1792727.8 | 1792727.8 | 1792727.8 | CGL | N/A | 1792727.8 | N/A | 1792727.8 | 100% | 1792727.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
330 | Vipingoni ECD | Construction of ECDE classrooms at Vipingoni | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 23'13''S 40 24'23''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 26/10/2016 | 26/10/2016 | 2162389.64 | 2162389.64 | 2162389.64 | CGL | N/A | 2162389.64 | N/A | 2162389.64 | 100% | 2162389.64 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
331 | Maleli ECD | Construction of ECDE classrooms at Maleli | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 18'23''S 40 24'10''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 14/12/2016 | 14/12/2016 | 1792693 | 1792693 | 1792693 | CGL | N/A | 1792693 | N/A | 1792693 | 100% | 1792693 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
332 | Witu ECD | Construction of ECDE classrooms at Witu | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 23'13''S 40 26'23''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 22/12/2016 | 22/12/2016 | 1799252.8 | 1799252.8 | 1799252.8 | CGL | N/A | 1799252.8 | N/A | 1799252.8 | 100% | 1799252.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
333 | Rehema ECD | Construction of ECDE classrooms at Rehema | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 22'11''S 40 27'47''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 2016-05-11 | 2016-05-11 | 2117299.28 | 2117299.28 | 2117299.28 | CGL | N/A | 2117299.28 | N/A | 2117299.28 | 100% | 2117299.28 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
334 | Boramoyo ECD | Construction of ECDE classrooms at Boramoyo | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 19'48''S 40 21'17''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 2016-10-12 | 2016-10-12 | 1781481.6 | 1781481.6 | 1781481.6 | CGL | N/A | 1781481.6 | N/A | 1781481.6 | 100% | 1781481.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
335 | Soroko ECD | Construction of ECDE classrooms at Soroko | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'17''S 40 28''18''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 14/12/2016 | 14/12/2016 | 1992010 | 1992010 | 1992010 | CGL | N/A | 1992010 | N/A | 1992010 | 100% | 1992010 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
336 | Witu social hall | Construction of Witu Social Hall | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building | Lamu west | Witu | 2 23'16''S 40 26'31''E | Education ,Gender,Youth, Sports,Community Development and Social Service | Social Service | Education | 2020/2021 | 2020/2021 | 2020-05-12 | 2020-05-12 | 5749478.64 | 5749478.64 | 5749478.64 | CGL | N/A | 5749478.64 | N/A | 5749478.64 | 100% | 5749478.64 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
337 | Nairobi area ECDE classroom and toilet | Construction of 2 ECDE classrooms and 2 door toilet at Nairobi Area | To improve learning and sanitation conditions | ECDE classrooms and toilet constructed | 3110299 | Construction of building | Lamu west | WITU | 2 25'22''S 40 24'44''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2021/2022 | 2021/2022 | 29/04/2022 | 29/04/2022 | 2758823 | 2758823 | 2758823 | CGL | N/A | 2758823 | N/A | 2758823 | 100% | 2758823 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
338 | Maisha Masha levelling, goalposts and nets | installing goalpost at maishamasha | improve sports activity | goalpost installed | 3110299 | Construction of building |  | WITU | 2 24'40''S 40 32'20''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 25/08/2016 | 25/08/2016 | 200000 | 200000 | 200000 | CGL | N/A | 200000 | N/A | 190000 | 100% | 190000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
339 | Construction of Mavuno Toilet | construction of toilet at mavuno | improve sanitation | toilet constructed | 3110299 | Construction of building |  | WITU | 2 20'40''S 40 34'2''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 25/08/2016 | 25/08/2016 | 1500000 | 1500000 | 1500000 | CGL | N/A | 1500000 | N/A |  | 100% |  | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
340 | Kitumbini ECDE | Construction of ECDE at kitumbini | promote childhood education | ecde constructed | 3110299 | Construction of building | Lamu west | Witu | 2 24'2''S 40 26'15''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 0 | 0 | stalled project | stalled project | 3000000 | 3000000 | 3000000 | CGL | N/A | 3000000 | N/A | 3000000 |  | 3000000 | N/A | N/A | Stalled |  | 50% | regime change | 2018 | 4 months | 2000000 | NO | to complete the project | financial | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the project stalled
341 | Witu Accident and emergency unit | construction of emergency unit at witu health center | improve health service | emergency unit constructed | 3218 | construction of building | lamu west | WITU | 2 16'09''S 40 50'21''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 23/06/2023 | 23/06/2023 | 2499897.44 | 2499897.44 | 2499897.44 | CGL | N/A | 2499897.44 | N/A | 2499897.44 | 100% | 2499897.44 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the project is complete but they need electrical upgrade with a transformer
342 | 4 door VIP toilet at Moa Dispensary | construction of 4 door VIP toilet at Moa Dispensary | improve health service | 4 door VIP toilet constructed | 3218 | construction of building | lamu west | WITU | 2 21'36''S 40 19'18''E | medical services | medical services | medical services | 2017/2018 | 2017/2018 | 23/05/2018 | 23/05/2018 | 999920 | 999920 | 999920 | CGL | N/A | 999920 | N/A | 999920 | 100% | 999920 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
343 | Laundry at Witu Sub-District Hospital | construction of laundry at witu hospital | improve health service | laundry constructed | 3218 | construction of building | lamu west | WITU | 2 23'14''S 40 26'27''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 16/06/2017 | 16/06/2017 | 5999500.28 | 5999500.28 | 5999500.28 | CGL | N/A | 5999500.28 | N/A | 5999500.28 | 100% | 5999500.28 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the building is complete but it lacks necessary machines to carry out daily activities
344 | Witu Theatre | construction of theater at witu hospital | improve health service | theater constructed | 3218 | construction of building | lamu west | WITU | 2 23'17''S 40 26'22''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 16/02/2017 | 16/02/2017 | 9443420.8 | 9443420.8 | 9443420.8 | CGL | N/A | 9443420.8 | N/A | 9443420.8 | 100% | 9443420.8 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
345 | Maisha Masha Dispensary | consruction of dispensary at maisha masha | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 24'31''S 40 32'22''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 15/06/2017 | 15/06/2017 | 4957880 | 4957880 | 4957880 | CGL | N/A | 4957880 | N/A | 4957880 | 100% | 4957880 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | project is complete but it needs electrical connectivity and network is a problem they face a lot of challenges when carrying out SHA payments
346 | Katsakakairu dispensary | construction of dispensary at katsakakairu | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 21'31''S 40 21'28''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 2017-08-06 | 2017-08-06 | 4798050 | 4798050 | 4798050 | CGL | N/A | 4798050 | N/A | 4798050 | 100% | 4798050 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
347 | 4 door VIP latrine at Katsakairu Dispensary | construction of 4 door VIP latrine at Katsakairu Dispensary | improve health service | 4 door VIP toilet constructed | 3218 | construction of building | lamu west | WITU | 2 20'49''S 40 21'17E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 2017-08-06 | 2017-08-06 | 996058.36 | 996058.36 | 996058.36 | CGL | N/A | 996058.36 | N/A | 996058.36 | 100% | 996058.36 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
348 | Moa Dispensary | construction of moa dispensary | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 21'36''S 40 19'17''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 25/08/2016 | 25/08/2016 | 5178332.8 | 5178332.8 | 5178332.8 | CGL | N/A | 5178332.8 | N/A | 5178332.8 | 100% | 5178332.8 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
349 | Construction of Maternity Wing at Maisha Masha | Construction of Maternity Wing at Maisha Masha | improve health service | maternity wing constructed | 3218 | construction of building | lamu west | WITU | 2 23'9''S 40 28'15''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 2500000 | 2500000 | 2500000 | CGL | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | project is complete but it is not in use because it needs complete renovation
350 | Construction of Dispensary at Mavuno whitehouse | Construction of Dispensary at Mavuno whitehouse | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 20'40''S 40 34'2''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3000000 | 3000000 | 3000000 | CGL | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
351 | Construction of Chalaluma dispensary | construction of chalaluma dispensary | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 24'18''S 40 21'23E | medical services | medical services | medical services | 2020/2021 | 2020/2021 | 2020/2021 | 2020/2021 | 6000000 | 6000000 | 6000000 | CGL | N/A | 6000000 | N/A | 6000000 | 100% | 6000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
352 | Construction of new OPD block at Witu H/C -Phase 2 | construction opd at witu hospital | improve health service | opd facility constructed | 3218 | construction of building | lamu west | WITU | 2 23'15''S 40 26'20''E | medical services | medical services | medical services | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 5000000 | 5000000 | 5000000 | CGL | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | project is complete but the facility need medical and laboratory equipments and renovation of maternity wing
353 | Witu perimetre fence | construction of perimeter fence in witu | improve health service | perimeter wall constructed | 3218 | construction of building | lamu west | WITU | 2 23'14''S 40 26'25''E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 1186771.22 | 1186771.22 | 1186771.22 | GOK | N/A | 1186771.22 | N/A | 1186771.22 | 100% | 1186771.22 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
354 | Provision of Public toilets- Witu & Lamu | Provision of Public toilets- Witu & Lamu | improve health service | toilet constructed | 3218 | construction of building | lamu west | WITU | 2 23'17''S 40 26'25''E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 1500000 | 1500000 | 1500000 | GOK | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
355 | DIDE WARIDE DISPENSARY | construction of dispensary at dide waride | improve health service | dispensary constructed | 3218 | construction of building | lamu west | WITU | 2 24'59''S 40 23'52''E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 6000000 | 6000000 | 6000000 | CGL | N/A | 6000000 | N/A | 6000000 | 100% | 6000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
356 | Construction of incinerator with shed at witu health center | Construction of incinerator with shed at witu health center | improve health service | incinerator constructed | 3218 | construction of building | lamu west | WITU | 2 23'14''S 40 26'27''E | medical services | medical services | medical services | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 657801.2 | 657801.2 | 657801.2 | CGL | N/A | 657801.2 | N/A | 657801.2 | 100% | 657801.2 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the building is complete but its not an incinerator its burninig chamber and the hospital needs modern incinarotor
357 | Construction of ward administrators office in witu | administrators office constructed | improve service | ward office constructed | 3230 | construction of building | lamu west | WITU | 2 23'15''S 40 26'37''E | DEVOLUTION | DEVOLUTION | DEVOLUTION | 2014/2015 | 2014/2015 | 2014-10-11 | 2014-10-11 | 5000000 | 5000000 | 5000000 | CGL | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the building is complete but needs rehabilitation and essential stationaries for the staff
358 | vipingoni water pan | construction of water pan at vipingoni | provision of water | water pan constructed | 3223 | construction of building | lamu west | WITU | 2 22'44''S 40 24'18''E | water | water | water | 2022/2023 | 2022/2023 | 23/4/2023 | 23/4/2023 | 2000000 | 2000000 | 2000000 | cgl | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | complete | 100% | n/a | n/a | n/a | n/a | n/a | no | N/A | N/A | no | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | no | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Complete and operational
359 | chalaluma streetlight | installation of streetlight at chalaluma village | provide security | streetlight installed | 3228 | streetlight installation | lamu west | WITU | 2 23'12''S 40 23'30''E | water and energy | water and energy | water and energy | 2015/2016 | 2015/2016 | 2015-03-08 | 2015-03-08 | 300000 | 300000 | 300000 | CGL | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | complete | 100% | n/a | n/a | n/a | n/a | n/a | no | N/A | N/A | no | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | no | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Complete and operational
360 | katsakakairu streetlight | installation of streetlight at katsakairu | provide security | streetlight installed | 3228 | streetlight installation | lamu west | WITU | 2 20'48''S 40 21'17''E | water and energy | water and energy | water and energy | 2015/2016 | 2015/2016 | 2015-03-09 | 2015-03-09 | 300000 | 300000 | 300000 | CGL | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | complete | 100% | n/a | n/a | n/a | n/a | n/a | no | N/A | N/A | no | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | no | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Complete and operational
361 | witu town streetlights | installation of streetlight at witu town | provide security | streetlight installed | 3228 | streetlight installation | lamu west | WITU | 2 23'18''S 40 26'24''E | water and energy | water and energy | water and energy | 2015/2016 | 2015/2016 | 2015-03-10 | 2015-03-10 | 300000 | 300000 | 300000 | CGL | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | complete | 100% | n/a | n/a | n/a | n/a | n/a | no | N/A | N/A | no | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | no | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Complete and operational
362 | pangani streetlight | installation of streetlight at pangani | provide security | streetlight installed | 3228 | streetlight installation | lamu west | WITU | 2 21'26''S 40 34'15''E | water and energy | water and energy | water and energy | 2015/2016 | 2015/2016 | 2015-03-11 | 2015-03-11 | 300000 | 300000 | 300000 | CGL | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | complete | 100% | n/a | n/a | n/a | n/a | n/a | no | N/A | N/A | no | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | no | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | Complete and operational
363 | mokowe town dumping site | construction of dumping site | improve hygiene | dumping site constructed | 3225 | construction of building | lamu west | HINDI | 2 14'12''S 40 50'55''E | public health | sanitation and environment | public health | 2023/2024 | 2023/2024 | 2023-03-12 | 2023-03-12 | 1500000 | 1500000 | 1500000 | CGL | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
364 | Construction of Waste Transfer Station | Construction of Waste Transfer Station | improve hygiene | waste transfer constructed | 3225 | construction of building | lamu west | HINDI | 2 15'31''S 40 53'17''E | public health | sanitation and environment | public health | 2023/2024 | 2023/2024 | 2023/2024 | 2023/2024 | 4000000 | 4000000 | 4000000 | CGL | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
365 | mokowe ward admin office | administrators office constructed | improve service | ward office constructed | 3230 | construction of building | lamu west | mokowe | 2 13'42''S 40 51'00''E | DEVOLUTION | DEVOLUTION | DEVOLUTION | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 5000000 | 5000000 | 5000000 | CGL | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
366 | Modern Toilet at Mokowe Town | construction Modern Toilet at Mokowe Town | promote proper sanitation around the market | toilet constructed | 3218 | construction of building | lamu west | HINDI | 2 14'12''S 40 50'54''E | trade and tourism | trade | trade and tourism | 2021/2022 | 2021/2022 | 2021-11-22 | 2021-11-22 | 1221062.4 | 1221062.4 | 1221062.4 | CGL | N/A | 1221062.4 | N/A | 1221062.4 | 100% | 1221062.4 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
367 | 4 Door VIP Toilet Ndeu | 4 Door VIP Toilet Ndeu | promote proper sanitation around the market | toilet constructed | 3218 | construction of building | lamu west | HINDI | 2 11'47''S 40 46'40''E | trade and tourism | trade | trade and tourism | 2019/2020 | 2019/2020 | 2019-01-09 | 2019-01-09 | 1499999.48 | 1499999.48 | 1499999.48 | CGL | N/A | 1499999.48 | N/A | 1499999.48 | 100% | 1499999.48 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
368 | Hindi fresh produce market | Hindi fresh produce market | promote proper sanitation around the market | toilet constructed | 3218 | construction of building | lamu west | HINDI | 2 10'35''S 40 48'49''E | trade and tourism | trade | trade and tourism | 2017/2018 | 2017/2018 | 2018-12-01 | 2018-12-01 | 8347046.8 | 8347046.8 | 8347046.8 | CGL | N/A | 8347046.8 | N/A | 8347046.8 | 100% | 8347046.8 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | the previous project was stalled but there is a new market that is under construction.
369 | CONSTRUCTION OF PUBLIC TIOLET AT HINDI | CONSTRUCTION OF PUBLIC TIOLET AT HINDI | promote proper sanitation around the market | toilet constructed | 3218 | construction of building | lamu west | HINDI | 2 10'51''S 40 48'56''E | trade and tourism | trade | trade and tourism | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 890122 | 890122 | 890122 | CGL | N/A | 890122 | N/A | 890122 | 100% | 890122 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
370 | Boda Boda shades in Hindi | Boda Boda shades in Hindi | promote trade and economic activity | shades constructed | 3218 | construction of building | lamu west | HINDI | 2 10'51''S 40 48'56''E | trade and tourism | trade | trade and tourism | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 1714924.8 | 1714924.8 | 1714924.8 | CGL | N/A | 1714924.8 | N/A | 1714924.8 | 100% | 1714924.8 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
371 | Mokowe modern market | construction of market at mokowe | promote trade and economic activity | market constructed | 3218 | construction of building | lamu west | HINDI | 2 13'40''S 40 51'27''E | trade and tourism | trade | trade and tourism | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 10000000 | 10000000 | 10000000 | CGL | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
372 | Mokowe market dumping site | construction of dumping site | promote health and sanitation around market place | dumping site constructed | 3218 | construction of building | lamu west | HINDI | 2 13'39''S 40 51'28''E | trade and tourism | trade | trade and tourism | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 1500000 | 1500000 | 1500000 | CGL | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | No | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
373 | Ablution block at Hindi Health Center | construction of ablution block at hindi health center | improve health service | abluation block constructed | 3218 | construction of building | lamu west | HINDI | 2 10'33''S 40 48'42''E | medical services | medical services | medical services | 2019/2020 | 2019/2020 | 26/06/2020 | 26/06/2020 | 2901358.35 | 2901358.35 | 2901358.35 | CGL | N/A | 2901358.35 | N/A | 2901358.35 | 100% | 2901358.35 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
374 | Hindi Health Centre | construction of health center at hindi | improve health service | health center constructed | 3218 | construction of building | lamu west | HINDI | 2 10'34''S 40 48'42''E | medical services | medical services | medical services | 2016/2017 | 2016/2017 | 19/06/2017 | 19/06/2017 | 18634350.2 | 18634350.2 | 18634350.2 | CGL | N/A | 18634350.2 | N/A | 18634350.2 | 100% | 18634350.2 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | project is complete but it need security fence,new roofing and power backup incase of power failure
375 | Upgrading of Mokowe Health centre | upgrade of health center at mokowe | improve health service | health center upgraded | 3218 | construction of building | lamu west | HINDI | 2 13'56''S 40 51'17''E | medical services | medical services | medical services | 2015/2016 | 2015/2016 | 2015/2016 | 2015/2016 | 3000000 | 3000000 | 3000000 | GOK | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
376 | MOKOWE maternity wing | construction of maternity wing at mokowe hospital | improve health service | maternity wing constructed | 3218 | construction of building | lamu west | HINDI | 2 13'53''S 40 51'18''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3000000 | 3000000 | 3000000 | CGL | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
377 | mokowe male and female wards | construction of male and female ward at mokowe hospital | improve health service | wards constructed | 3218 | construction of building | lamu west | HINDI | 2 13'54''S 40 51'18''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 5000000 | 5000000 | 5000000 | CGL | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
378 | mokowe main theater | construction of mokowe main theater | improve health service | theater constructed | 3218 | construction of building | lamu west | HINDI | 2 13'55''S 40 51'18''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 5000000 | 5000000 | 5000000 | CGL | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
379 | mokowe hospital phsysotherapy | construction of mokowe hospital physotherapy | improve health service | phsysotherapy constructed | 3218 | construction of building | lamu west | HINDI | 2 13'55''S 40 51'19''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 2000000 | 2000000 | 2000000 | CGL | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
380 | mokowe hospital eye unit | construction of mokowe hospital eye unit | improve health service | eye unit constructed | 3218 | construction of building | lamu west | HINDI | 2 13'56''S 40 51'19''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 2000000 | 2000000 | 2000000 | CGL | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
381 | mokowe hospital kitchen | construction of mokowe hospital kitchen | improve health service | kitchen constructed | 3218 | construction of building | lamu west | HINDI | 2 13'56''S 40 51'20''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 1000000 | 1000000 | 1000000 | CGL | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
382 | mokowe hospital asbestos unit | construction of asbestos unit at mokowe hospital | improve health service | asbestos unit constructed | 3218 | construction of building | lamu west | HINDI | 2 13'55''S 40 51'14''E | medical services | medical services | medical services | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 1000000 | 1000000 | 1000000 | CGL | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | complete and operational
383 | revenue staff shade in NDEU | construction of revenue staff shade | to improve revenue collection | shade constructed | 3213 | construction of building | lamu west | hindi | 2 11'47''S 40 46'40''E | FINANCE | FINANCE | FINANCE | 2014/2015 | 2014/2015 | 2014/2015 | 2014/2015 | 1500000 | 1500000 | 1500000 | CGL | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
384 | Mokowe ICT Hub | construction of ict hub | To improve access to information services | ICT HUB constructed | 3110299 | Construction of building | Lamu west | mokowe | 2 13'41''S 40 51'00''E | ICT | ICT | ICT | 2022/2023 | 2022/2023 | 2022/2023 | 2022/2023 | 3000000 | 3000000 | 3000000 | CGL | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
385 | hindi public WIFI | public wifi installed at hindi | To improve access to information services | WIFI installed | 3110299 | WIFI installed | Lamu west | HINDI | 2 15'31''S 40 53'17''E | ICT | ICT | ICT | 2023/2024 | 2023/2024 | 2023/2024 | 2023/2024 | 1000000 | 1000000 | 1000000 | CGL | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
386 | mokowe public WIFI | public wifi installed at mokowe | To improve access to information services | WIFI installed | 3110299 | WIFI installed | Lamu west | HINDI | 2 14'13''S 40 50'54''E | ICT | ICT | ICT | 2023/2024 | 2023/2024 | 2023/2024 | 2023/2024 | 1000000 | 1000000 | 1000000 | CGL | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | PROJECT IS COMPLETE AND OPERATIONAL
387 | Hindi ECD | Construction of ECDE classrooms at Hindi | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 10'56''S 40 49'3''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2020/2021 | 2020/2021 | 13/1/2021 | 13/1/2021 | 3599967.2 | 3599967.2 | 3599967.2 | CGL | N/A | 3599967.2 | N/A | 3599967.2 | 100% | 3599967.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
388 | Bobo ECD | Construction of ECDE classrooms at Bobo | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 10'28''S 40 48'39''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2018/2019 | 2018/2019 | 2018-09-11 | 2018-09-11 | 3465766.8 | 3465766.8 | 3465766.8 | CGL | N/A | 3465766.8 | N/A | 3465766.8 | 100% | 3465766.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
389 | Ndeu ECD | Construction of ECDE classrooms at Ndeu | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 11'51''S 40 47'26''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2016/2017 | 2016/2017 | 2017-12-06 | 2017-12-06 | 2276349.2 | 2276349.2 | 2276349.2 | CGL | N/A | 2276349.2 | N/A | 2276349.2 | 100% | 2276349.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
390 | Mokowe Primary ECD | Construction of ECDE classrooms at Mokowe Primary | To improve access to ECDE services | ECDE classrooms constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 14'09''S 40 51'01''S | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2014/2015 | 2014/2015 | 26/1/2015 | 26/1/2015 | 1792800.88 | 1792800.88 | 1792800.88 | CGL | N/A | 1792800.88 | N/A | 1792800.88 | 100% | 1792800.88 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
391 | Social HALL at Mokowe Town | construction of social hall at mokowe town | To enhance access to community meeting space | Social hall constructed | 3110299 | Construction of building |  |  | 2 14'00''S 40 50'50''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2018/2019 | 2018/2019 | 2018/2019 | 2018/2019 | 1925909 | 1925909 | 1925909 | CGL | N/A | 1925909 | N/A | 1925371.48 | 99.97% | 1925371.48 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
392 | Construction of Milimani ECD/NEW ECDE IN MOKOWE | Construction of ECDE | promote childhood education | ecde constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 14'10''S 40 51'00''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 3300000 | 3300000 | 3300000 | CGL | N/A | 3300000 | N/A | 3300000 | 100% | 3300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
393 | Wadhajir ECDE | construction of ecde at wadhajir | promote childhood education | ecde constructed | 3110299 | Construction of building | Lamu west | Hindi | 2 13'58''S 40 50'24''E | Education ,Gender,Youth, Sports,Community Development and Social Service | ECDE | Education | 2019/2020 | 2019/2020 | 2019/2020 | 2019/2020 | 3000000 | 3000000 | 3000000 | CGL | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
394 | Proposed Cabro Works at Mpeketoni Market and Matondoni - Mkomani Ward. | Cabro Paving of Roads | Improved transport services | Motorable road |  | Roads and Transport | Lamu west | Bahari, Mkomani | 2°16'04.37"S 40°50'23.02"E 2°23'18.29"S 40°41'54.07"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2019/2020 |  |  |  | 15582129.2 | 15582129.2 | 15582129.2 | CGL | N/A | 15582129.2 | N/A | 15582129.2 | 100% | 15582129.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
395 | Proposed Cabro Paving Works at Mpeketoni Buspark (former Market) Phase II. | Cabro Paving of Buspark | Improved accessibility | Transport Improved |  | Roads and Transport | Lamu west | Bahari | 2°23'18.29"S 40°41'54.07"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2019/2020 |  |  |  | 9285684 | 9285684 | 9285684 | CGL | N/A | 9285684 | N/A | 9285684 | 100% | 9285684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
396 | A7 Junction - Moa - Chalaluma Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Witu | 2°21'47.16"S 40°19'45.73"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 5th Feb 2021 | 5th June 2021 | 5th June 2021 | 6000002.4 | 5978396.4 | 6000002.4 | CGL | N/A | 5978396.4 | N/A | 5978396.4 | 100% | 5978396.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
397 | A7 Junction-Nairobi Area Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Witu | 2°23'40.57"S 40°24'21.45"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 5th Feb 2021 | 5th June 2021 | 5th June 2021 | 6000025.2 | 5962629.75 | 6000025.2 | CGL | N/A | 5962629.75 | N/A | 5962629.75 | 100% | 5962629.75 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
398 | Majembeni - Sinambio Road 1 | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hongwe | 2°23'18.21"S 40°36'29.28"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 1st Feb 2021 | 31st May 2021 | 31st May 2021 | 9500001.9 | 9410685.6 | 9500001.9 | CGL | N/A | 9410685.6 | N/A | 9410685.6 | 100% | 9410685.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
399 | Majembeni - Sinambio Road 2 | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hongwe | 2°22'45.62"S 40°36'51.26"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 5th Feb 2021 | 5th June 2021 | 5th June 2021 | 9499962 | 9374501.02 | 9499962 | CGL | N/A | 9374501.02 | N/A | 9374501.02 | 100% | 9374501.02 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
400 | Mpeketoni-Baharini Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°23'41.81"S 40°41'57.58"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 3rd Feb 2021 | 3rd June 2021 | 3rd June 2021 | 3999918 | 3998809.07 | 3999918 | CGL | N/A | 3998809.07 | N/A | 3998809.07 | 100% | 3998809.07 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
401 | Mpeketoni-Ndambwe Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°19'02.73"S 40°43'07.16"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 1st Feb 2021 | 31st May 2021 | 31st May 2021 | 3999576 | 3940172 | 3999576 | CGL | N/A | 3940172 | N/A | 3940172 | 100% | 3940172 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
402 | Ngoi road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°22'48.61"S 40°45'17.37"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 4th Feb 2021 | 4th June 2021 | 4th June 2021 | 6000013.8 | 5995262.51 | 6000013.8 | CGL | N/A | 5995262.51 | N/A | 5995262.51 | 100% | 5995262.51 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
403 | Mpeketoni- Uziwa Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°21'32.97"S 40°44'19.33"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 1st Feb 2021 | 31st May 2021 | 31st May 2021 | 6000006.96 | 5999162.6 | 6000006.96 | CGL | N/A | 5999162.6 | N/A | 5999162.6 | 100% | 5999162.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
404 | Tewe Town Junction -Kiongwe Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°23'55.64"S 40°47'10.18"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 4th Feb 2021 | 4th June 2021 | 4th June 2021 | 8000002.44 | 7997910 | 8000002.44 | CGL | N/A | 7997910 | N/A | 7997910 | 100% | 7997910 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
405 | Nathan - Kizuke Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°19'49.31"S 40°44'45.43"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 4th Feb 2021 | 4th June 2021 | 4th June 2021 | 4000010.34 | 3998346.7 | 4000010.34 | CGL | N/A | 3998346.7 | N/A | 3998346.7 | 100% | 3998346.7 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
406 | Hindi -Hindi Magogoni Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°08'51.47"S 40°48'09.88"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 1st Feb 2021 | 31st May 2021 | 31st May 2021 | 6000020.64 | 5940543.28 | 6000020.64 | CGL | N/A | 5940543.28 | N/A | 5940543.28 | 100% | 5940543.28 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
407 | Ndeu Ecd - Hindi Magogoni Road 2 | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°11'33.60"S 40°47'08.24"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 4th Feb 2021 | 4th June 2021 | 4th June 2021 | 2069670 | 2067786.3 | 2069670 | CGL | N/A | 2067786.3 | N/A | 2067786.3 | 100% | 2067786.3 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
408 | A7 Junction - Mokowe Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°11'52.09"S 40°48'32.78"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 1st Feb 2021 | 31st May 2021 | 31st May 2021 | 3000115.2 | 2976919.6 | 3000115.2 | CGL | N/A | 2976919.6 | N/A | 2976919.6 | 100% | 2976919.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
409 | Lamu Boni Forest(Kiangwe - Basuba) Road | Opening of road | Improved accessibility | Murram Road Opened |  | Opening of Roads | Lamu east | Basuba | 1°56'12.50"S 40°58'07.32"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2020/2021 | 2nd Feb 2021 | 1st June 2021 | 1st June 2021 | 8000012.7 | 7941661.6 | 8000012.7 | CGL | N/A | 7941661.6 | N/A | 7941661.6 | 100% | 7941661.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
410 | Routine Maintenance of Kiongwe Mangu Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°21'47.69"S 40°45'41.61"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4997001.6 | 4997001.6 | CGL | N/A | 4997001.6 | N/A | 4997001.6 | 100% | 4997001.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
411 | Routine Maintenance of Kiongwe Ngoi Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°22'48.61"S 40°45'17.37"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4999405.12 | 4999405.12 | CGL | N/A | 4999405.12 | N/A | 4999405.12 | 100% | 4999405.12 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
412 | Routine Maintenance of Kiongwe Tewe Junction Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°23'55.64"S 40°47'10.18"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4969706.8 | 4969706.8 | CGL | N/A | 4969706.8 | N/A | 4969706.8 | 100% | 4969706.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
413 | Routine Maintenance of Umoja Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°22'32.28"S 40°40'39.71"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4999252 | 4999252 | CGL | N/A | 4999252 | N/A | 4999252 | 100% | 4999252 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
414 | Routine Maintenance of Lakeside Mpeketoni Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°23'36.14"S 40°41'02.73"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 3500000 | 3497811.8 | 3497811.8 | CGL | N/A | 3497811.8 | N/A | 3497811.8 | 100% | 3497811.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
415 | Routine Maintenance of Juakali Mkopwani Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari/Mkunumbi | 2°23'15.10"S 40°42'17.59"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4997454 | 4997454 | CGL | N/A | 4997454 | N/A | 4997454 | 100% | 4997454 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
416 | Routine Maintenance of Nadhan Bomani Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°22'20.87"S 40°39'27.76"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4998368.08 | 4998368.08 | CGL | N/A | 4998368.08 | N/A | 4998368.08 | 100% | 4998368.08 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
417 | Routine Maintenance of Uziwa Uzida Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°20'18.39"S 40°43'42.91"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4993867.28 | 4993867.28 | CGL | N/A | 4993867.28 | N/A | 4993867.28 | 100% | 4993867.28 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
418 | Routine Maintenance of Mkunumbi Bahati Njema Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°21'05.15"S 40°41'14.85"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4998440 | 4998440 | CGL | N/A | 4998440 | N/A | 4998440 | 100% | 4998440 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
419 | Routine Maintenance of Uziwa Ndambwe Mjini Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°19'52.28"S 40°44'47.11"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4998869.19 | 4998869.19 | CGL | N/A | 4998869.19 | N/A | 4998869.19 | 100% | 4998869.19 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
420 | Routine Maintenance of Juhudi Salama Marafa Witho Road 1 | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°18'42.44"S 40°36'24.27"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4957956.2 | 4957956.2 | CGL | N/A | 4957956.2 | N/A | 4957956.2 | 100% | 4957956.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
421 | Routine Maintenance of Juhudi Salama Marafa Witho Road 2 | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°15'34.83"S 40°36'28.72"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4951054 | 4951054 | CGL | N/A | 4951054 | N/A | 4951054 | 100% | 4951054 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
422 | Routine Maintenance of PCEA MauMau Kisimani Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hongwe | 2°20'56.60"S 40°39'35.71"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4998857.6 | 4998857.6 | CGL | N/A | 4998857.6 | N/A | 4998857.6 | 100% | 4998857.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
423 | Routine Maintenance of Witu Tangeni Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Witu | 2°22'03.96"S 40°27'48.30"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4998962 | 4998962 | CGL | N/A | 4998962 | N/A | 4998962 | 100% | 4998962 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
424 | Routine Maintenance of Witu Boko Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Witu | 2°20'25.07"S 40°26'07.91"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4982490 | 4982490 | CGL | N/A | 4982490 | N/A | 4982490 | 100% | 4982490 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
425 | Routine Maintenance of Moa Chalaluma Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Witu | 2°22'22.55"S 40°19'53.95"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4839868 | 4839868 | CGL | N/A | 4839868 | N/A | 4839868 | 100% | 4839868 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
426 | Routine Maintenance of Hindi Magogoni Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°08'51.47"S 40°48'09.88"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4994322 | 4994322 | CGL | N/A | 4994322 | N/A | 4994322 | 100% | 4994322 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
427 | Routine Maintenance of New Roads at Hindi Township | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°09'49.53"S 40°48'49.70"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 5000000 | 4986261.16 | 4986261.16 | CGL | N/A | 4986261.16 | N/A | 4986261.16 | 100% | 4986261.16 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
428 | Routine Maintenance of A7-junction Mokowe Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Hindi | 2°11'52.09"S 40°48'32.78"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 3500000 | 3380936 | 3380936 | CGL | N/A | 3380936 | N/A | 3380936 | 100% | 3380936 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
429 | Cabro paving at Hindi Town | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Hindi | 2°10'46.60"S 40°48'56.59"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 9258075.8 | 9258075.8 | CGL | N/A | 9258075.8 | N/A | 9258075.8 | 100% | 9258075.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
430 | Construction of Lamu Sea Wall and stairs from Donkey Hospital to Huduma Centre | Sea Wall Rehabilitation | Improved sea transport | Sea Wall Rehabilitated |  | Sea Wall Rehabilitation | Lamu west | Mkomani | 2°16'01.75"S 40°54'07.98"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 9336544 | 9336544 | CGL | N/A | 9336544 | N/A | 9336544 | 100% | 9336544 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
431 | Cabro Paving at Mkunumbi | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkunumbi | 2°18'11.30"S 40°42'15.30"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 9782929.6 | 9782929.6 | CGL | N/A | 9782929.6 | N/A | 9782929.6 | 100% | 9782929.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
432 | Cabro Paving at Pate | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Faza | 2°08'32.07"S 40°59'58.72"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 8944978.08 | 8944978.08 | CGL | N/A | 8944978.08 | N/A | 8944978.08 | 100% | 8944978.08 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
433 | Cabro Paving at Siyu | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Faza | 2°06'05.72"S 41°03'35.64"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 9863886 | 9863886 | CGL | N/A | 9863886 | N/A | 9863886 | 100% | 9863886 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
434 | Cabro Paving at Faza | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Faza | 2°03'28.50"S 41°06'40.56"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 8000000 | 7473207.2 | 7473207.2 | CGL | N/A | 7473207.2 | N/A | 7473207.2 | 100% | 7473207.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
435 | Cabro Paving at Mkomani | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkomani | 2°16'12.64"S 40°54'03.91"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-06-01 | 2023-06-01 | 10000000 | 9703446.4 | 9703446.4 | CGL | N/A | 9703446.4 | N/A | 9703446.4 | 100% | 9703446.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
436 | Cabro Paving of Shiban Road | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Shella | 2°17'34.44"S 40°54'41.18"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-12-01 | 2023-12-01 | 5000000 | 4999250.8 | 4999250.8 | CGL | N/A | 4999250.8 | N/A | 4999250.8 | 100% | 4999250.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
437 | Concrete Paving at Lamu | Cabro Paving of Roads | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkomani | 2°16'00.99"S 40°54'05.97"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2022/2023 | 2022-07-01 | 2023-12-01 | 2023-12-01 | 5000000 | 4937685 | 4937685 | CGL | N/A | 4937685 | N/A | 4937685 | 100% | 4937685 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
438 | Opening up of Hindi Kibokoni Road (Open Tender) | Opening of road | Improved accessibility | Murram Road Opened |  | Opening of Roads | Lamu west | Hindi | 2°12'00.89"S 40°46'43.29"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 26th January 2024 | 26th January 2024 | 10000000 | 9477362.4 | 9477362.4 | CGL | N/A | 9477362.4 | N/A | 9477362.4 | 100% | 9477362.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
439 | Opening of Kiangwe Ndununi Road (Reserved for Women) | Opening of road | Improved accessibility | Murram Road Opened |  | Opening of Roads | Lamu east | Basuba | 1°56'05.26"S 40°58'16.68"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 20th Nov 2023 | 20th Nov 2023 | 5000000 | 4999043.2 | 4999043.2 | CGL | N/A | 4999043.2 | N/A | 4999043.2 | 100% | 4999043.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
440 | Opening up of Hongwe Secondary School- Mtondoni Road (Open Tender) | Opening of road | Improved accessibility | Murram Road Opened |  | Opening of Roads | Lamu west | Hongwe | 2°21'11.80"S 40°38'47.03"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 2nd Nov 2023 | 2nd Nov 2023 | 8000000 | 7084642 | 7084642 | CGL | N/A | 7084642 | N/A | 7084642 | 100% | 7084642 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
441 | Routine maintenance of Theddy to Kwa Haruni road (Reserved for Women) | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°22'56.52"S 40°41'41.84"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 16th Nov 2023 | 16th Nov 2023 | 5000000 | 4,999,217.20 | 4,999,217.20 | CGL | N/A | 4,999,217.20 | N/A | 4,999,217.20 | 100% | 4,999,217.20 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
442 | Routine maintenance of Mkunumbi –Kibaoni road (Open Tender) | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Mkunumbi | 2°19'20.08"S 40°39'09.57"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 24th October 2023 | 24th October 2023 | 8400000 | 7921425.4 | 7921425.4 | CGL | N/A | 7921425.4 | N/A | 7921425.4 | 100% | 7921425.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
443 | Routine maintenance of Manda Access roads (Reserved for Women) | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Shella | 2°18'37.03"S 40°55'50.45"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 16th October 2023 | 16th October 2023 | 7000000 | 6702248 | 6702248 | CGL | N/A | 6702248 | N/A | 6702248 | 100% | 6702248 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
444 | Paved Walkways in Mkomani (Reserved for Youth) | Concrete Paving of road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkomani | 2°16'09.06"S 40°54'00.52"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 22nd February 2024 | 22nd February 2024 | 2000000 | 1991082 | 1991082 | CGL | N/A | 1991082 | N/A | 1991082 | 100% | 1991082 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
445 | Paved Walkways in Kiunga (Open Tender) | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Kiunga | 1°44'43.96"S 41°29'22.94"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 25th October 2023 | 25th October 2023 | 15000000 | 14824220 | 14824220 | CGL | N/A | 14824220 | N/A | 14824220 | 100% | 14824220 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
446 | Proposed Cabro works at Kizingitini (Open Tender) | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Faza | 2°04'18.90"S 41°08'37.84"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 31st October 2023 | 31st October 2023 | 10000000 | 9800260 | 9800260 | CGL | N/A | 9800260 | N/A | 9800260 | 100% | 9800260 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
447 | Routine maintenance of Stormwater Drainage System in Mpeketoni Town | Routine Maintenance of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Bahari | 2°23'19.62"S 40°41'57.06"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 19th December 2023 | 19th December 2023 | 2000000 | 1998853 | 1998853 | CGL | N/A | 1998853 | N/A | 1998853 | 100% | 1998853 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
448 | Improvement of Drainage in Witu Town (Reserved for Youth) | Routine Maintenance of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Witu | 2°23'17.27"S 40°26'19.36"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 26th October 2023 | 26th October 2023 | 8000000 | 7699442 | 7699442 | CGL | N/A | 7699442 | N/A | 7699442 | 100% | 7699442 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
449 | Routine maintenance of Mpeketoni – Bahari Road | Routine Maintenance of Road | Improved accessibility | Murram Road Maintained |  | Maintenance of Roads | Lamu west | Bahari | 2°23'41.81"S 40°41'57.58"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2023/2024 | 2023-07-01 | 26th March 2024 | 26th March 2024 | 5000000 | 4999000 | 4999000 | CGL | N/A | 4999000 | N/A | 4999000 | 100% | 4999000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
450 | Cabro Paving at Hindi Town | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Hindi | 2°10'46.11"S 40°48'56.05"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 17th Dec 2024 | 13th Feb 2025 | 13th Feb 2025 | 10000000 | 8713050 | 8713050 | CGL | N/A | 8713050 | N/A | 8713050 | 100% | 8713050 | N/A | N/A | Completed | 200% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
451 | Cabro Paving at Mkomani | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkomani | 2°16'19.02"S 40°54'03.37"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 20th Dec 2024 | 13th March 2025 | 13th March 2025 | 6500000 | 6237668 | 6237668 | CGL | N/A | 6237668 | N/A | 6237668 | 100% | 6237668 | N/A | N/A | Completed | 300% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
452 | Cabro Paving at Hongwe | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Hongwe | 2°21'04.13"S 40°40'01.77"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 15th Jan 2025 | 29th April 2025 | 29th April 2025 | 8569251 | 7801667 | 7801667 | CGL | N/A | 7801667 | N/A | 7801667 | 100% | 7801667 | N/A | N/A | Completed | 400% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
453 | Concrete Paving Concrete Walkways at Ndau | Concrete Paving of road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Kiunga | 2°00'47.39"S 41°12'46.84"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 20th Dec 2024 | 13th Feb 2025 | 13th Feb 2025 | 10000000 | 9474469 | 9474469 | CGL | N/A | 9474469 | N/A | 9474469 | 100% | 9474469 | N/A | N/A | Completed | 500% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
454 | Construction of Mbwajumwali Seawall & ladder | Sea Wall Construction | Improved sea transport | Sea Wall Constructed |  | Sea Wall Constructed | Lamu east | Faza | 2°04'38.64"S 41°07'51.41"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 28th Feb 2025 | 20th Jun 2025 | 20th Jun 2025 | 25000000 | 24972480 | 24972480 | CGL | N/A | 24972480 | N/A | 24972480 | 100% | 24972480 | N/A | N/A | Completed | 600% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
455 | Concrete blocks (cabro) paving Walkways at Tchudwa | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu east | Faza | 2°04'46.53"S 41°06'50.75"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 21st March 2025 | 29th April 2025 | 29th April 2025 | 10000000 | 8889254 | 8889254 | CGL | N/A | 8889254 | N/A | 8889254 | 100% | 8889254 | N/A | N/A | Completed | 700% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
456 | Cabro Paving at Shella | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Shella | 2°17'34.44"S 40°54'41.18"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 |  |  |  | 5000000 | 4999225 | 4999225 | CGL | N/A | 4999225 | N/A | 4999225 | 100% | 4999225 | N/A | N/A | Completed | 800% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
457 | Cabro Paving at Mkunumbi | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Mkunumbi | 2°18'23.25"S 40°42'17.31"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 2nd April 2025 | 29th April 2025 | 29th April 2025 | 3000000 | 2999006 | 2999006 | CGL | N/A | 2999006 | N/A | 2999006 | 100% | 2999006 | N/A | N/A | Completed | 900% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL
458 | Cabro Paving at ATC | Cabro Paving of Road | Improved transport services | Transport Improved |  | Roads and Transport | Lamu west | Bahari | 2°22'45.02"S 40°41'16.69"E | Roads, Transport Infrastructure | Roads | Infrastructure | 2024/2025 | 15th Jan 2025 | 13th Feb 2025 | 13th Feb 2025 | 2000000 | 1948104 | 1948104 | CGL | N/A | 1948104 | N/A | 1948104 | 100% | 1948104 | N/A | N/A | Completed | 1000% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | NO | Screening was not undertaken at the time of project planning; the county is strengthening screening in current and future projects. | no | Formal screening not done; safeguards will be incorporated in future project planning. | NO | Feasibility study not conducted; viability currently guided by sector priorities and budget allocation. | COMPLETE AND OPERATIONAL